## G1
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G1: Summary - Investment
|  |  |  | Actual and Forecast | [8 empty] | Confidence Grades
Line | Description | Units | Field | Actual Pre | Report Year -1 | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Post | Total | Actual Pre | Report Year -1 | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Forecast Post
Ref. |  |  | Type | [7 empty] | 2026-27 | [8 empty] | 2026-27
|  |  |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27 |  | 2021-22 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2026-27
Repair & Refurbishment - Water
G1.01 | Inspections and testing | £m | I | 6.812 | 11.153 | 15.5116 | 16.6974 | 20.757 | 6.4598 | 4.93 | 0.6939 | 75.5089 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.02 | Repair | £m | I | 202.4918 | 84.6658 | 109.226 | 102.4498 | 35.9197 | 26.7003 | 17.9646 | 29.2311 | 376.9261 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.03 | Refurbishment | £m | I | 87.3239 | 31.799 | 47.5781 | 45.3992 | 29.463 | 29.566 | 21.7277 | 15.9523 | 205.5328 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.04 | Total Repair & Refurbishment - Water | £m | C | 296.6277 | 127.6178 | 172.3157 | 164.5464 | 86.1397 | 62.726 | 44.6222 | 45.8773 | 657.9678
Repair & Refurbishment - Wastewater
G1.05 | Inspections and testing | £m | I | 5.6868 | 12.8323 | 12.7424 | 12.9711 | 17.021 | 11.6188 | 10.8531 | 2.9052 | 78.0386 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.06 | Repair | £m | I | 90.2274 | 81.2694 | 106.2596 | 82.0285 | 18.3291 | 4.7529 | 5.6664 | 2.3307 | 298.3059 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.07 | Refurbishment | £m | I | 40.4285 | 13.1042 | 21.3387 | 28.3034 | 28.8965 | 16.9678 | 9.1314 | 5.1769 | 117.742 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.08 | Total Repair & Refurbishment - Wastewater | £m | C | 136.3427 | 107.2059 | 140.3406 | 123.3029 | 64.2466 | 33.3395 | 25.6508 | 10.4128 | 494.0865
Repair & Refurbishment - General
G1.09 | Inspections and testing | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.10 | Repair | £m | I | 1.1933 | 1.2944 | 1.1694 | 1.35 | 0.76121 | 0.0006824 | -0.057575 | 4e-08 | 4.5181 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.11 | Refurbishment | £m | I | 0.96735 | 1.6204 | 2.1916 | 2.38 | 8.6238 | 5.6485 | 5.76 | 5.1231 | 26.2243 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.12 | Total Repair & Refurbishment - General | £m | C | 2.1606 | 2.9148 | 3.361 | 3.73 | 9.3851 | 5.6492 | 5.7024 | 5.1231 | 30.7424
Asset Replacement
G1.13 | Water Services | £m | I | 408.9605 | 118.1018 | 126.5447 | 146.7968 | 149.1713 | 85.7556 | 65.0331 | 56.3726 | 691.4032 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.14 | Wastewater Services | £m | I | 286.787 | 70.2081 | 75.7362 | 84.8138 | 88.6989 | 63.1183 | 60.3809 | 58.1155 | 442.9563 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.15 | Business Services | £m | I | 102.6767 | 35.3906 | 79.3275 | 109.3251 | 92.7282 | 23.3436 | 2.7634 | 1.668 | 342.8783 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.16 | Total Asset Replacement | £m | C | 798.4242 | 223.7004 | 281.6083 | 340.9358 | 330.5984 | 172.2175 | 128.1774 | 116.1561 | 1477.2378
Growth
G1.17 | Growth in the Water Network | £m | I | 48.3089 | 13.834 | 18.3479 | 22.6176 | 11.3572 | 27.1938 | 9.4961 | 2.3269 | 102.8465 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.18 | Growth in the Wastewater Network | £m | I | 101.4288 | 38.8982 | 53.1589 | 65.5674 | 134.1485 | 98.9352 | 66.3316 | 106.8461 | 457.0399 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.19 | Service Relocations Water | £m | I | 33.3132 | 3.5084 | 3.3781 | 2.5819 | 4.9078 | 1.4384 | 1.5234 | 0.58372 | 17.338 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.20 | Service Relocations Wastewater | £m | I | 8.1686 | 0.77394 | 0.33532 | 0.92051 | 2.8753 | 0.67854 | 0.67854 | 0.33308 | 6.2621 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.21 | Total Growth | £m | C | 191.2195 | 57.0146 | 75.2202 | 91.6874 | 153.2889 | 128.2459 | 78.0296 | 110.0898 | 583.4865
Enhancement
G1.22 | Circular Economy | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.23 | Climate Change, Adaptation and Mitigation | £m | I | 3.2371 | 3.56 | 6.0439 | 16.4413 | 15.8809 | 6.6703 | 5.0375 | 38.1938 | 53.6339 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.24 | Drinking Water | £m | I | 76.9258 | 58.7489 | 46.6839 | 66.0576 | 142.0491 | 194.6068 | 181.6455 | 264.5771 | 689.7917 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.25 | Environment | £m | I | 33.7031 | 10.4405 | 8.6504 | 10.3496 | 28.5102 | 19.2679 | 26.5364 | 145.6108 | 103.755 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.26 | Flooding/Surface Water Management | £m | I | 2.0459 | -0.50635 | 0.24002 | 0.12833 | 0 | 0.19097 | 0.0091129 | 0 | 0.062086 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.27 | Long Term Water Sector Vision | £m | I | 0 | 0.73461 | 0.77166 | 1.4937 | 0 | 0 | 0 | 0 | 3 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.28 | Other | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.29 | Private Finance Initiative Funded Contracts | £m | I | 0.25604 | 0.35955 | 20.2165 | 8.8003 | 0.79616 | 2.3427 | 19.8565 | 42.496 | 52.3717 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.30 | Security & Resilience | £m | I | 11.5624 | 1.2236 | 0.017599 | 0.67751 | 4.0317 | 0.17924 | 0.025392 | 0 | 6.155 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.31 | Standards of Service | £m | I | 85.9306 | 37.5133 | 38.6439 | 37.0229 | 70.7336 | 74.8883 | 62.5735 | 39.3099 | 321.3755 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.32 | Total Enhancement | £m | C | 213.661 | 112.0741 | 121.2678 | 140.9712 | 262.0015 | 298.1463 | 295.684 | 530.1875 | 1230.1449
Support
G1.33 | Asset Support Direct | £m | I | 15.8544 | 24.7222 | 22.7453 | 6.2521 | 4.1286 | 1.5335 | 1.995 | 0.34671 | 61.3767 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.34 | Asset Support Indirect | £m | I | 9.3685 | -1.9738 | -8.6127 | 8.3883 | 2.1574 | 2.1574 | 2.4194 | -0.12902 | 4.536 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.35 | Non Asset Support | £m | I | 0 | 2.891 | 10.4219 | 14.08 | 7.3225 | 1.4448 | 1.679 | 2.502 | 37.8393 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.36 | Total Support | £m | C | 25.2228 | 25.6395 | 24.5545 | 28.7203 | 13.6086 | 5.1357 | 6.0935 | 2.7197 | 103.7519
Completion Programme
G1.37 | SR10 Completion | £m | I | 517.6151 | 7.0609 | 1.4933 | 9.2514 | 17.5263 | 13.4054 | 0.89193 | 0.030544 | 49.6293 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.38 | SR15 Completion - Enhancement | £m | I | 495.6436 | 72.8527 | 31.4518 | 15.6747 | 9.5036 | 15.134 | 1.7115 | 0.8386 | 146.3283 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.39 | SR15 Completion - Growth | £m | I | 22.2466 | 6.1342 | 5.2917 | 4.239 | 0.079622 | 0 | -7.9 | 0 | 7.8445 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.40 | SR15 Completion - Exceptional Asset Maintenance | £m | I | 133.2156 | 32.2036 | 22.6394 | 19.5678 | 5.9726 | 0.0792 | 0.0662 | 0 | 80.5287 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.41 | Total Completion Programme | £m | C | 1168.7209 | 118.2513 | 60.8761 | 48.733 | 33.0822 | 28.6186 | -5.2303 | 0.86914 | 284.3308
Total Additional Operating Expenditure
G1.42 | Additional Operating Expenditure from Investment | £m | I | 0 | 0.89113 | -0.75487 | 1.3558 | 1.1638 | 1.7715 | 3.6942 | 3.7961 | 8.1215 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
Grants and Contributions
G1.43 | Grants for infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.44 | Grants for non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.45 | Contributions to infrastructure assets | £m | I | 0 | 10.2197 | 3.3754 | 7.3958 | 7.3958 | 7.3958 | 7.3958 | 0 | 43.1782 | A1 | A1 | A1 | B1 | B1 | B1 | B1 | B1
G1.46 | Contributions to non-infrastructure assets | £m | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.47 | Row intentionally blank
G1.48 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 7.3958 | 7.3958 | 7.3958 | 7.3958 | 0 | 43.1782
Unallocated Investment
G1.49 | Allowed For Investment Still to Be Allocated | £m | I |  | -20.2475 | -6.3853 | 34.2486 | 96.0015 | 374.1897 | 603.3844 | 0 | 1081.1914 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
Expenditure Totals
G1.50 | Repair & Refurbishment - Water | £m | C | 296.6277 | 127.6178 | 172.3157 | 164.5464 | 86.1397 | 62.726 | 44.6222 | 45.8773 | 657.9678
G1.51 | Repair & Refurbishment - Wastewater | £m | C | 136.3427 | 107.2059 | 140.3406 | 123.3029 | 64.2466 | 33.3395 | 25.6508 | 10.4128 | 494.0865
G1.52 | Repair & Refurbishment - General | £m | C | 2.1606 | 2.9148 | 3.361 | 3.73 | 9.3851 | 5.6492 | 5.7024 | 5.1231 | 30.7424
G1.53 | Asset Replacement | £m | C | 798.4242 | 223.7004 | 281.6083 | 340.9358 | 330.5984 | 172.2175 | 128.1774 | 116.1561 | 1477.2378
G1.54 | Growth | £m | C | 191.2195 | 57.0146 | 75.2202 | 91.6874 | 153.2889 | 128.2459 | 78.0296 | 110.0898 | 583.4865
G1.55 | Enhancement | £m | C | 213.661 | 112.0741 | 121.2678 | 140.9712 | 262.0015 | 298.1463 | 295.684 | 530.1875 | 1230.1449
G1.56 | Support | £m | C | 25.2228 | 25.6395 | 24.5545 | 28.7203 | 13.6086 | 5.1357 | 6.0935 | 2.7197 | 103.7519
G1.57 | Completion Programme | £m | C | 1168.7209 | 118.2513 | 60.8761 | 48.733 | 33.0822 | 28.6186 | -5.2303 | 0.86914 | 284.3308
G1.58 | Gross Investment | £m | C | 2832.3794 | 774.4184 | 879.5442 | 942.627 | 952.3508 | 734.0786 | 578.7296 | 821.4356 | 4861.7487
G1.59 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 7.3958 | 7.3958 | 7.3958 | 7.3958 | 0 | 43.1782
G1.60 | Net Investment | £m | C | 2832.3794 | 764.1987 | 876.1688 | 935.2313 | 944.9551 | 726.6829 | 571.3338 | 821.4356 | 4818.5706
G1.61 | Total Asset Additions | £m | C | 1598.8243 | 312.9795 | 281.9185 | 310.1119 | 461.9811 | 460.1464 | 374.5767 | 643.8662 | 2201.7142
G1.62 | Total Additional Operating Expenditure | £m | C | 0 | 0.89113 | -0.75487 | 1.3558 | 1.1638 | 1.7715 | 3.6942 | 3.7961 | 8.1215
Risk and Overhead Investment Breakdown
G1.63 | Direct costs | £m | I | [8 empty] | 4414.5865 | [7 empty] | A1
G1.64 | Project overheads allocated to projects | £m | I | [8 empty] | 341.7365 | [7 empty] | A1
G1.65 | Risk allowance | £m | I | [8 empty] | 105.4258 | [7 empty] | A1
G1.66 | Gross Investment | £m | C | [8 empty] | 4861.7487
Primary Purpose Investment Breakdown
G1.67 | Water | £m | I | 1552.8616 | 408.2892 | 430.006 | 461.5317 | 452.0572 | 403.0135 | 311.5057 | 399.1234 | 2466.4033 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.68 | Wastewater | £m | I | 1088.2809 | 304.4061 | 349.6486 | 338.7727 | 384.8652 | 295.8942 | 253.1094 | 412.2191 | 1926.6961 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.69 | General | £m | I | 191.2369 | 61.7231 | 99.8897 | 142.3227 | 115.4284 | 35.171 | 14.1145 | 10.0931 | 468.6493 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.70 | Gross Investment | £m | C | 2832.3794 | 774.4184 | 879.5442 | 942.627 | 952.3508 | 734.0786 | 578.7296 | 821.4356 | 4861.7487
Planned and Responsive Repair & Refurbishment
G1.71 | Responsive repair and refurbishment investment previously expensed as operating expenditure ('Tier 1') | £m | I | 19.434 | 53 | 58.0953 | 52.5142 | 0 | 0 | 7.2683e-07 | 2.9073e-08 | 163.6094 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.72 | Remaining responsive repair and refurbishment investment ('Tier 1') | £m | I | 280.3676 | 99.6429 | 134.8106 | 101.9141 | 42.752 | 16.0119 | 22.092 | 20.89 | 417.2235 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.73 | Planned repair and refurbishment investment ('Tier 2') | £m | I | 135.3294 | 85.0956 | 123.1115 | 137.151 | 117.0193 | 85.7028 | 53.8835 | 40.5232 | 601.9638 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.74 | Total Repair and Refurbishment | £m | C | 435.131 | 237.7385 | 316.0173 | 291.5793 | 159.7714 | 101.7147 | 75.9755 | 61.4132 | 1182.7967
Tier Investment Breakdown
G1.75 | Tier 1a | £m | I | 306.2687 | 152.9338 | 193.0195 | 155.3531 | 43.9533 | 16.0145 | 22.0941 | 20.89 | 583.3682 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.76 | Tier 2 - Pre Committed List | £m | I | 541.0854 | 37.9268 | 72.4803 | 324.4439 | 706.0686 | 650.9595 | 528.4405 | 789.2482 | 2320.3196 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.77 | Tier 2 - Committed List | £m | I | 1985.0253 | 583.5578 | 614.0445 | 462.83 | 202.329 | 67.1047 | 28.1949 | 11.2974 | 1958.0609 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.78 | Gross Investment | £m | C | 2832.3794 | 774.4184 | 879.5442 | 942.627 | 952.3508 | 734.0786 | 578.7296 | 821.4356 | 4861.7487
G1.79 | Tier 2 Investment for comparison to FD | £m | C | 1734.1537 | 387.8554 | 401.6546 | 439.8672 | 571.6047 | 538.4535 | 421.0645 | 684.3895 | 2760.4999
Comparison to Historical Investment Baseline
G1.80 | Water Reasonable Cost Contributions | £m | I | 55.4641 | 9.8301 | 9.9872 | 6.7982 | 5.4454 | 8.3883 | 8.4514 | 0 | 48.9006 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.81 | Wastewater Reasonable Cost Contributions | £m | I | 92.4341 | 14.734 | 22.6883 | 17.7816 | 10.6697 | 10.1626 | 8.8375 | 0 | 84.8738 | A1 | A1 | A1 | A1 | A1 | A1 | A1 | A1
G1.82 | Total Investment including Reasonable Cost Contributions | £m | C | 2980.2776 | 798.9826 | 912.2197 | 967.2068 | 968.466 | 752.6295 | 596.0185 | 821.4356 | 4995.5231
G1.83 | Infrastructure charge contributions for infrastructure assets | £m | I | 0 | 11.4288 | 17.0209 | 18.9208 | 18.9208 | 18.9208 | 18.9208 | 0 | 104.1329 | A1 | A1 | A1 | B1 | B1 | B1 | B1 | B1
G1.84 | Total capital contributions (excluding infrastructure charge contributions) | £m | C | 0 | 10.2197 | 3.3754 | 7.3958 | 7.3958 | 7.3958 | 7.3958 | 0 | 43.1782 | A1 | A1 | A1 | B1 | B1 | B1 | B1 | B1
G1.85 | Net Capital Investment | £m | C | 2980.2776 | 777.3341 | 891.8233 | 940.8902 | 942.1494 | 726.313 | 569.702 | 821.4356 | 4848.212
Prepared by: ……………………………………………...…..
Checked by: ……………………………………………...…..
Authorised by: ……………………………………………...….. |  | Date:

## G2a
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G2a: Summary - Outputs by Ministerial Objective
Line Ref | Field Type | Output Description | Output Units | Output code | Management Approach Reference(s) |  | Number of Outputs
[7 empty] | Pre-2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27 | Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Asset Maintenance
G2a.001 | I/C | Number of Transformation initiatives implemented | Number | O_TF1_E | MA104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Circular Economy
G2a.002 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation
G2a.003 | I/C | Wastewater Non Infrastructure - Sludge Treatment Facilities | Number | O_CM_STF | MA109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.004 | I/C | Reduction in energy usage through improved energy efficiency | GWh | O_LC1_E | MA027, MA077 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3.4197 | 15.2197 | 15.2197
G2a.005 | I/C | Increase in renewable energy generated | GWh | O_LC2_E1 | MA109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.006 | I/C | Number of studies complete | Number | O_LC2_E2 | MA109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.007 | I/C | Number of alternative fuel refuelling infrastructure points | Number | O_LV2_M | MA071 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2a.008 | I/C | Number of peatland catchment assessments | Number | O_OM8_E | MA028, MA077 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 12 | 12 | 12
G2a.009 | I/C | Number of Private Finance Initiative (PFI) sites returned to Scottish Water | Number | O_PF1_E | MA109 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.010 | I/C | Number of generators /turbines maintained | Number | O_RE1_M | MA056 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.011 | I/C | Number of education campaigns targeted at reducing water wastage in households | Number | O_SA11_E | MA099 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2a.012 | I/C | Number of Climate Change studies | Number | O_SE1_E | MA103 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.013 | I/C | Energy generated by hosting renewable energy at SW sites | GWh | O_SE2_E | MA101 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.22 | 2.4 | 3.2 | 5.2 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2a.014 | I/C | Number of studies complete | Number | O_SE2_E | MA101 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.22 | 2.4 | 3.2 | 5.2 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2a.015 | I/C | Number of sites assessed for renewable energy generation | Number | O_SE2_E2 | MA101 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 10 | 12 | 13.74 | 18.74 | 20.24 | 21.24 | 24.24 | 37.24 | 38.24 | 38.24 | 38.24 | 38.24 | 38.24 | 39.24 | 41.24 | 41.24
G2a.016 | I/C | Number of Climate Change studies | Number | O_SE3_E | MA077 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.017 | I/C | Number of Climate Change Audits | Number | O_SE4_E | MA102 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32
G2a.018 | I/C | Number of carbon capture sites established or supported | Number | O_SE8_E | MA077 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 7 | 48 | 48
G2a.019 | I/C | Number of renewable energy asset interventions | Number | O_SE9_M | MA056 |  | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23
G2a.020 | I/C | Number of studies complete | Number | O_WW5_E | MA076 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Drinking Water
G2a.021 | I/C | Number of Asset Inspections completed | Number | O_AI1_M | MA006, MA087 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.022 | I/C | Number of sites with enhanced metals removal | Number | O_DC1_E | MA006 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.023 | I/C | Number of WTW sites with phosphate equipment dosing optimised | Number | O_LD1_E1 | MA041 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5
G2a.024 | I/C | Number of sites where new phosphate monitoring equipment has been provided | Number | O_LD1_E3 | MA041 |  | 0 | 0 | 0 | 4 | 21 | 21 | 21 | 21 | 21 | 21 | 33 | 33 | 33 | 50 | 50 | 50 | 65 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67
G2a.025 | I/C | Number of lead communication pipes replaced | Number | O_LD2_E | MA041 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1945 | 1945 | 1945
G2a.026 | I/C | Number of properties with lead sampling and risk assessment completed | Number | O_LD4_E | MA041 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20004 | 20004
G2a.027 | I/C | Number of membranes replaced or maintained | Number | O_OM1_M1 | MA006 |  | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5
G2a.028 | I/C | Number of sites made compliant with standards | Number | O_OM12_E | IR 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.029 | I/C | Number of treated water storage asset interventions | Number | O_OM2_M1 | MA006 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.030 | I/C | Number of sample point interventions | Number | O_OM2_M2 | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.031 | I/C | Number of WTW sites made compliant with standards | Number | O_OM3_E | MA006 |  | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 12 | 19 | 39 | 66 | 74 | 77 | 78 | 79 | 80 | 84 | 84 | 85 | 87 | 88 | 90 | 96 | 99 | 132 | 132
G2a.032 | I/C | Number of WTW sites with auto-shutdown risk control interventions | Number | O_OM4_E | MA006 |  | 0 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 9 | 10 | 10 | 10 | 11 | 14 | 17 | 29 | 29
G2a.033 | I/C | Number of WTW sites with improved organics removal | Number | O_OM5_E | MA006 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.034 | I/C | Number of single supply standard products developed | Number | O_OM7_E | MA006 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.035 | I/C | Number of sites with emergency planning equipment interventions | Number | O_WR1_M | MA087 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.036 | I/C | Number of Resilience Improvements | Number | O_WR11_E | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.037 | I/C | Number of Water Supply Zones with improved resilience | Number | O_WR6_E | MA087 |  | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 10 | 10 | 10 | 13 | 17 | 20 | 21 | 23 | 23 | 24 | 24 | 24 | 28 | 28 | 29 | 30 | 34 | 34
G2a.038 | I/C | Number of WTW's with capacity restored | Number | O_WR7_E | MA006 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
G2a.039 | I/C | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA006 |  | 0 | 0 | 0 | 0 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
Environment
G2a.040 | I/C | Number of WTW sites with Legacy Sludge Issues resolved | Number | O_AD3_E | MA085 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 5 | 11 | 11
G2a.041 | I/C | Number of sites with abstraction and compensation monitoring equipment interventions | Number | O_AD4_M | MA063 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 6 | 6
G2a.042 | I/C | Number of sites with Water Framework Directive improvements | Number | O_AD6_E | MA063 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
G2a.043 | I/C | Number of WwTW sites with Environmental Pollution risk reduced | Number | O_BR2_E | MA085 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.044 | I/C | Number of industrial Emissions Directive compliance action plans | Number | O_BR3_E | MA077 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2a.045 | I/C | tbc | Number | O_IRNMO | IR 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.046 | I/C | Number of unsatisfactory intermittent discharges improved or removed | Number | O_IRUID | IR 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.047 | I/C | Number of continuous discharges improved or removed | Number | O_IRWWT | IR 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.048 | I/C | Number of catchments with intelligent network technology | Number | O_NI1_E1 | MA107 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.049 | I/C | Number of Event Duration Monitors (EDM) deployed | Number | O_NI1_E2 | MA107 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55 | 55
G2a.050 | I/C | Number of Combined Storm Overflow (CSO) screen interventions | Number | O_SN1_M8 | MA005 |  | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.051 | I/C | Number of unsatisfactory intermittent discharges improved or removed | Number | O_SN2_E | MA005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.052 | I/C | Number of unsatisfactory intermittent discharges (UID) improved or removed for aesthetics | Number | O_SN2_E1 | IR 18, MA005 |  | 0 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 16 | 19 | 19 | 19 | 23 | 24 | 24 | 24 | 24 | 29 | 32 | 36 | 38 | 44 | 45 | 51 | 75 | 75
G2a.053 | I/C | Number of unsatisfactory intermittent discharges (UID) improved or removed for water quality | Number | O_SN2_E2 | MA005 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.054 | I/C | Number of WWTW continuous discharges improved or removed | Number | O_WW2_E | MA005, MA084 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 32 | 32
G2a.055 | I/C | Number of studies complete | Number | O_WW3_E | IR 18, MA076, MA084 |  | 0 | 0 | 27 | 191 | 292 | 293 | 295 | 300 | 301 | 302 | 304 | 305 | 306 | 306 | 309 | 310 | 310 | 310 | 310 | 310 | 311 | 311 | 311 | 312 | 312 | 313 | 313
G2a.056 | I/C | Number of studies complete | Number | O_WW4_E | MA076 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Flooding and Surface Water Management
G2a.057 | I/C | No outputs identified for this ministerial objective |  | - |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Long Term Water Sector Vision
G2a.058 | I/C | Number of sites enabled for community access | Number | O_CR3_E | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.059 | I/C | Number of new top-up-from-the-tap points | Number | O_CR5_E | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2a.060 | I/C | Number of private water supplies investigated | Number | O_CR7_E | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.061 | I/C | Number of Hydro Nation ideas put into practice | Number | O_SE7_E | MA048 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Private Finance Initiative Funded Projects
G2a.062 | I/C | Number of Private Finance Initiative (PFI) sites returned to Scottish Water | Number | O_PF1_E | MA108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 7 | 7
G2a.063 | I/C | Number of approved plans for PFI Contracts transitioned to Scottish Water | Number | O_PF2_E | MA108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2
Security & Resilience
G2a.064 | I/C | Number of digital transformation interventions | Number | O_DI1_M | MA066 |  | 0 | 1 | 1 | 5 | 7 | 8 | 8 | 9 | 9 | 10 | 11 | 15 | 15 | 15 | 15 | 16 | 16 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2a.065 | I/C | Number of sites with water security interventions | Number | O_HS1_M10 | MA089 |  | 0 | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 204 | 204 | 204 | 204 | 204 | 205 | 505 | 506 | 506 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507
Standards of service
G2a.066 | I/C | Number of WTW sludge handling asset interventions | Number | O_AD1_M | MA025, MA052, MA093 |  | 0 | 14 | 45 | 66 | 75 | 110 | 122 | 137 | 176 | 263 | 266 | 273 | 275 | 276 | 276 | 276 | 278 | 278 | 278 | 278 | 279 | 279 | 280 | 281 | 281 | 282 | 282
G2a.067 | I/C | Number of leakage management equipment interventions | Number | O_AD5_M | MA037, MA073 |  | 0 | 0 | 0 | 1 | 3 | 5 | 9 | 11 | 16 | 31 | 35 | 42 | 49 | 717 | 1928 | 1928 | 1932 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 1934 | 2540 | 2540
G2a.068 | I/C | Number of sites with Water Framework Directive improvements | Number | O_AD6_E | MA063 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.069 | I/C | Number of Asset Inspections completed | Number | O_AI1_M | MA002, MA004, MA012, MA014, MA016, MA017, MA023, MA025, MA033, MA037, MA039, MA042, MA043, MA046, MA057, MA058, MA082, MA091, MA094, MA096, SR15 |  | 0 | 6 | 69 | 1275 | 1335 | 1369 | 1389 | 1389 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487 | 1487 | 1487
G2a.070 | I/C | Number of sludge treatment centre asset interventions | Number | O_BR1_M | MA024, MA043, MA057 |  | 0 | 17 | 49 | 72 | 99 | 123 | 128 | 150 | 179 | 280 | 282 | 292 | 294 | 297 | 300 | 300 | 300 | 300 | 300 | 301 | 302 | 303 | 309 | 309 | 329 | 332 | 332
G2a.071 | I/C | Number of WwTW sites with Environmental Pollution risk reduced | Number | O_BR2_E | MA084 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
G2a.072 | I/C | Number of plans to improve customer experience | Number | O_CE1_E1 | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4
G2a.073 | I/C | Number of process improvements to support improved response to priority service customers | Number | O_CE1_E2 | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.074 | I/C | Number of plans to improve customer experience developed | Number | O_CE3_E | MA110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.075 | I/C | Investigations | Number | O_CM_INV | MA002, MA003, MA062 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695 | 703 | 703 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2a.076 | I/C | Water Infrastructure - Reservoir Maintenance | Number | O_CM_RES | MA004 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.077 | I/C | Wastewater Infrastructure Sewers | Number | O_CM_SEW | MA014 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.078 | I/C | Wastewater Non Infrastructure - Sludge Treatment Facilities | Number | O_CM_STF | MA024 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.079 | I/C | Water Non Infrastructure - Treated Water Pumping | Number | O_CM_TWP | MA082 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4
G2a.080 | I/C | Number of sites with metals removal interventions | Number | O_DC1_M | MA033 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
G2a.081 | I/C | Length of water main replaced or refurbished | Metres | O_DC2_E | MA016 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 7432 | 7433 | 7943 | 10283 | 11483 | 11483 | 11483 | 11483 | 14230 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2a.082 | I/C | Length of water mains cleaned | Metres | O_DC2_M | MA016 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106687 | 106687 | 106687 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 638649 | 638649 | 638649 | 638649 | 647649 | 647649 | 647649 | 647649
G2a.083 | I/C | Length of water mains cleaned | Metres | O_DC2_M1 | MA016, MA099, SR15 |  | 0 | 0 | 449939 | 2249939 | 2249939 | 2249939 | 2249939 | 2249940 | 2257940 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2a.084 | I/C | Length of water mains replaced or refurbished | Metres | O_DC2_M2 | MA016 |  | 0 | 0 | 0 | 1 | 257 | 358 | 1941 | 1942 | 9546 | 27948 | 29299 | 30730 | 30730 | 30730 | 30730 | 30730 | 32734 | 32736 | 32736 | 32736 | 32737 | 32737 | 32737 | 33987 | 33987 | 33987 | 33987
G2a.085 | I/C | Number of plans to improve customer experience | Number | O_DC4_E | MA016 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.086 | I/C | Number of digital transformation interventions | Number | O_DI1_M | MA066 |  | 0 | 5 | 6 | 8 | 10 | 13 | 13 | 13 | 13 | 17 | 19 | 22 | 23 | 26 | 29 | 30 | 31 | 33 | 33 | 33 | 4534 | 4534 | 4534 | 4534 | 4538 | 4538 | 4538
G2a.087 | I/C | Increase in Part 4 capacity to meet local growth requirements | Population Equivalent | O_ED3_G | MA017, MA043 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114 | 1114
G2a.088 | I/C | Number of properties removed from internal flooding at risk register. | Number | O_FR1_F1 | MA020, MA039, SR15 |  | 0 | 10 | 11 | 149 | 167 | 175 | 182 | 196 | 223 | 234 | 236 | 242 | 244 | 245 | 282 | 295 | 297 | 301 | 318 | 335 | 349 | 357 | 375 | 384 | 404 | 457 | 457
G2a.089 | I/C | Number of properties with temporary internal flood prevention measures | Number | O_FR1_F2 | MA020 |  | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 219 | 219
G2a.090 | I/C | Number of properties removed from external flooding at risk register. | Number | O_FR2_F | MA020, SR15 |  | 0 | 8 | 10 | 19 | 49 | 49 | 54 | 54 | 55 | 81 | 86 | 89 | 91 | 115 | 122 | 122 | 122 | 122 | 201 | 249 | 257 | 322 | 331 | 350 | 364 | 391 | 391
G2a.091 | I/C | Number of flood risk management (Section 16) models | Number | O_FR3_F | MA020 |  | 0 | 2 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10
G2a.092 | I/C | Number of education campaigns targeted at customers in sewer choke hot spot areas | Number | O_FR5_F2 | MA020 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.093 | I/C | Number of reservoir interests of Safety interventions | Number | O_HS1_M1 | MA004 |  | 0 | 5 | 16 | 32 | 43 | 78 | 137 | 156 | 213 | 235 | 267 | 312 | 323 | 352 | 364 | 368 | 378 | 383 | 385 | 391 | 404 | 415 | 417 | 418 | 419 | 422 | 422
G2a.094 | I/C | Number of sites with standby power equipment interventions | Number | O_HS1_M11 | MA092, MA096 |  | 0 | 15 | 18 | 25 | 41 | 50 | 292 | 296 | 299 | 308 | 308 | 310 | 310 | 310 | 311 | 312 | 313 | 313 | 314 | 314 | 314 | 314 | 316 | 316 | 316 | 323 | 323
G2a.095 | I/C | Number of water sites with telemetry interventions | Number | O_HS1_M12 | MA022, MA044 |  | 0 | 3 | 5 | 220 | 225 | 227 | 227 | 227 | 227 | 239 | 244 | 245 | 247 | 247 | 350 | 536 | 608 | 608 | 710 | 793 | 853 | 853 | 853 | 853 | 853 | 854 | 854
G2a.096 | I/C | Number of water property operational buildings interventions | Number | O_HS1_M13 | MA015, MA025, MA096 |  | 1 | 23 | 58 | 90 | 111 | 117 | 129 | 135 | 150 | 367 | 370 | 390 | 397 | 399 | 506 | 506 | 511 | 511 | 512 | 513 | 515 | 516 | 517 | 517 | 517 | 517 | 517
G2a.097 | I/C | Number of raw water storage asset interventions | Number | O_HS1_M2 | MA025, MA074, MA094 |  | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2a.098 | I/C | Number of water pipe bridge interventions | Number | O_HS1_M3 | MA003, MA016, MA025, MA070 |  | 0 | 0 | 0 | 2 | 5 | 5 | 7 | 11 | 18 | 37 | 39 | 40 | 40 | 45 | 45 | 47 | 47 | 47 | 104 | 104 | 121 | 190 | 190 | 194 | 195 | 375 | 375
G2a.099 | I/C | Number of fixed wire electrical system or statutory maintenance asset interventions | Number | O_HS1_M4 | MA068 |  | 0 | 0 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2a.100 | I/C | Number of SCADA, HMI, PLC asset interventions | Number | O_HS1_M5 | MA022, MA091, MA095 |  | 0 | 3 | 9 | 41 | 51 | 52 | 54 | 55 | 60 | 67 | 67 | 73 | 76 | 82 | 83 | 251 | 253 | 257 | 258 | 269 | 273 | 290 | 300 | 305 | 447 | 474 | 474
G2a.101 | I/C | Number of WTW Chemical Storage and Dosing Vessel interventions | Number | O_HS1_M6 | MA046, MA095, MA096 |  | 0 | 1 | 4 | 120 | 120 | 120 | 123 | 125 | 128 | 183 | 184 | 189 | 191 | 193 | 750 | 752 | 755 | 757 | 1111 | 1111 | 1112 | 1112 | 1112 | 1131 | 1131 | 1131 | 1131
G2a.102 | I/C | Number of street furniture interventions | Number | O_HS1_M7 | MA018 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.103 | I/C | Number of high voltage system interventions | Number | O_HS1_M8 | MA058, MA091, MA092 |  | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 7 | 31 | 31 | 33 | 33 | 33 | 33 | 33 | 33 | 36 | 36 | 45 | 45 | 46 | 46 | 46 | 51 | 60 | 60
G2a.104 | I/C | Number of water sites with Motor Control Centre interventions | Number | O_HS1_M9 | MA025, MA082, MA091, MA092, MA094 |  | 0 | 1 | 2 | 3 | 4 | 18 | 19 | 19 | 20 | 123 | 123 | 256 | 258 | 258 | 258 | 258 | 258 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 268 | 268
G2a.105 | I/C | Number of sites with water security enhancements | Number | O_HS2_E | MA089 |  | 0 | 0 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2a.106 | I/C | Number of sites with reservoir drawdown enhancements | Number | O_HS3_E | MA004 |  | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 15 | 15
G2a.107 | I/C | Number of interventions to reduce risk of flooding from mains | Number | O_HS4_E | MA025, MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5
G2a.108 | I/C | Number of sites with catchment management safety interventions | Number | O_HS5_M | _MA_proj_app_W |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.109 | I/C | Number of innovation pilot programmes undertaken | Number | O_IN1_M | MA048, SR15 |  | 0 | 0 | 0 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 157 | 157
G2a.110 | I/C | Number of Transformation activities enabled | Number | O_IN2_M | MA104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 16 | 19 | 19 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22
G2a.111 | I/C | Number of scientific services facilities upgraded | Number | O_JH1_M | _MA_proj_app_SS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3
G2a.112 | I/C | Number of Phosphate Equipment asset interventions | Number | O_LD1_M | MA094 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.113 | I/C | Number of Phosphate Equipment asset interventions | Number | O_LD1_M1 | MA046, MA094 |  | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 7 | 7 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2a.114 | I/C | Number of WTW Instrumentation interventions | Number | O_LD1_M2 | MA095 |  | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2a.115 | I/C | Number of vehicle or plant item interventions | Number | O_LV1_M | MA071 |  | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 1782 | 1782 | 1782 | 1782 | 1782
G2a.116 | I/C | Number of existing meter interventions | Number | O_MR1_M | MA034 |  | 0 | 0 | 0 | 0 | 0 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2a.117 | I/C | Number of properties with meter installations for first time registered non domestic premises | Number | O_MR2_G | MA034 |  | 0 | 0 | 0 | 0 | 0 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2a.118 | I/C | Number of catchments with intelligent network technology | Number | O_NI1_E1 | MA104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2a.119 | I/C | Number of Event Duration Monitors (EDM) deployed | Number | O_NI1_E2 | MA104 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2a.120 | I/C | Number of Programme Overhead management lines | Number | O_OH1_M | SR21_Prog_Over |  | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 18 | 20 | 20
G2a.121 | I/C | Number of membranes replaced or maintained | Number | O_OM1_M1 | MA033, MA094 |  | 0 | 1 | 2 | 4 | 7 | 14 | 16 | 78.7 | 92.7 | 139.7 | 146.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 152.7 | 220.7 | 220.7 | 220.7 | 221.7 | 222.7 | 222.7 | 222.7 | 222.7
G2a.122 | I/C | Number of WTW sand filters with media replaced | Number | O_OM1_M2 | MA033, MA094 |  | 6 | 7 | 12 | 22 | 34 | 35 | 47 | 48 | 49 | 52 | 58 | 59 | 75 | 114 | 114 | 114 | 114 | 115 | 150 | 151 | 151 | 159 | 159 | 168 | 168 | 174 | 174
G2a.123 | I/C | Number of WTW Granular Activated Carbon (GAC) filters with media replaced | Number | O_OM1_M3 | MA033 |  | 0 | 0 | 1 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2a.124 | I/C | Number of WTW chemical storage and dosing interventions | Number | O_OM1_M4 | MA025, MA033, MA046 |  | 0 | 13 | 57 | 86 | 853 | 1011 | 1050 | 1079 | 1108 | 1249 | 1571 | 1594 | 1610 | 1622 | 1633 | 1668 | 1671 | 1679 | 1715 | 1723 | 1734 | 1749 | 1751 | 1756 | 1756 | 1767 | 1767
G2a.125 | I/C | Number of Filtration and disinfection asset interventions | Number | O_OM1_M5 | MA033, MA093, MA094 |  | 0 | 33 | 92 | 146 | 209 | 393 | 477 | 618 | 864 | 1305 | 1317 | 1336 | 1343 | 1345 | 1347 | 1347 | 1349 | 1349 | 1350 | 1352 | 1356 | 1357 | 1357 | 1360 | 1360 | 1369 | 1369
G2a.126 | I/C | Number of WTW instrumentation interventions | Number | O_OM1_M6 | MA095 |  | 0 | 10 | 26 | 149 | 181 | 205 | 213 | 215 | 219 | 241 | 244 | 252 | 294 | 316 | 320 | 320 | 326 | 334 | 345 | 349 | 349 | 351 | 351 | 351 | 363 | 426 | 426
G2a.127 | I/C | Number of catchments managed to protect and improve water quality | Number | O_OM10_M | MA096 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 10 | 12 | 16 | 17 | 18 | 18 | 19 | 21 | 21 | 49 | 49 | 49 | 51 | 52 | 52 | 53 | 54 | 54
G2a.128 | I/C | Number of treated water storage or secondary disinfection asssets replaced or maintained | Number | O_OM2_M | MA025, MA037, MA081, MA106 |  | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 15 | 111 | 247 | 255 | 258 | 259 | 259 | 404 | 404 | 404 | 408 | 409 | 410 | 411 | 413 | 413 | 413 | 414 | 414 | 414
G2a.129 | I/C | Number of treated water storage asset interventions | Number | O_OM2_M1 | MA037, MA046, MA095, MA106 |  | 0 | 16 | 67 | 93 | 167 | 206 | 239 | 291 | 360 | 423 | 426 | 429 | 481 | 685 | 747 | 747 | 751 | 871 | 879 | 1026 | 1027 | 1027 | 1028 | 1029 | 1030 | 1040 | 1040
G2a.130 | I/C | Number of sample point interventions | Number | O_OM2_M2 | MA081, MA092 |  | 0 | 0 | 3 | 8 | 12 | 12 | 82 | 122 | 147 | 149 | 236 | 514 | 514 | 514 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588 | 588
G2a.131 | I/C | Number of secondary disinfection asset interventions | Number | O_OM2_M3 | MA037, MA106 |  | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 13 | 25 | 25 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2a.132 | I/C | Number of WTW sites made compliant with standards | Number | O_OM3_E | MA100 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 148 | 148 | 148 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149
G2a.133 | I/C | Numberof treated water storage operability (by-pass) interventions | Number | O_OM6_E | MA037 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 10 | 11 | 12 | 12 | 13 | 30 | 68 | 69 | 70 | 72 | 72
G2a.134 | I/C | Number of treated water storage by-pass interventions | Number | O_OM6_M | MA037 |  | 0 | 0 | 2 | 9 | 15 | 22 | 24 | 26 | 34 | 106 | 115 | 115 | 115 | 115 | 117 | 117 | 120 | 121 | 123 | 123 | 124 | 139 | 159 | 166 | 167 | 187 | 187
G2a.135 | I/C | Number ATOM water asset interventions | Number | O_OM9_M | MA068 |  | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2a.136 | I/C | Number of property asset interventions | Number | O_PE1_M | MA029, MA096 |  | 0 | 0 | 114 | 116 | 118 | 121 | 122 | 122 | 123 | 123 | 125 | 127 | 127 | 135 | 376 | 377 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 379 | 379 | 379 | 379
G2a.137 | I/C | Revised Bathing Water Directive (proposed) | Number | O_pEC16 | MA049 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.138 | I/C | Length of trunk mains replaced or maintained | Metres | O_SA1_M | MA001, MA025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | 5200 | 5222 | 5544 | 5545 | 5545 | 12945.05 | 24887.05 | 24887.05 | 24887.05 | 24887.05 | 24887.05 | 24906.6 | 24906.6 | 24906.6 | 24906.9 | 24906.9 | 24906.9 | 24906.9
G2a.139 | I/C | Length of trunk main interventions to address recurring customer interruptions to supply | Metres | O_SA1_M1 | MA001, MA025 |  | 0 | 890 | 1260 | 1260 | 1260 | 1260 | 4992 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2a.140 | I/C | Length of trunk main interventions | Metres | O_SA1_M2 | MA025 |  | 0 | 100 | 100 | 260 | 14550 | 14750 | 14751 | 14752 | 14753 | 14756 | 14758 | 15033 | 31735 | 65577 | 77078 | 77079 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79630 | 79630
G2a.141 | I/C | Number of water demand management interventions | Number | O_SA10_M | MA099 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 103 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
G2a.142 | I/C | Number of plans to improve customer experience | Number | O_SA12_E | MA001 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.143 | I/C | Number of raw water intake interventions | Number | O_SA2_M | MA025 |  | 0 | 1 | 2 | 6 | 7 | 9 | 10 | 11 | 14 | 27 | 27 | 31 | 38 | 45 | 342 | 345 | 348 | 348 | 348 | 349 | 350 | 350 | 351 | 352 | 352 | 353 | 353
G2a.144 | I/C | Number of treated water pump interventions | Number | O_SA3_M1 | MA015, MA058 |  | 0 | 9 | 22 | 32 | 45 | 55 | 61 | 74 | 130 | 182 | 185 | 190 | 193 | 202 | 307 | 311 | 314 | 314 | 314 | 315 | 321 | 321 | 321 | 321 | 321 | 356 | 356
G2a.145 | I/C | Number of raw water pump interventions | Number | O_SA3_M2 | MA058, MA096 |  | 0 | 2 | 8 | 12 | 17 | 20 | 23 | 27 | 33 | 46 | 46 | 46 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 52 | 53 | 53
G2a.146 | I/C | Length of raw water mains interventions | Metres | O_SA4_M | MA025 |  | 0 | 0 | 41 | 395 | 491 | 492 | 842 | 842 | 4759 | 4759 | 4760 | 4761 | 4761 | 4771 | 4771 | 9027 | 9027 | 9028 | 9028 | 9034 | 9034 | 9034 | 9035 | 9035 | 9035 | 9036 | 9036
G2a.147 | I/C | Length of aqueducts or tunnel interventions | Metres | O_SA5_M | MA025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36200 | 36251 | 36251 | 43127 | 45227 | 45235 | 45311 | 45313 | 330313 | 330664 | 330664 | 330664 | 330666 | 330666 | 330666 | 330668 | 330668 | 358669 | 358669
G2a.148 | I/C | Length of new or enhanced distribution mains | Metres | O_SA6_E | MA001, MA015, MA037, MA087 |  | 0 | 0 | 0 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2a.149 | I/C | Length of distribution mains interventions | Metres | O_SA6_M1 | MA001, MA015 |  | 0 | 0 | 0 | 250 | 250 | 4034 | 7469 | 29070 | 37387 | 37654 | 40754 | 41051 | 41351 | 41852 | 41852 | 41852 | 43852 | 45052 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 45215 | 46730 | 46730
G2a.150 | I/C | Length of distribution mains interventions | Number | O_SA6_M1 | MA001, MA015 |  | 0 | 0 | 0 | 250 | 250 | 4034 | 7469 | 29070 | 37387 | 37654 | 40754 | 41051 | 41351 | 41852 | 41852 | 41852 | 43852 | 45052 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 45215 | 46730 | 46730
G2a.151 | I/C | Length of distribution mains interventions to address recurring customer interruptions to supply | Metres | O_SA6_M2 | MA001, MA015, MA016, MA037, SR15 |  | 0 | 21244 | 31136 | 60922 | 89127 | 91620 | 104741 | 115301 | 161137.88 | 194955.88 | 243085.88 | 264772.98 | 296956.98 | 358028.98 | 394306.08 | 421278.28 | 480447.28 | 620843.28 | 632756.28 | 667961.91 | 716276.91 | 738771.91 | 738773.01 | 738773.01 | 738773.01 | 743673.01 | 743673.01
G2a.152 | I/C | Length of mains with pressure management intervention | Metres | O_SA6_M3 | MA015 |  | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2a.153 | I/C | Length of mains with pressure management intervention | Number | O_SA6_M3 | MA015 |  | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2a.154 | I/C | Number of properties where persistent low pressure is resolved | Number | O_SA7_E | MA001, MA070 |  | 0 | 0 | 0 | 0 | 7 | 8 | 11 | 11 | 12 | 16 | 16 | 35 | 37.4 | 38.4 | 56.4 | 62.4 | 70.4 | 70.4 | 70.4 | 70.4 | 73.4 | 73.4 | 73.4 | 73.4 | 73.4 | 174.4 | 174.4
G2a.155 | I/C | Number of borehole interventions | Number | O_SA8_M | MA080 |  | 0 | 0 | 4 | 8 | 36 | 59 | 60 | 64 | 72 | 89 | 90 | 217 | 218 | 228 | 228 | 246 | 250 | 250 | 284 | 284 | 284 | 284 | 291 | 291 | 291 | 291 | 291
G2a.156 | I/C | Number of sub-sea main interventions | Number | O_SA9_M | MA025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4
G2a.157 | I/C | Number of scientific equipment instruments replaced | Number | O_SC1_M | MA053 |  | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2a.158 | I/C | Number of sites assessed for renewable energy generation | Number | O_SE2_E2 | SR15 |  | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2a.159 | I/C | Length of critical sewers interventions | Metres | O_SN1_M1 | MA002, MA012, MA014 |  | 0 | 500 | 1309 | 1692 | 1694 | 2939 | 2943 | 55011.01 | 164577.01 | 171271.01 | 171404.01 | 171412.01 | 171425.01 | 171856.01 | 171856.01 | 171857.01 | 174452.01 | 174974.05 | 174975.05 | 175395.05 | 175395.05 | 177695.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05
G2a.160 | I/C | Number of Legacy sewage pumping stations improved to meet appropriate standard | Number | O_SN1_M10 | MA023 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
G2a.161 | I/C | Number of wastewater Network Motor Control Centre interventions | Number | O_SN1_M11 | MA011, MA023 |  | 0 | 6 | 6 | 13 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20
G2a.162 | I/C | Number of sites with wastewater pipebridge interventions | Number | O_SN1_M12 | MA003, MA014, MA062 |  | 0 | 0 | 1 | 10 | 17 | 18 | 20 | 23 | 26 | 28 | 28 | 32 | 33 | 33 | 35 | 41 | 41 | 46 | 58 | 61 | 62 | 62 | 63 | 63 | 63 | 63 | 63
G2a.163 | I/C | Number of screw pumps intervention | Number | O_SN1_M13 | MA023, MA036 |  | 0 | 0 | 1 | 1 | 3 | 5 | 5 | 5 | 8 | 11 | 11 | 11 | 11 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2a.164 | I/C | Number of sites with sewage pumping station interventions | Number | O_SN1_M14 | MA012, MA017, MA023, MA043, MA057, MA062 |  | 0 | 91 | 215 | 329 | 397 | 530 | 593 | 679 | 776 | 1129 | 1143 | 1162 | 1171 | 1176 | 1208 | 1215 | 1419 | 1422 | 1425 | 1429 | 1429 | 1430 | 1432 | 1433 | 1435 | 1444 | 1444
G2a.165 | I/C | Number of wastewater network models maintained | Number | O_SN1_M15 | MA054 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 207
G2a.166 | I/C | Number of storm tank interventions | Number | O_SN1_M16 | MA039, MA062 |  | 0 | 1 | 3 | 4 | 4 | 11 | 12 | 13 | 15 | 25 | 25 | 26 | 27 | 28 | 28 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66 | 66
G2a.167 | I/C | Number of sites with sewer structure syphons interventions | Number | O_SN1_M17 | MA062 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2a.168 | I/C | Number of wastewater property operational building interventions | Number | O_SN1_M18 | MA096 |  | 0 | 0 | 1 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2a.169 | I/C | Length of wastewater pumping main interventions | Metres | O_SN1_M2 | MA012 |  | 0 | 455 | 457 | 838 | 919 | 2221 | 5723 | 10653 | 11238 | 11273 | 12073 | 12084 | 13085.32 | 14210.32 | 16040.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32 | 17390.32
G2a.170 | I/C | Number of Sustainable Drainage system interventions | Number | O_SN1_M20 | MA062 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.171 | I/C | Number of high voltage system interventions | Number | O_SN1_M22 | MA091 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7 | 7 | 7
G2a.172 | I/C | Length of sea outfalls replaced or maintained | Metres | O_SN1_M3 | MA035 |  | 0 | 0 | 2 | 12 | 15 | 17 | 118 | 515 | 517 | 517 | 517 | 631 | 635 | 636 | 654 | 670 | 670 | 980 | 1085 | 1185 | 1189 | 1189 | 1189 | 1326 | 1327 | 1327 | 1327
G2a.173 | I/C | Length of non-critical sewer interventions | Metres | O_SN1_M4 | MA002, MA003, MA012, MA014, MA062 |  | 0 | 629 | 905 | 2498 | 2875 | 3056 | 4752 | 4827 | 7868 | 8931 | 9600 | 10069 | 10502 | 10647 | 12207 | 14006 | 14166 | 14270.01 | 16339.01 | 16617.01 | 17007.01 | 18618.01 | 18619.01 | 18750.01 | 18750.01 | 20326.01 | 20326.01
G2a.174 | I/C | Number of street furniture interventions | Number | O_SN1_M5 | MA018 |  | 0 | 0 | 0 | 1 | 1 | 4 | 8 | 16 | 21 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2a.175 | I/C | Number of air valves interventions at wastewater pumping mains | Number | O_SN1_M6 | MA012 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37 | 37 | 37
G2a.176 | I/C | Number of sites with sewer structures APNRV intervention | Number | O_SN1_M7 | MA062 |  | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2a.177 | I/C | Number of Combined Storm Overflow (CSO) screen interventions | Number | O_SN1_M8 | MA017, MA023, MA039, MA043, MA062 |  | 0 | 2 | 4 | 7 | 8 | 8 | 10 | 12 | 13 | 21 | 24 | 24 | 28 | 28 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 32 | 32
G2a.178 | I/C | Number of fixed wire electrical system or statutory maintenance asset interventions | Number | O_SN1_M9 | MA068 |  | 0 | 0 | 0 | 0 | 0 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2a.179 | I/C | Number of unsatisfactory intermittent discharges (UID) improved or removed for water quality | Number | O_SN2_E2 | SR15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.180 | I/C | Number of Transformation initiatives implemented | Number | O_TF1_E | MA104 |  | 0 | 0 | 0 | 0 | 2 | 10 | 12 | 13 | 18 | 24 | 34 | 36 | 43 | 46 | 48 | 50 | 54 | 56 | 57 | 57 | 58 | 58 | 58 | 58 | 65 | 67 | 67
G2a.181 | I/C | Number of sites with emergency planning equipment installed | Number | O_WR1_E1 | MA098 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.182 | I/C | Number of sites with standby power equipment installed | Number | O_WR1_E2 | MA092 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.183 | I/C | Number of sites with emergency planning equipment interventions | Number | O_WR1_M | MA098 |  | 0 | 0 | 0 | 4 | 5 | 5 | 6 | 6 | 6 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2a.184 | I/C | Number of strategic network valve interventions | Number | O_WR2_M | MA060 |  | 0 | 0 | 4 | 6 | 6 | 52009 | 52009 | 52010 | 52013 | 52024 | 52031 | 52032 | 52032 | 52034 | 52034 | 52035 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52916 | 52916 | 52916
G2a.185 | I/C | Number of water hydraulic models maintained | Number | O_WR4_M | MA054 |  | 0 | 0 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2a.186 | I/C | Number of WTW's with capacity restored | Number | O_WR7_E | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.187 | I/C | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.188 | I/C | Number of sites with security fending or gate interventions - wastewater | Metres | O_WW1_M1 | MA096 |  | 0 | 3 | 3 | 5 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16 | 16
G2a.189 | I/C | Number of WWTW odour equipment asset interventions | Number | O_WW1_M10 | MA049, SR15 |  | 0 | 1 | 4 | 7 | 10 | 10 | 11 | 14 | 16 | 46 | 46 | 47 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2a.190 | I/C | Number of WWTW primary treatment asset interventions | Number | O_WW1_M11 | MA013, MA017, MA039, MA042, MA043 |  | 0 | 17 | 60 | 99 | 113 | 134 | 147 | 163 | 180 | 235 | 235 | 237 | 240 | 242 | 244 | 258 | 259 | 399 | 400 | 400 | 400 | 402 | 402 | 402 | 405 | 414 | 414
G2a.191 | I/C | Number of redundant or abandoned assets interventions - WWTW | Number | O_WW1_M12 | MA011, MA096 |  | 0 | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39
G2a.192 | I/C | Number of WWTW secondary treatment asset interventions | Number | O_WW1_M13 | MA017, MA024, MA035, MA036, MA042, MA043, MA057 |  | 0 | 93 | 199 | 291 | 342 | 452 | 516 | 597 | 696 | 932 | 951 | 970 | 981 | 985 | 1000 | 1000 | 1007 | 1392 | 1393 | 1396 | 1402 | 1402 | 1408 | 1409 | 1411 | 1459 | 1459
G2a.193 | I/C | Number of site welfare facilities interventions - WWTW | Number | O_WW1_M14 | MA096 |  | 0 | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 12 | 12
G2a.194 | I/C | Number of WWTW sites with temporary process unit interventions | Number | O_WW1_M15 | MA021, MA043, MA057 |  | 0 | 3 | 4 | 4 | 10 | 10 | 15 | 15 | 16 | 16 | 16 | 18 | 24 | 24 | 25 | 27 | 28 | 29 | 29 | 29 | 31 | 32 | 33 | 33 | 33 | 34 | 34
G2a.195 | I/C | Number of WWTW treatment ancillaries asset interventions | Number | O_WW1_M16 | MA011, MA023, MA024, MA039, MA043, MA057, MA096 |  | 1 | 73 | 220 | 381 | 776 | 1136 | 1311 | 1517 | 1803 | 2604 | 2618 | 2641 | 2645 | 2700 | 2702 | 2704 | 2709 | 2811 | 2816 | 2818 | 2822 | 2825 | 3499 | 3800 | 3800 | 3826 | 3826
G2a.196 | I/C | Number of high voltage system interventions | Number | O_WW1_M17 | MA091 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
G2a.197 | I/C | Number of WWTW statutory maintenance asset interventions | Number | O_WW1_M18 | MA068 |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2a.198 | I/C | Number of fixed wire electrical system asset interventions | Number | O_WW1_M2 | MA068 |  | 0 | 0 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2a.199 | I/C | Number of WWTW Motor Control Centre interventions | Number | O_WW1_M3 | MA011 |  | 0 | 5 | 11 | 12 | 13 | 218 | 219 | 225 | 225 | 466 | 466 | 468 | 468 | 469 | 474 | 474 | 476 | 476 | 476 | 476 | 479 | 479 | 479 | 486 | 486 | 494 | 494
G2a.200 | I/C | Number of wastewater SCADA interventions | Number | O_WW1_M4 | MA011, MA013, MA023 |  | 0 | 15 | 17 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 22 | 22 | 24 | 26 | 26 | 38 | 40 | 42 | 42 | 42 | 50 | 50
G2a.201 | I/C | Number of screw pumps intervention | Number | O_WW1_M5 | MA036 |  | 0 | 8 | 17 | 21 | 28 | 28 | 28 | 28 | 30 | 30 | 30 | 30 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33
G2a.202 | I/C | Number of wastewater telemetry interventions | Number | O_WW1_M6 | MA044 |  | 1 | 63 | 117 | 128 | 128 | 339 | 533 | 536 | 536 | 540 | 540 | 541 | 542 | 542 | 719 | 1008 | 1139 | 1139 | 1330 | 1419 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511
G2a.203 | I/C | Number of wastewater property operational building interventions | Number | O_WW1_M7 | MA096 |  | 0 | 15 | 60 | 96 | 112 | 126 | 135 | 147 | 155 | 164 | 173 | 174 | 197 | 199 | 199 | 199 | 203 | 203 | 233 | 236 | 237 | 237 | 237 | 237 | 237 | 237 | 237
G2a.204 | I/C | Number of WWTW inlet works asset interventions | Number | O_WW1_M9 | MA011, MA017, MA023, MA042, MA043 |  | 0 | 23 | 67 | 113 | 127 | 220 | 242 | 272 | 328 | 441 | 464 | 470.01 | 476.01 | 484.01 | 486.01 | 496.01 | 507.01 | 757.01 | 769.01 | 781.01 | 781.01 | 781.01 | 781.01 | 781.01 | 781.01 | 791.01 | 791.01
G2a.205 | I/C | Number of WWTW continuous discharges improved or removed | Number | O_WW2_E | MA014, MA049 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01
G2a.206 | I/C | Number of studies complete | Number | O_WW3_E | MA017, MA039 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Supporting Sustainable Economic Growth
G2a.207 | I/C | Number of Asset Inspections completed | Number | O_AI1_M | MA065, MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2a.208 | I/C | Number of sludge treatment centre asset interventions | Number | O_BR1_M | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.209 | I/C | Investigation | Number | O_DW5A | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2a.210 | I/C | Number of WWTW sites requiring RRR activities to support Part 4 Growth | Number | O_ED1_M | MA026 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 5027 | 5027 | 5027 | 5027 | 5027 | 5028 | 5028 | 5029 | 5029 | 15838 | 15838
G2a.211 | I/C | Increase in Part 4 capacity to meet strategic growth requirements | Population Equivalent | O_ED2_G | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 25476 | 27998 | 27998
G2a.212 | I/C | Increase in Part 4 capacity to meet local growth requirements | Population Equivalent | O_ED3_G | MA026 |  | 0 | 151 | 2745 | 2745 | 3699 | 3805 | 12044 | 21110.1 | 21787.11 | 26905.14 | 29646.17 | 30275.28 | 133865.28 | 138462.28 | 152091.28 | 153775.28 | 156969.28 | 158401.28 | 162606.28 | 162682.28 | 162922.28 | 163825.28 | 165833.28 | 172067.28 | 173457.28 | 255674.28 | 255674.28
G2a.213 | I/C | Additional Capacity enabled from strategic wastewater network reinforcement | Population Equivalent | O_ED4_G | MA032 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 107 | 107 | 107 | 107 | 13996 | 16396 | 16396 | 18886 | 18887 | 18888 | 27321 | 27323 | 59131 | 59131 | 59131 | 60297 | 60297
G2a.214 | I/C | Number of schemes supported by Reasonable Cost Contributions | Number | O_ED5_G | MA065 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2a.215 | I/C | Increase in Part 4 capacity to meet commercial growth requirements | Population Equivalent | O_ED6_G | MA026 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 3065 | 3065 | 3065 | 5265 | 5265 | 5265 | 5265
G2a.216 | I/C | Number of service relocations | Number | O_EG1_G | MA065 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1129 | 1129 | 1129 | 1176 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186 | 1186 | 1186
G2a.217 | I/C | Population benefiting from strategic network reinforcement | Population Equivalent | O_EG2_G | MA032 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 35745 | 35745 | 35745 | 35745 | 45745 | 45745 | 45745 | 45746 | 45747 | 45747
G2a.218 | I/C | Additional Capacity enabled from strategic water network reinforcement | Population Equivalent | O_WR10_G1 | MA032, MA065 |  | 0 | 0 | 0 | 1320 | 11665 | 11665 | 12525 | 13236 | 14933 | 19283 | 24716 | 48556 | 61132 | 64178 | 85578 | 90750 | 124250 | 125702 | 125702 | 125702 | 173702 | 173702 | 173702 | 173702 | 173977 | 177977 | 177977
G2a.219 | I/C | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2a.220 | I/C | Number of resilience improvements via Water Efficiency campaigns | Number | O_WR8_G2 | MA087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2a.221 | I/C | Number of resilience improvements at rural supply hubs to provide capacity for new demand | Number | O_WR8_G3 | MA087 |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2a.222 | I/C | Number of tanker fill points installed | Number | O_WR8_G4 | MA087 |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2a.223 | I/C | Length of service relocations - water mains | Metres | O_WR9_G1 | MA065 |  | 0 | 1 | 1077 | 7970 | 7973 | 7973 | 7973 | 8401 | 25509 | 25669 | 25675 | 25755 | 25756 | 26032 | 30440 | 30775 | 30775 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585
G2a.224 | I/C | Number of WWTW secondary treatment asset interventions | Number | O_WW1_M13 | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3
G2a.225 | I/C | Number of WWTW inlet works asset interventions | Number | O_WW1_M9 | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2a.226 | I/C | Number of studies complete | Number | O_WW3_E | MA026 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: | [5 empty] | Date:

## G2b
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G2b: Completion Investment
Line Ref | Field Type | Output Description | Output Units | Output Code | Management Approach Reference(s) |  | Pre-2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Total
[8 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
2015-21 outputs remaining that were planned to complete in the 2021-27 period - Planned
G2b.1 | I/C | Number of water treatment works improved | No. | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2b.2 | I/C | Number of zones made compliant with iron & manganese standards | No. | 2 |  |  | 3 | 6 | 6 | 7 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2b.3 | I/C | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8
G2b.4 | I/C | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2b.5 | I/C | Distribution mains cleaned (km) | km | 5 |  |  | 0 | 0 | 2323.845 | 2323.845 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405 | 2335.405
G2b.6 | I/C | Number of water quality etc studies to inform future periods | No. | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.7 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.8 | I/C | Water supply resilience strategy and improvements made | No. | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.9 | I/C | Number of zones with improved security of supply (SOSI) | No. | 9 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.10 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2b.11 | I/C | Number of WWTWs improved to meet UWWTD | No. | 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.12 | I/C | Number of waste water networks improved to meet UWWTD | No. | 12 |  |  | 0 | 3 | 6 | 6 | 7 | 7 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G2b.13 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.14 | I/C | Number of improvements required to meet the Water Framework Directive | No. | 14 |  |  | 0 | 0 | 1 | 2 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2b.15 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  |  | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.16 | I/C | Number of environmental studies to inform future periods | No. | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.17 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.18 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-21 completion outputs remaining - Delayed
G2b.19 | I/C | Number of water treatment works improved | No. | 1 |  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2b.20 | I/C | Number of zones made compliant with iron & manganese standards | No. | 2 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.21 | I/C | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  |  | 3 | 6 | 7 | 8 | 9 | 9 | 9 | 10 | 10 | 13 | 13 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18
G2b.22 | I/C | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  |  | 2 | 11 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2b.23 | I/C | Distribution mains cleaned (km) | km | 5 |  |  | 48.4 | 48.4 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2b.24 | I/C | Number of water quality etc studies to inform future periods | No. | 6 |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.25 | I/C | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  |  | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2b.26 | I/C | Water supply resilience strategy and improvements made | No. | 8 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.27 | I/C | Number of zones with improved security of supply (SOSI) | No. | 9 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.28 | I/C | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.29 | I/C | Number of WWTWs improved to meet UWWTD | No. | 11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2b.30 | I/C | Number of waste water networks improved to meet UWWTD | No. | 12 |  |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2b.31 | I/C | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  |  | 3 | 4 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2b.32 | I/C | Number of improvements required to meet the Water Framework Directive | No. | 14 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 9 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2b.33 | I/C | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2b.34 | I/C | Number of environmental studies to inform future periods | No. | 16 |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2b.35 | I/C | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  |  | 2 | 2 | 2 | 2 | 2 | 13 | 13 | 33 | 33 | 33 | 33 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40
G2b.36 | I/C | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
|  | SR15 Completion projects | Units
G2b.37 | I/C | SR10 projects remaining (Q&S3b) | Nr |  |  |  | 19 | 15 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
G2b.38 | I/C | SR15 projects remaining (Q&SIV) | Nr |  |  |  | 124 | 94 | 73 | 67 | 55 | 52 | 48 | 40 | 35 | 29 | 25 | 18 | 16 | 13 | 11 | 9 | 7 | 5 | 5 | 3 | 2 | 2 | 2 | 2 | 1
G2b.39 | I/C | 2015-21 projects remaining that were planned to complete in the 2021-27 period - Planned | Nr |  |  |  | 57 | 49 | 33 | 30 | 22 | 21 | 19 | 16 | 14 | 12 | 9 | 7 | 6 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
G2b.40 | I/C | 2015-21 completion projects remaining - Delayed | Nr |  |  |  | 86 | 60 | 50 | 45 | 39 | 37 | 35 | 30 | 27 | 23 | 20 | 14 | 13 | 10 | 8 | 8 | 7 | 4 | 4 | 3 | 1 | 1 | 1 | 1 | 0
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: | [5 empty] | Date:

## G2c
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G2c: Outputs by Milestone
Asset Maintenance | [7 empty] | Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0001 | I | Number of Transformation initiatives implemented | Number | O_TF1_E | MA104 | Baseline | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0002 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0003 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0004 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0005 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0006 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0007 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0008 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Circular Economy |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0009 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0010 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0011 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0012 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0013 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0014 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0015 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0016 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0017 | I | Wastewater Non Infrastructure - Sludge Treatment Facilities | Number | O_CM_STF | MA109 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0018 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0019 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0020 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0021 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0022 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0023 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0024 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0025 | I | Reduction in energy usage through improved energy efficiency | GWh | O_LC1_E | MA027, MA077 | Baseline | G90 - Delivery Approval | 10 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 15.2197
G2c.0026 | I | [5 empty] | SOS - Start On Site | 9 | 9 | 9 | 9 | 9 | 9.4197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 12.2197
G2c.0027 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 3.2197 | 12.2197
G2c.0028 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 12.2197
G2c.0029 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 10 | 12.2197 | 12.2197 | 12.2197 | 12.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 15.2197
G2c.0030 | I | [5 empty] | SOS - Start On Site | 10 | 10 | 11.8 | 11.8 | 12.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 13.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 14.2197 | 15.2197
G2c.0031 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3.4197 | 15.2197
G2c.0032 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 15.2197
G2c.0033 | I | Increase in renewable energy generated | GWh | O_LC2_E1 | MA109 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0034 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0035 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0036 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0037 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0038 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0039 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0040 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0041 | I | Number of studies complete | Number | O_LC2_E2 | MA109 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0042 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0043 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0044 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0045 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0046 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0047 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0048 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0049 | I | Number of alternative fuel refuelling infrastructure points | Number | O_LV2_M | MA071 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0050 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0051 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0052 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0053 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0054 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0055 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0056 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413 | 413
G2c.0057 | I | Number of peatland catchment assessments | Number | O_OM8_E | MA028, MA077 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0058 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0059 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0060 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0061 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0062 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0063 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 12 | 12
G2c.0064 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 6 | 6 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 12
G2c.0065 | I | Number of Private Finance Initiative (PFI) sites returned to Scottish Water | Number | O_PF1_E | MA109 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0066 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0067 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0068 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0069 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0070 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0071 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0072 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0073 | I | Number of generators /turbines maintained | Number | O_RE1_M | MA056 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0074 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0075 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0076 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0077 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0078 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0079 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0080 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0081 | I | Number of education campaigns targeted at reducing water wastage in households | Number | O_SA11_E | MA099 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0082 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0083 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0084 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0085 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0086 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0087 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0088 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0089 | I | Number of Climate Change studies | Number | O_SE1_E | MA103 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0090 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0091 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0092 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0093 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0094 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0095 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0096 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0097 | I | Energy generated by hosting renewable energy at SW sites | GWh | O_SE2_E | MA101 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.07 | 1.07 | 3.02 | 4.7 | 4.7 | 5.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0098 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0099 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0100 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0101 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.07 | 1.07 | 3.02 | 4.7 | 4.7 | 5.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0102 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.22 | 3.02 | 3.7 | 4.7 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0103 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.22 | 2.4 | 3.2 | 5.2 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0104 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 2.22 | 2.22 | 3.02 | 6.02 | 7.52 | 7.52 | 7.52 | 7.52 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0105 | I | Number of studies complete | Number | O_SE2_E | MA101 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.07 | 1.07 | 3.02 | 4.7 | 4.7 | 5.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0106 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0107 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0108 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07
G2c.0109 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.07 | 1.07 | 3.02 | 4.7 | 4.7 | 5.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0110 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 1.22 | 3.02 | 3.7 | 4.7 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0111 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.07 | 1.07 | 1.22 | 2.4 | 3.2 | 5.2 | 6.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0112 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.07 | 2.22 | 2.22 | 3.02 | 6.02 | 7.52 | 7.52 | 7.52 | 7.52 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
G2c.0113 | I | Number of sites assessed for renewable energy generation | Number | O_SE2_E2 | MA101 | Baseline | G90 - Delivery Approval | 0 | 2 | 2 | 14 | 14 | 16 | 17 | 19 | 19 | 28.74 | 34.24 | 34.24 | 36.24 | 38.24 | 38.24 | 39.24 | 40.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24
G2c.0114 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 14 | 14 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G2c.0115 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 16
G2c.0116 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 16
G2c.0117 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 2 | 2 | 14 | 14 | 16 | 17 | 19 | 19 | 28.74 | 34.24 | 34.24 | 36.24 | 38.24 | 38.24 | 39.24 | 40.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24
G2c.0118 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 14 | 14 | 14 | 18 | 19 | 20 | 26.74 | 29.24 | 33.24 | 36.24 | 38.24 | 38.24 | 40.24 | 40.24 | 40.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24 | 41.24
G2c.0119 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 5 | 10 | 12 | 13.74 | 18.74 | 20.24 | 21.24 | 24.24 | 37.24 | 38.24 | 38.24 | 38.24 | 38.24 | 38.24 | 39.24 | 41.24
G2c.0120 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 10 | 12 | 13.74 | 19.74 | 20.24 | 22.24 | 34.24 | 37.24 | 38.24 | 38.24 | 38.24 | 38.24 | 38.24 | 41.24
G2c.0121 | I | Number of Climate Change studies | Number | O_SE3_E | MA077 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0122 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0123 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0124 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0125 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0126 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0127 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0128 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0129 | I | Number of Climate Change Audits | Number | O_SE4_E | MA102 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 2 | 22 | 22 | 22 | 22 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0130 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G2c.0131 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22
G2c.0132 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
G2c.0133 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 2 | 22 | 22 | 22 | 22 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0134 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0135 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
G2c.0136 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
G2c.0137 | I | Number of carbon capture sites established or supported | Number | O_SE8_E | MA077 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 5 | 5 | 45 | 45 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.0138 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
G2c.0139 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 46
G2c.0140 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 46
G2c.0141 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 5 | 5 | 45 | 45 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.0142 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 45 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.0143 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 7 | 48
G2c.0144 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 48
G2c.0145 | I | Number of renewable energy asset interventions | Number | O_SE9_M | MA056 | Baseline | G90 - Delivery Approval | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0146 | I | [5 empty] | SOS - Start On Site | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G2c.0147 | I | [5 empty] | G100 - Acceptance | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22
G2c.0148 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22
G2c.0149 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0150 | I | [5 empty] | SOS - Start On Site | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G2c.0151 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23
G2c.0152 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23
G2c.0153 | I | Number of studies complete | Number | O_WW5_E | MA076 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0154 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0155 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0156 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0157 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0158 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0159 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0160 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Drinking Water |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0161 | I | Number of Asset Inspections completed | Number | O_AI1_M | MA006, MA087 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0162 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0163 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0164 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0165 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0166 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0167 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0168 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0169 | I | Number of sites with enhanced metals removal | Number | O_DC1_E | MA006 | Baseline | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0170 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0171 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0172 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0173 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0174 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0175 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0176 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0177 | I | Number of WTW sites with phosphate equipment dosing optimised | Number | O_LD1_E1 | MA041 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0178 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0179 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5
G2c.0180 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5
G2c.0181 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0182 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0183 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5
G2c.0184 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5
G2c.0185 | I | Number of sites where new phosphate monitoring equipment has been provided | Number | O_LD1_E3 | MA041 | Baseline | G90 - Delivery Approval | 0 | 0 | 4 | 4 | 21 | 21 | 33 | 33 | 33 | 50 | 65 | 65 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67
G2c.0186 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0187 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0188 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0189 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 4 | 4 | 21 | 21 | 33 | 33 | 33 | 50 | 65 | 65 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67
G2c.0190 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 4 | 21 | 21 | 21 | 21 | 33 | 33 | 65 | 65 | 65 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67
G2c.0191 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 21 | 21 | 21 | 21 | 21 | 21 | 33 | 33 | 33 | 50 | 50 | 50 | 65 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67 | 67
G2c.0192 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 33 | 50 | 50 | 50 | 50 | 65 | 65 | 67 | 67 | 67 | 67 | 67 | 67
G2c.0193 | I | Number of lead communication pipes replaced | Number | O_LD2_E | MA041 | Baseline | G90 - Delivery Approval | 2 | 542 | 1942 | 1942 | 1942 | 1942 | 1942 | 1942 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945
G2c.0194 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 1402 | 1942 | 1942 | 1942 | 1942 | 1942 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945
G2c.0195 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 1490 | 1491 | 1491 | 1491 | 1491 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1945 | 1945
G2c.0196 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 1490 | 1490 | 1491 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1492 | 1945 | 1945
G2c.0197 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 542 | 1942 | 1942 | 1942 | 1942 | 1942 | 1942 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945
G2c.0198 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 1402 | 1942 | 1942 | 1942 | 1942 | 1942 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945 | 1945
G2c.0199 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1945 | 1945
G2c.0200 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581 | 1581 | 1581 | 1581 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1582 | 1945 | 1945
G2c.0201 | I | Number of properties with lead sampling and risk assessment completed | Number | O_LD4_E | MA041 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 20002 | 20002 | 20003 | 20003 | 20003 | 20003 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004
G2c.0202 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 20002 | 20002 | 20002 | 20002 | 20002 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003 | 20003
G2c.0203 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 20003
G2c.0204 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 20003
G2c.0205 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 20002 | 20002 | 20003 | 20003 | 20003 | 20003 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004
G2c.0206 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 20002 | 20002 | 20002 | 20003 | 20003 | 20003 | 20003 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004 | 20004
G2c.0207 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20004
G2c.0208 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20004
G2c.0209 | I | Number of membranes replaced or maintained | Number | O_OM1_M1 | MA006 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0210 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0211 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0212 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0213 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0214 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.0215 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5
G2c.0216 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5
G2c.0217 | I | Number of sites made compliant with standards | Number | O_OM12_E | IR 18 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0218 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0219 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0220 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0221 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0222 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0223 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0224 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0225 | I | Number of treated water storage asset interventions | Number | O_OM2_M1 | MA006 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0226 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0227 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0228 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0229 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0230 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0231 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0232 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0233 | I | Number of sample point interventions | Number | O_OM2_M2 | MA087 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0234 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0235 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0236 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0237 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0238 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0239 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0240 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0241 | I | Number of WTW sites made compliant with standards | Number | O_OM3_E | MA006 | Baseline | G90 - Delivery Approval | 61 | 64 | 64 | 64 | 65 | 68 | 69 | 73 | 77 | 80 | 82 | 84 | 88 | 89 | 93 | 95 | 97 | 98 | 102 | 108 | 110 | 110 | 111 | 111 | 111 | 132
G2c.0242 | I | [5 empty] | SOS - Start On Site | 8 | 10 | 27 | 28 | 28 | 58 | 66 | 67 | 73 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74 | 74
G2c.0243 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 8 | 16 | 25 | 26 | 56 | 56 | 65 | 66 | 69 | 70 | 71 | 72 | 72 | 72 | 72 | 73 | 73 | 74 | 74 | 74 | 74 | 74 | 74
G2c.0244 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 8 | 8 | 16 | 16 | 26 | 26 | 56 | 64 | 65 | 66 | 67 | 69 | 71 | 71 | 72 | 72 | 72 | 72 | 73 | 73 | 74 | 74 | 74
G2c.0245 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 61 | 64 | 64 | 64 | 65 | 68 | 69 | 73 | 77 | 80 | 82 | 84 | 88 | 89 | 93 | 95 | 97 | 98 | 102 | 108 | 110 | 110 | 111 | 111 | 111 | 132
G2c.0246 | I | [5 empty] | SOS - Start On Site | 8 | 10 | 18 | 27 | 28 | 43 | 67 | 69 | 74 | 78 | 81 | 81 | 85 | 89 | 89 | 93 | 95 | 97 | 98 | 105 | 108 | 110 | 110 | 111 | 111 | 132
G2c.0247 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 12 | 19 | 39 | 66 | 74 | 77 | 78 | 79 | 80 | 84 | 84 | 85 | 87 | 88 | 90 | 96 | 99 | 132
G2c.0248 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 10 | 17 | 38 | 43 | 66 | 75 | 77 | 78 | 80 | 80 | 84 | 84 | 87 | 88 | 89 | 95 | 132
G2c.0249 | I | Number of WTW sites with auto-shutdown risk control interventions | Number | O_OM4_E | MA006 | Baseline | G90 - Delivery Approval | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 7 | 9 | 10 | 11 | 11 | 15 | 16 | 18 | 24 | 25 | 25 | 26 | 27 | 27 | 29
G2c.0250 | I | [5 empty] | SOS - Start On Site | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0251 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0252 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0253 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 7 | 9 | 10 | 11 | 11 | 15 | 16 | 18 | 24 | 25 | 25 | 26 | 27 | 27 | 29
G2c.0254 | I | [5 empty] | SOS - Start On Site | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 9 | 9 | 10 | 10 | 14 | 15 | 22 | 24 | 25 | 25 | 26 | 27 | 29
G2c.0255 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 9 | 10 | 10 | 10 | 11 | 14 | 17 | 29
G2c.0256 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 7 | 7 | 9 | 9 | 10 | 11 | 14 | 29
G2c.0257 | I | Number of WTW sites with improved organics removal | Number | O_OM5_E | MA006 | Baseline | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0258 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0259 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0260 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0261 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0262 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0263 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0264 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0265 | I | Number of single supply standard products developed | Number | O_OM7_E | MA006 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0266 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0267 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0268 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0269 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0270 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0271 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0272 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0273 | I | Number of sites with emergency planning equipment interventions | Number | O_WR1_M | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0274 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0275 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0276 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0277 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0278 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0279 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0280 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0281 | I | Number of Resilience Improvements | Number | O_WR11_E | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0282 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0283 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0284 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0285 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0286 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0287 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0288 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0289 | I | Number of Water Supply Zones with improved resilience | Number | O_WR6_E | MA087 | Baseline | G90 - Delivery Approval | 1 | 2 | 3 | 4 | 4 | 6 | 8 | 10 | 12 | 17 | 19 | 21 | 21 | 23 | 24 | 26 | 26 | 29 | 30 | 31 | 33 | 33 | 33 | 34 | 34 | 34
G2c.0290 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 3 | 3 | 4 | 4 | 6 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0291 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 5 | 6 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0292 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 4 | 5 | 5 | 5 | 6 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0293 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 3 | 4 | 4 | 6 | 8 | 10 | 12 | 17 | 19 | 21 | 21 | 23 | 24 | 26 | 26 | 29 | 30 | 31 | 33 | 33 | 33 | 34 | 34 | 34
G2c.0294 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 3 | 4 | 4 | 6 | 6 | 7 | 10 | 13 | 15 | 17 | 19 | 22 | 24 | 24 | 26 | 26 | 29 | 30 | 31 | 33 | 33 | 33 | 34 | 34
G2c.0295 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 5 | 10 | 10 | 10 | 13 | 17 | 20 | 21 | 23 | 23 | 24 | 24 | 24 | 28 | 28 | 29 | 30 | 34
G2c.0296 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 4 | 5 | 8 | 9 | 9 | 10 | 13 | 17 | 18 | 21 | 22 | 23 | 23 | 24 | 24 | 26 | 28 | 29 | 34
G2c.0297 | I | Number of WTW's with capacity restored | Number | O_WR7_E | MA006 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0298 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0299 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0300 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0301 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0302 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0303 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G2c.0304 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
G2c.0305 | I | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA006 | Baseline | G90 - Delivery Approval | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0306 | I | [5 empty] | SOS - Start On Site | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0307 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0308 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0309 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0310 | I | [5 empty] | SOS - Start On Site | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0311 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
G2c.0312 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884 | 884
Environment |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0313 | I | Number of WTW sites with Legacy Sludge Issues resolved | Number | O_AD3_E | MA085 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 11
G2c.0314 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0315 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0316 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0317 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 11
G2c.0318 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 11
G2c.0319 | I | [5 empty] | G100 - Acceptance | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 5 | 11
G2c.0320 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 11
G2c.0321 | I | Number of sites with abstraction and compensation monitoring equipment interventions | Number | O_AD4_M | MA063 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6
G2c.0322 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0323 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0324 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0325 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6
G2c.0326 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6
G2c.0327 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 6
G2c.0328 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 6
G2c.0329 | I | Number of sites with Water Framework Directive improvements | Number | O_AD6_E | MA063 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0330 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0331 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0332 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0333 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0334 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0335 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
G2c.0336 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0337 | I | Number of WwTW sites with Environmental Pollution risk reduced | Number | O_BR2_E | MA085 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0338 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0339 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0340 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0341 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0342 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0343 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0344 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0345 | I | Number of industrial Emissions Directive compliance action plans | Number | O_BR3_E | MA077 | Baseline | G90 - Delivery Approval | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0346 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0347 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0348 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0349 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0350 | I | [5 empty] | SOS - Start On Site | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0351 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0352 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.0353 | I | tbc | Number | O_IRNMO | IR 18 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0354 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0355 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0356 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0357 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0358 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0359 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0360 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0361 | I | Number of unsatisfactory intermittent discharges improved or removed | Number | O_IRUID | IR 18 | Baseline | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0362 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0363 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0364 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0365 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0366 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0367 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0368 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0369 | I | Number of continuous discharges improved or removed | Number | O_IRWWT | IR 18 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0370 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0371 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0372 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
G2c.0373 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0374 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0375 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0376 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0377 | I | Number of catchments with intelligent network technology | Number | O_NI1_E1 | MA107 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0378 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0379 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0380 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0381 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0382 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0383 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0384 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0385 | I | Number of Event Duration Monitors (EDM) deployed | Number | O_NI1_E2 | MA107 | Baseline | G90 - Delivery Approval | 1 | 1 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55 | 55 | 55 | 55 | 55
G2c.0386 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0387 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0388 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.0389 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55 | 55 | 55 | 55 | 55
G2c.0390 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55 | 55 | 55
G2c.0391 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55
G2c.0392 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 55
G2c.0393 | I | Number of Combined Storm Overflow (CSO) screen interventions | Number | O_SN1_M8 | MA005 | Baseline | G90 - Delivery Approval | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0394 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0395 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0396 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0397 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0398 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0399 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0400 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0401 | I | Number of unsatisfactory intermittent discharges improved or removed | Number | O_SN2_E | MA005 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0402 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0403 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0404 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0405 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0406 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0407 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0408 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0409 | I | Number of unsatisfactory intermittent discharges (UID) improved or removed for aesthetics | Number | O_SN2_E1 | IR 18, MA005 | Baseline | G90 - Delivery Approval | 5 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 23 | 23 | 24 | 26 | 29 | 32 | 36 | 42 | 44 | 45 | 55 | 71 | 74 | 74 | 75 | 75 | 75
G2c.0410 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0411 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 3 | 3 | 4 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0412 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0413 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 23 | 23 | 24 | 26 | 29 | 32 | 36 | 42 | 44 | 45 | 55 | 71 | 74 | 74 | 75 | 75 | 75
G2c.0414 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 3 | 3 | 5 | 6 | 8 | 10 | 10 | 20 | 23 | 23 | 24 | 29 | 29 | 33 | 37 | 43 | 45 | 48 | 55 | 72 | 73 | 74 | 75 | 75
G2c.0415 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 16 | 19 | 19 | 19 | 23 | 24 | 24 | 24 | 24 | 29 | 32 | 36 | 38 | 44 | 45 | 51 | 75
G2c.0416 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 15 | 15 | 16 | 18 | 19 | 19 | 22 | 24 | 24 | 24 | 29 | 29 | 33 | 37 | 43 | 45 | 75
G2c.0417 | I | Number of unsatisfactory intermittent discharges (UID) improved or removed for water quality | Number | O_SN2_E2 | MA005 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0418 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0419 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0420 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0421 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0422 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0423 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0424 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0425 | I | Number of WWTW continuous discharges improved or removed | Number | O_WW2_E | MA005, MA084 | Baseline | G90 - Delivery Approval | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 32
G2c.0426 | I | [5 empty] | SOS - Start On Site | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0427 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0428 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.0429 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 32
G2c.0430 | I | [5 empty] | SOS - Start On Site | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 32
G2c.0431 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 32
G2c.0432 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 32
G2c.0433 | I | Number of studies complete | Number | O_WW3_E | IR 18, MA076, MA084 | Baseline | G90 - Delivery Approval | 292 | 294 | 298 | 300 | 303 | 303 | 303 | 306 | 306 | 307 | 307 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 313
G2c.0434 | I | [5 empty] | SOS - Start On Site | 291 | 292 | 297 | 299 | 300 | 301 | 302 | 304 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305
G2c.0435 | I | [5 empty] | G100 - Acceptance | 0 | 27 | 114 | 290 | 292 | 292 | 298 | 298 | 299 | 302 | 302 | 303 | 304 | 304 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305
G2c.0436 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 290 | 290 | 295 | 295 | 299 | 301 | 302 | 303 | 304 | 304 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305
G2c.0437 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 292 | 294 | 298 | 300 | 303 | 303 | 303 | 306 | 306 | 307 | 307 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 312 | 312 | 313
G2c.0438 | I | [5 empty] | SOS - Start On Site | 291 | 292 | 298 | 300 | 301 | 302 | 302 | 304 | 305 | 306 | 306 | 310 | 310 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 312 | 312 | 312 | 312 | 313
G2c.0439 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 27 | 191 | 292 | 293 | 295 | 300 | 301 | 302 | 304 | 305 | 306 | 306 | 309 | 310 | 310 | 310 | 310 | 310 | 311 | 311 | 311 | 312 | 312 | 313
G2c.0440 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 115 | 290 | 292 | 293 | 299 | 300 | 301 | 301 | 303 | 304 | 309 | 309 | 309 | 309 | 310 | 310 | 310 | 311 | 311 | 311 | 312 | 313
G2c.0441 | I | Number of studies complete | Number | O_WW4_E | MA076 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0442 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0443 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0444 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0445 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0446 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0447 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0448 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Flooding and Surface Water Management |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0449 | I | No outputs identified for this ministerial objective |  | - |  | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0450 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0451 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0452 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0453 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0454 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0455 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0456 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Long Term Water Sector Vision |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0457 | I | Number of sites enabled for community access | Number | O_CR3_E | MA110 | Baseline | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0458 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0459 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0460 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0461 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0462 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0463 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0464 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0465 | I | Number of new top-up-from-the-tap points | Number | O_CR5_E | MA110 | Baseline | G90 - Delivery Approval | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0466 | I | [5 empty] | SOS - Start On Site | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0467 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50
G2c.0468 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50
G2c.0469 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0470 | I | [5 empty] | SOS - Start On Site | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0471 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0472 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.0473 | I | Number of private water supplies investigated | Number | O_CR7_E | MA110 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0474 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0475 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0476 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0477 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0478 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0479 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0480 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0481 | I | Number of Hydro Nation ideas put into practice | Number | O_SE7_E | MA048 | Baseline | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0482 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0483 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0484 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0485 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0486 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0487 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0488 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Private Finance Initiative Funded Projects |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0489 | I | Number of Private Finance Initiative (PFI) sites returned to Scottish Water | Number | O_PF1_E | MA108 | Baseline | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7
G2c.0490 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0491 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3
G2c.0492 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3
G2c.0493 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7
G2c.0494 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7
G2c.0495 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 7
G2c.0496 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 7
G2c.0497 | I | Number of approved plans for PFI Contracts transitioned to Scottish Water | Number | O_PF2_E | MA108 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0498 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0499 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0500 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0501 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0502 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0503 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
G2c.0504 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Security & Resilience |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0505 | I | Number of digital transformation interventions | Number | O_DI1_M | MA066 | Baseline | G90 - Delivery Approval | 8 | 8 | 8 | 8 | 8 | 10 | 11 | 12 | 15 | 16 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0506 | I | [5 empty] | SOS - Start On Site | 6 | 7 | 7 | 7 | 7 | 9 | 10 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0507 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 7 | 7 | 7 | 7 | 7 | 8 | 9 | 9 | 10 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0508 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 2 | 7 | 7 | 8 | 9 | 9 | 9 | 10 | 11 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0509 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 8 | 8 | 8 | 8 | 8 | 10 | 11 | 12 | 15 | 16 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0510 | I | [5 empty] | SOS - Start On Site | 7 | 7 | 7 | 8 | 8 | 9 | 10 | 11 | 14 | 16 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0511 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 5 | 7 | 8 | 8 | 9 | 9 | 10 | 11 | 15 | 15 | 15 | 15 | 16 | 16 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0512 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 7 | 8 | 8 | 8 | 9 | 9 | 11 | 11 | 15 | 15 | 15 | 16 | 16 | 16 | 17 | 19 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0513 | I | Number of sites with water security interventions | Number | O_HS1_M10 | MA089 | Baseline | G90 - Delivery Approval | 2 | 4 | 6 | 6 | 206 | 206 | 206 | 206 | 206 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507
G2c.0514 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 6 | 6 | 175 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206
G2c.0515 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 6 | 6 | 6 | 7 | 8 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206
G2c.0516 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 7 | 176 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206 | 206
G2c.0517 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 4 | 6 | 6 | 206 | 206 | 206 | 206 | 206 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507
G2c.0518 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 6 | 6 | 175 | 205 | 205 | 205 | 205 | 205 | 506 | 506 | 506 | 506 | 506 | 506 | 506 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507 | 507
G2c.0519 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 204 | 204 | 204 | 204 | 204 | 205 | 505 | 506 | 506 | 507 | 507 | 507 | 507 | 507 | 507 | 507
G2c.0520 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 36 | 36 | 204 | 204 | 204 | 204 | 204 | 205 | 206 | 207 | 507 | 507 | 507 | 507
Standards of service |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.0521 | I | Number of WTW sludge handling asset interventions | Number | O_AD1_M | MA025, MA052, MA093 | Baseline | G90 - Delivery Approval | 46 | 77 | 98 | 112 | 150 | 154 | 177 | 229 | 272 | 275 | 276 | 276 | 278 | 278 | 278 | 278 | 279 | 280 | 281 | 281 | 281 | 281 | 281 | 281 | 281 | 282
G2c.0522 | I | [5 empty] | SOS - Start On Site | 35 | 64 | 89 | 106 | 138 | 146 | 171 | 224 | 269 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270
G2c.0523 | I | [5 empty] | G100 - Acceptance | 0 | 35 | 64 | 85 | 99 | 135 | 141 | 167 | 222 | 266 | 268 | 269 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270
G2c.0524 | I | [5 empty] | G110 - Financial Closure | 0 | 35 | 64 | 85 | 99 | 130 | 137 | 161 | 215 | 260 | 264 | 266 | 267 | 267 | 268 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270
G2c.0525 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 46 | 77 | 98 | 112 | 150 | 154 | 177 | 229 | 272 | 275 | 276 | 276 | 278 | 278 | 278 | 278 | 279 | 280 | 281 | 281 | 281 | 281 | 281 | 281 | 281 | 282
G2c.0526 | I | [5 empty] | SOS - Start On Site | 35 | 65 | 86 | 107 | 140 | 144 | 169 | 221 | 267 | 273 | 275 | 276 | 276 | 276 | 278 | 278 | 278 | 280 | 280 | 281 | 281 | 281 | 281 | 281 | 281 | 282
G2c.0527 | I | [5 empty] | G100 - Acceptance | 0 | 14 | 45 | 66 | 75 | 110 | 122 | 137 | 176 | 263 | 266 | 273 | 275 | 276 | 276 | 276 | 278 | 278 | 278 | 278 | 279 | 279 | 280 | 281 | 281 | 282
G2c.0528 | I | [5 empty] | G110 - Financial Closure | 0 | 14 | 45 | 62 | 70 | 104 | 115 | 132 | 171 | 256 | 262 | 265 | 269 | 272 | 275 | 275 | 275 | 278 | 278 | 278 | 278 | 279 | 279 | 280 | 281 | 282
G2c.0529 | I | Number of leakage management equipment interventions | Number | O_AD5_M | MA037, MA073 | Baseline | G90 - Delivery Approval | 2423 | 2440 | 2444 | 2444 | 2499 | 2502 | 2506 | 2519 | 2525 | 2529 | 2529 | 2529 | 2533 | 2533 | 2533 | 2533 | 2533 | 2533 | 2533 | 2534 | 2534 | 2534 | 2536 | 2538 | 2538 | 2540
G2c.0530 | I | [5 empty] | SOS - Start On Site | 14 | 1867 | 1888 | 1888 | 1888 | 1944 | 1947 | 1958 | 2521 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524
G2c.0531 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 3 | 7 | 17 | 36 | 1891 | 1947 | 1958 | 1962 | 1963 | 1964 | 2522 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524
G2c.0532 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 3 | 7 | 7 | 23 | 36 | 1894 | 1958 | 1960 | 1961 | 1961 | 1963 | 2520 | 2521 | 2522 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524 | 2524
G2c.0533 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2423 | 2440 | 2444 | 2444 | 2499 | 2502 | 2506 | 2519 | 2525 | 2529 | 2529 | 2529 | 2533 | 2533 | 2533 | 2533 | 2533 | 2533 | 2533 | 2534 | 2534 | 2534 | 2536 | 2538 | 2538 | 2540
G2c.0534 | I | [5 empty] | SOS - Start On Site | 14 | 2439 | 2443 | 2444 | 2444 | 2488 | 2493 | 2504 | 2516 | 2523 | 2528 | 2528 | 2528 | 2532 | 2533 | 2533 | 2533 | 2533 | 2533 | 2533 | 2534 | 2534 | 2534 | 2536 | 2538 | 2540
G2c.0535 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 3 | 5 | 9 | 11 | 16 | 31 | 35 | 42 | 49 | 717 | 1928 | 1928 | 1932 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 1934 | 2540
G2c.0536 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 7 | 12 | 31 | 31 | 33 | 35 | 58 | 623 | 1883 | 1928 | 1928 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 1933 | 2540
G2c.0537 | I | Number of sites with Water Framework Directive improvements | Number | O_AD6_E | MA063 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0538 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0539 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0540 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0541 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0542 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0543 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0544 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
G2c.0545 | I | Number of Asset Inspections completed | Number | O_AI1_M | MA002, MA004, MA012, MA014, MA016, MA017, MA023, MA025, MA033, MA037, MA039, MA042, MA043, MA046, MA057, MA058, MA082, MA091, MA094, MA096, SR15 | Baseline | G90 - Delivery Approval | 1475 | 1478 | 1484 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487 | 1487 | 1487 | 1487 | 1487 | 1487
G2c.0546 | I | [5 empty] | SOS - Start On Site | 1465 | 1474 | 1476 | 1479 | 1481 | 1483 | 1483 | 1483 | 1483 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484
G2c.0547 | I | [5 empty] | G100 - Acceptance | 0 | 115 | 166 | 1421 | 1479 | 1481 | 1482 | 1483 | 1483 | 1483 | 1483 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484
G2c.0548 | I | [5 empty] | G110 - Financial Closure | 0 | 16 | 55 | 165 | 1361 | 1424 | 1429 | 1481 | 1482 | 1483 | 1483 | 1483 | 1483 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484 | 1484
G2c.0549 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1475 | 1478 | 1484 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487 | 1487 | 1487 | 1487 | 1487 | 1487
G2c.0550 | I | [5 empty] | SOS - Start On Site | 1466 | 1475 | 1481 | 1483 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487 | 1487 | 1487 | 1487
G2c.0551 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 69 | 1275 | 1335 | 1369 | 1389 | 1389 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487 | 1487
G2c.0552 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 16 | 23 | 1228 | 1234 | 1290 | 1298 | 1353 | 1484 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1485 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1486 | 1487 | 1487
G2c.0553 | I | Number of sludge treatment centre asset interventions | Number | O_BR1_M | MA024, MA043, MA057 | Baseline | G90 - Delivery Approval | 57 | 95 | 125 | 150 | 170 | 172 | 194 | 235 | 294 | 296 | 317 | 317 | 317 | 319 | 321 | 321 | 324 | 329 | 329 | 329 | 329 | 330 | 330 | 330 | 331 | 332
G2c.0554 | I | [5 empty] | SOS - Start On Site | 54 | 90 | 116 | 140 | 162 | 165 | 185 | 227 | 285 | 286 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288
G2c.0555 | I | [5 empty] | G100 - Acceptance | 0 | 48 | 85 | 113 | 137 | 159 | 161 | 184 | 224 | 282 | 283 | 287 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288
G2c.0556 | I | [5 empty] | G110 - Financial Closure | 0 | 48 | 85 | 111 | 135 | 157 | 157 | 179 | 222 | 279 | 280 | 280 | 285 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288
G2c.0557 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 57 | 95 | 125 | 150 | 170 | 172 | 194 | 235 | 294 | 296 | 317 | 317 | 317 | 319 | 321 | 321 | 324 | 329 | 329 | 329 | 329 | 330 | 330 | 330 | 331 | 332
G2c.0558 | I | [5 empty] | SOS - Start On Site | 55 | 93 | 120 | 144 | 167 | 168 | 189 | 229 | 289 | 291 | 314 | 315 | 316 | 318 | 318 | 320 | 320 | 324 | 329 | 329 | 329 | 329 | 330 | 330 | 330 | 332
G2c.0559 | I | [5 empty] | G100 - Acceptance | 0 | 17 | 49 | 72 | 99 | 123 | 128 | 150 | 179 | 280 | 282 | 292 | 294 | 297 | 300 | 300 | 300 | 300 | 300 | 301 | 302 | 303 | 309 | 309 | 329 | 332
G2c.0560 | I | [5 empty] | G110 - Financial Closure | 0 | 17 | 47 | 71 | 99 | 121 | 126 | 144 | 172 | 275 | 276 | 282 | 285 | 289 | 294 | 296 | 298 | 299 | 299 | 299 | 299 | 301 | 303 | 306 | 309 | 332
G2c.0561 | I | Number of WwTW sites with Environmental Pollution risk reduced | Number | O_BR2_E | MA084 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0562 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0563 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0564 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0565 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0566 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0567 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
G2c.0568 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
G2c.0569 | I | Number of plans to improve customer experience | Number | O_CE1_E1 | MA110 | Baseline | G90 - Delivery Approval | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0570 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0571 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
G2c.0572 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4
G2c.0573 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0574 | I | [5 empty] | SOS - Start On Site | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0575 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
G2c.0576 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4
G2c.0577 | I | Number of process improvements to support improved response to priority service customers | Number | O_CE1_E2 | MA110 | Baseline | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0578 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0579 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0580 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0581 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0582 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0583 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0584 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0585 | I | Number of plans to improve customer experience developed | Number | O_CE3_E | MA110 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0586 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0587 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0588 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0589 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0590 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0591 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0592 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0593 | I | Investigations | Number | O_CM_INV | MA002, MA003, MA062 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0594 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0595 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695 | 703 | 703 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0596 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 703 | 703 | 703 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0597 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0598 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 273 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0599 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695 | 703 | 703 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0600 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 703 | 703 | 703 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947 | 947
G2c.0601 | I | Water Infrastructure - Reservoir Maintenance | Number | O_CM_RES | MA004 | Baseline | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0602 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0603 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0604 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0605 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0606 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0607 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0608 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0609 | I | Wastewater Infrastructure Sewers | Number | O_CM_SEW | MA014 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0610 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0611 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0612 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0613 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0614 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0615 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0616 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0617 | I | Wastewater Non Infrastructure - Sludge Treatment Facilities | Number | O_CM_STF | MA024 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0618 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0619 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0620 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0621 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0622 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0623 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.0624 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.0625 | I | Water Non Infrastructure - Treated Water Pumping | Number | O_CM_TWP | MA082 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0626 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0627 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0628 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0629 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0630 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0631 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
G2c.0632 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
G2c.0633 | I | Number of sites with metals removal interventions | Number | O_DC1_M | MA033 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
G2c.0634 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0635 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0636 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0637 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
G2c.0638 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2
G2c.0639 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
G2c.0640 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
G2c.0641 | I | Length of water main replaced or refurbished | Metres | O_DC2_E | MA016 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 7501 | 7501 | 7502 | 7502 | 9433 | 10283 | 14075 | 14075 | 15475 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2c.0642 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 7311 | 7502 | 7622 | 8173 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433
G2c.0643 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 313 | 9003 | 9293 | 9293 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433
G2c.0644 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 312 | 492 | 783 | 9293 | 9293 | 9293 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433 | 9433
G2c.0645 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 7501 | 7501 | 7502 | 7502 | 9433 | 10283 | 14075 | 14075 | 15475 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2c.0646 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 7311 | 7311 | 7312 | 7312 | 7993 | 9433 | 10283 | 14075 | 14075 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2c.0647 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 7432 | 7433 | 7943 | 10283 | 11483 | 11483 | 11483 | 11483 | 14230 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2c.0648 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 122 | 302 | 8753 | 10283 | 11483 | 11483 | 11483 | 11638 | 14230 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630 | 15630
G2c.0649 | I | Length of water mains cleaned | Metres | O_DC2_M | MA016 | Baseline | G90 - Delivery Approval | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 647648 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649
G2c.0650 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 636648 | 636648 | 636648 | 636648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648 | 645648
G2c.0651 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 292423 | 636648 | 636648 | 636648 | 645648 | 645648 | 645648
G2c.0652 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 292423 | 292423 | 636648 | 636648 | 645648
G2c.0653 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 647648 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649
G2c.0654 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 104687 | 104687 | 104687 | 104687 | 104687 | 104687 | 106687 | 638649 | 638649 | 638649 | 638649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649 | 647649
G2c.0655 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106687 | 106687 | 106687 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 638649 | 638649 | 638649 | 638649 | 647649 | 647649 | 647649
G2c.0656 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 106687 | 106687 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 106688 | 638649 | 638649 | 638649 | 638649 | 647649
G2c.0657 | I | Length of water mains cleaned | Metres | O_DC2_M1 | MA016, MA099, SR15 | Baseline | G90 - Delivery Approval | 2249939 | 2249939 | 2257939 | 5071939 | 5071940 | 5071940 | 5071940 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2c.0658 | I | [5 empty] | SOS - Start On Site | 2249939 | 2249939 | 2249939 | 5063939 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940
G2c.0659 | I | [5 empty] | G100 - Acceptance | 0 | 449939 | 449939 | 2249939 | 2249939 | 2706940 | 2706940 | 2706940 | 2706940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940
G2c.0660 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1800000 | 2249939 | 2249940 | 2249940 | 2249940 | 2706940 | 2706940 | 2706940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940 | 5063940
G2c.0661 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2249939 | 2249939 | 2257939 | 5071939 | 5071940 | 5071940 | 5071940 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2c.0662 | I | [5 empty] | SOS - Start On Site | 2249939 | 2249939 | 2257939 | 5071939 | 5071940 | 5071940 | 5071940 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2c.0663 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 449939 | 2249939 | 2249939 | 2249939 | 2249939 | 2249940 | 2257940 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2c.0664 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 449939 | 449939 | 449939 | 449939 | 449940 | 449940 | 2249941 | 2257941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941 | 5071941
G2c.0665 | I | Length of water mains replaced or refurbished | Metres | O_DC2_M2 | MA016 | Baseline | G90 - Delivery Approval | 18401 | 19983 | 20238 | 20238 | 27942 | 27943 | 27946 | 27946 | 30730 | 30730 | 32730 | 32736 | 32736 | 32736 | 32736 | 32736 | 32736 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987
G2c.0666 | I | [5 empty] | SOS - Start On Site | 18400 | 18400 | 19982 | 19983 | 20238 | 20240 | 20243 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343
G2c.0667 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 217 | 1798 | 1839 | 1842 | 1843 | 1943 | 1943 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343
G2c.0668 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 215 | 215 | 1797 | 1800 | 1801 | 1842 | 1843 | 1943 | 1943 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343 | 20343
G2c.0669 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 18401 | 19983 | 20238 | 20238 | 27942 | 27943 | 27946 | 27946 | 30730 | 30730 | 32730 | 32736 | 32736 | 32736 | 32736 | 32736 | 32736 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987
G2c.0670 | I | [5 empty] | SOS - Start On Site | 18400 | 18400 | 18401 | 18402 | 27940 | 27941 | 27945 | 27945 | 29029 | 30730 | 30730 | 32730 | 32736 | 32736 | 32736 | 32736 | 32736 | 32737 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987 | 33987
G2c.0671 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 257 | 358 | 1941 | 1942 | 9546 | 27948 | 29299 | 30730 | 30730 | 30730 | 30730 | 30730 | 32734 | 32736 | 32736 | 32736 | 32737 | 32737 | 32737 | 33987 | 33987 | 33987
G2c.0672 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 359 | 1944 | 1945 | 20347 | 20847 | 28679 | 29530 | 30730 | 30730 | 30730 | 30730 | 32734 | 32736 | 32736 | 32737 | 32737 | 32737 | 33987 | 33987
G2c.0673 | I | Number of plans to improve customer experience | Number | O_DC4_E | MA016 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0674 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0675 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0676 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0677 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0678 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0679 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0680 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0681 | I | Number of digital transformation interventions | Number | O_DI1_M | MA066 | Baseline | G90 - Delivery Approval | 9 | 15 | 16 | 17 | 19 | 4522 | 4525 | 4529 | 4529 | 4530 | 4535 | 4536 | 4536 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538
G2c.0682 | I | [5 empty] | SOS - Start On Site | 6 | 8 | 10 | 12 | 13 | 4515 | 4519 | 4521 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523 | 4523
G2c.0683 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 7 | 7 | 7 | 7 | 7 | 10 | 11 | 13 | 13 | 14 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 4519 | 4519 | 4519 | 4519 | 4523 | 4523
G2c.0684 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 4 | 6 | 7 | 7 | 10 | 11 | 13 | 14 | 14 | 16 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 4519 | 4519 | 4519 | 4523 | 4523
G2c.0685 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9 | 15 | 16 | 17 | 19 | 4522 | 4525 | 4529 | 4529 | 4530 | 4535 | 4536 | 4536 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538
G2c.0686 | I | [5 empty] | SOS - Start On Site | 9 | 15 | 16 | 17 | 18 | 4520 | 4525 | 4526 | 4529 | 4529 | 4535 | 4535 | 4536 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538 | 4538
G2c.0687 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 6 | 8 | 10 | 13 | 13 | 13 | 13 | 17 | 19 | 22 | 23 | 26 | 29 | 30 | 31 | 33 | 33 | 33 | 4534 | 4534 | 4534 | 4534 | 4538 | 4538
G2c.0688 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 4 | 7 | 9 | 11 | 12 | 12 | 13 | 13 | 16 | 21 | 21 | 24 | 26 | 29 | 31 | 31 | 33 | 33 | 33 | 4534 | 4534 | 4534 | 4538 | 4538
G2c.0689 | I | Increase in Part 4 capacity to meet local growth requirements | Population Equivalent | O_ED3_G | MA017, MA043 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 1114
G2c.0690 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0691 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0692 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0693 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 765 | 1114
G2c.0694 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 765 | 765 | 1114
G2c.0695 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114
G2c.0696 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114
G2c.0697 | I | Number of properties removed from internal flooding at risk register. | Number | O_FR1_F1 | MA020, MA039, SR15 | Baseline | G90 - Delivery Approval | 84 | 214 | 219 | 225 | 236 | 260 | 260 | 262 | 275 | 277 | 290 | 297 | 307 | 318 | 333 | 348 | 362 | 384 | 393 | 411 | 437 | 454 | 455 | 456 | 456 | 457
G2c.0698 | I | [5 empty] | SOS - Start On Site | 61 | 78 | 85 | 215 | 216 | 220 | 233 | 245 | 245 | 266 | 266 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268
G2c.0699 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 15 | 32 | 56 | 195 | 217 | 223 | 223 | 224 | 233 | 238 | 238 | 245 | 256 | 267 | 267 | 267 | 268 | 268 | 268 | 268 | 268 | 268 | 268 | 268
G2c.0700 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 16 | 27 | 165 | 186 | 206 | 223 | 223 | 228 | 228 | 235 | 245 | 245 | 255 | 267 | 267 | 268 | 268 | 268 | 268 | 268 | 268 | 268
G2c.0701 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 84 | 214 | 219 | 225 | 236 | 260 | 260 | 262 | 275 | 277 | 290 | 297 | 307 | 318 | 333 | 348 | 362 | 384 | 393 | 411 | 437 | 454 | 455 | 456 | 456 | 457
G2c.0702 | I | [5 empty] | SOS - Start On Site | 64 | 80 | 208 | 214 | 220 | 234 | 253 | 253 | 255 | 267 | 282 | 283 | 291 | 307 | 319 | 338 | 348 | 363 | 385 | 398 | 426 | 440 | 454 | 455 | 456 | 457
G2c.0703 | I | [5 empty] | G100 - Acceptance | 0 | 10 | 11 | 149 | 167 | 175 | 182 | 196 | 223 | 234 | 236 | 242 | 244 | 245 | 282 | 295 | 297 | 301 | 318 | 335 | 349 | 357 | 375 | 384 | 404 | 457
G2c.0704 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 14 | 25 | 35 | 173 | 207 | 215 | 230 | 233 | 237 | 241 | 252 | 263 | 295 | 297 | 301 | 313 | 322 | 343 | 355 | 368 | 383 | 457
G2c.0705 | I | Number of properties with temporary internal flood prevention measures | Number | O_FR1_F2 | MA020 | Baseline | G90 - Delivery Approval | 28 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0706 | I | [5 empty] | SOS - Start On Site | 28 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216
G2c.0707 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 216
G2c.0708 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 216
G2c.0709 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 28 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0710 | I | [5 empty] | SOS - Start On Site | 28 | 28 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219 | 219
G2c.0711 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 219
G2c.0712 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 219
G2c.0713 | I | Number of properties removed from external flooding at risk register. | Number | O_FR2_F | MA020, SR15 | Baseline | G90 - Delivery Approval | 61 | 75 | 75 | 81 | 88 | 92 | 92 | 98 | 101 | 103 | 104 | 139 | 142 | 166 | 234 | 261 | 321 | 331 | 351 | 364 | 377 | 382 | 382 | 383 | 383 | 391
G2c.0714 | I | [5 empty] | SOS - Start On Site | 14 | 28 | 28 | 28 | 36 | 48 | 48 | 48 | 48 | 48 | 49 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0715 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 2 | 10 | 10 | 10 | 36 | 36 | 42 | 42 | 48 | 48 | 48 | 48 | 48 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0716 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 2 | 2 | 10 | 10 | 18 | 22 | 22 | 28 | 28 | 34 | 34 | 48 | 48 | 48 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0717 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 61 | 75 | 75 | 81 | 88 | 92 | 92 | 98 | 101 | 103 | 104 | 139 | 142 | 166 | 234 | 261 | 321 | 331 | 351 | 364 | 377 | 382 | 382 | 383 | 383 | 391
G2c.0718 | I | [5 empty] | SOS - Start On Site | 53 | 67 | 67 | 67 | 68 | 74 | 84 | 84 | 85 | 90 | 92 | 96 | 131 | 142 | 206 | 234 | 257 | 322 | 343 | 351 | 364 | 377 | 382 | 383 | 383 | 391
G2c.0719 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 10 | 19 | 49 | 49 | 54 | 54 | 55 | 81 | 86 | 89 | 91 | 115 | 122 | 122 | 122 | 122 | 201 | 249 | 257 | 322 | 331 | 350 | 364 | 391
G2c.0720 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 19 | 20 | 47 | 49 | 54 | 55 | 66 | 66 | 67 | 70 | 95 | 118 | 122 | 122 | 130 | 193 | 214 | 256 | 274 | 325 | 343 | 391
G2c.0721 | I | Number of flood risk management (Section 16) models | Number | O_FR3_F | MA020 | Baseline | G90 - Delivery Approval | 4 | 4 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0722 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0723 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0724 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0725 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 4 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0726 | I | [5 empty] | SOS - Start On Site | 4 | 4 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10
G2c.0727 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10
G2c.0728 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 10 | 10 | 10 | 10
G2c.0729 | I | Number of education campaigns targeted at customers in sewer choke hot spot areas | Number | O_FR5_F2 | MA020 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0730 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0731 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0732 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0733 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0734 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0735 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0736 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0737 | I | Number of reservoir interests of Safety interventions | Number | O_HS1_M1 | MA004 | Baseline | G90 - Delivery Approval | 98 | 167 | 206 | 238 | 253 | 269 | 289 | 325 | 340 | 352 | 369 | 377 | 379 | 389 | 393 | 393 | 393 | 418 | 418 | 420 | 420 | 420 | 421 | 422 | 422 | 422
G2c.0738 | I | [5 empty] | SOS - Start On Site | 74 | 90 | 168 | 182 | 214 | 226 | 264 | 292 | 303 | 322 | 324 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325
G2c.0739 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 14 | 68 | 140 | 168 | 198 | 215 | 245 | 267 | 276 | 309 | 313 | 315 | 320 | 320 | 323 | 324 | 324 | 324 | 325 | 325 | 325 | 325 | 325 | 325
G2c.0740 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 7 | 17 | 62 | 145 | 164 | 196 | 212 | 241 | 257 | 283 | 301 | 308 | 317 | 319 | 321 | 323 | 324 | 324 | 324 | 324 | 324 | 325 | 325 | 325
G2c.0741 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 98 | 167 | 206 | 238 | 253 | 269 | 289 | 325 | 340 | 352 | 369 | 377 | 379 | 389 | 393 | 393 | 393 | 418 | 418 | 420 | 420 | 420 | 421 | 422 | 422 | 422
G2c.0742 | I | [5 empty] | SOS - Start On Site | 75 | 96 | 121 | 140 | 227 | 232 | 266 | 292 | 323 | 334 | 354 | 367 | 374 | 382 | 388 | 389 | 389 | 408 | 418 | 418 | 420 | 420 | 420 | 421 | 422 | 422
G2c.0743 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 16 | 32 | 43 | 78 | 137 | 156 | 213 | 235 | 267 | 312 | 323 | 352 | 364 | 368 | 378 | 383 | 385 | 391 | 404 | 415 | 417 | 418 | 419 | 422
G2c.0744 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 7 | 18 | 53 | 66 | 81 | 154 | 207 | 225 | 244 | 292 | 315 | 345 | 356 | 363 | 375 | 380 | 383 | 389 | 398 | 407 | 414 | 417 | 422
G2c.0745 | I | Number of sites with standby power equipment interventions | Number | O_HS1_M11 | MA092, MA096 | Baseline | G90 - Delivery Approval | 274 | 282 | 293 | 295 | 306 | 306 | 307 | 309 | 311 | 311 | 313 | 313 | 313 | 313 | 313 | 314 | 314 | 314 | 314 | 316 | 316 | 317 | 317 | 317 | 322 | 323
G2c.0746 | I | [5 empty] | SOS - Start On Site | 273 | 280 | 288 | 290 | 301 | 303 | 304 | 305 | 306 | 306 | 307 | 307 | 307 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308
G2c.0747 | I | [5 empty] | G100 - Acceptance | 14 | 271 | 277 | 286 | 289 | 301 | 301 | 301 | 305 | 306 | 306 | 307 | 307 | 307 | 307 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308
G2c.0748 | I | [5 empty] | G110 - Financial Closure | 14 | 256 | 277 | 284 | 286 | 298 | 301 | 301 | 301 | 303 | 304 | 306 | 307 | 307 | 307 | 307 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308
G2c.0749 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 274 | 282 | 293 | 295 | 306 | 306 | 307 | 309 | 311 | 311 | 313 | 313 | 313 | 313 | 313 | 314 | 314 | 314 | 314 | 316 | 316 | 317 | 317 | 317 | 322 | 323
G2c.0750 | I | [5 empty] | SOS - Start On Site | 273 | 280 | 288 | 292 | 304 | 306 | 306 | 307 | 308 | 308 | 310 | 311 | 311 | 312 | 313 | 313 | 314 | 314 | 314 | 314 | 316 | 316 | 317 | 317 | 317 | 323
G2c.0751 | I | [5 empty] | G100 - Acceptance | 0 | 15 | 18 | 25 | 41 | 50 | 292 | 296 | 299 | 308 | 308 | 310 | 310 | 310 | 311 | 312 | 313 | 313 | 314 | 314 | 314 | 314 | 316 | 316 | 316 | 323
G2c.0752 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 18 | 21 | 40 | 48 | 292 | 296 | 298 | 307 | 308 | 309 | 310 | 310 | 310 | 310 | 312 | 312 | 313 | 313 | 314 | 314 | 314 | 316 | 316 | 323
G2c.0753 | I | Number of water sites with telemetry interventions | Number | O_HS1_M12 | MA022, MA044 | Baseline | G90 - Delivery Approval | 223 | 237 | 240 | 241 | 244 | 244 | 418 | 418 | 511 | 696 | 698 | 793 | 793 | 793 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 854 | 854
G2c.0754 | I | [5 empty] | SOS - Start On Site | 209 | 223 | 233 | 234 | 237 | 242 | 242 | 416 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509
G2c.0755 | I | [5 empty] | G100 - Acceptance | 0 | 208 | 222 | 225 | 234 | 237 | 237 | 242 | 242 | 242 | 242 | 243 | 243 | 243 | 243 | 335 | 407 | 407 | 509 | 509 | 509 | 509 | 509 | 509 | 509 | 509
G2c.0756 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 220 | 225 | 226 | 237 | 237 | 237 | 242 | 242 | 242 | 242 | 243 | 243 | 243 | 243 | 243 | 335 | 407 | 407 | 509 | 509 | 509 | 509 | 509 | 509
G2c.0757 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 223 | 237 | 240 | 241 | 244 | 244 | 418 | 418 | 511 | 696 | 698 | 793 | 793 | 793 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 854 | 854
G2c.0758 | I | [5 empty] | SOS - Start On Site | 209 | 231 | 235 | 236 | 239 | 244 | 244 | 418 | 511 | 511 | 615 | 615 | 710 | 710 | 710 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 853 | 854
G2c.0759 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 220 | 225 | 227 | 227 | 227 | 227 | 239 | 244 | 245 | 247 | 247 | 350 | 536 | 608 | 608 | 710 | 793 | 853 | 853 | 853 | 853 | 853 | 854
G2c.0760 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 4 | 10 | 217 | 226 | 227 | 227 | 227 | 239 | 239 | 239 | 245 | 247 | 247 | 349 | 349 | 536 | 608 | 608 | 793 | 793 | 853 | 853 | 853 | 854
G2c.0761 | I | Number of water property operational buildings interventions | Number | O_HS1_M13 | MA015, MA025, MA096 | Baseline | G90 - Delivery Approval | 252 | 304 | 446 | 447 | 475 | 476 | 488 | 491 | 502 | 506 | 508 | 510 | 510 | 513 | 513 | 513 | 513 | 516 | 517 | 517 | 517 | 517 | 517 | 517 | 517 | 517
G2c.0762 | I | [5 empty] | SOS - Start On Site | 54 | 278 | 308 | 319 | 349 | 357 | 466 | 467 | 481 | 482 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484
G2c.0763 | I | [5 empty] | G100 - Acceptance | 0 | 50 | 273 | 300 | 309 | 342 | 349 | 353 | 466 | 468 | 480 | 482 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484
G2c.0764 | I | [5 empty] | G110 - Financial Closure | 0 | 46 | 89 | 299 | 304 | 330 | 336 | 345 | 350 | 463 | 467 | 467 | 469 | 483 | 483 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484 | 484
G2c.0765 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 252 | 304 | 446 | 447 | 475 | 476 | 488 | 491 | 502 | 506 | 508 | 510 | 510 | 513 | 513 | 513 | 513 | 516 | 517 | 517 | 517 | 517 | 517 | 517 | 517 | 517
G2c.0766 | I | [5 empty] | SOS - Start On Site | 56 | 101 | 315 | 319 | 354 | 358 | 361 | 366 | 381 | 494 | 500 | 502 | 505 | 506 | 508 | 508 | 508 | 512 | 516 | 517 | 517 | 517 | 517 | 517 | 517 | 517
G2c.0767 | I | [5 empty] | G100 - Acceptance | 1 | 23 | 58 | 90 | 111 | 117 | 129 | 135 | 150 | 367 | 370 | 390 | 397 | 399 | 506 | 506 | 511 | 511 | 512 | 513 | 515 | 516 | 517 | 517 | 517 | 517
G2c.0768 | I | [5 empty] | G110 - Financial Closure | 1 | 18 | 53 | 86 | 105 | 111 | 121 | 125 | 140 | 359 | 360 | 373 | 374 | 394 | 501 | 504 | 505 | 508 | 509 | 511 | 511 | 514 | 516 | 517 | 517 | 517
G2c.0769 | I | Number of raw water storage asset interventions | Number | O_HS1_M2 | MA025, MA074, MA094 | Baseline | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 49 | 49 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0770 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0771 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0772 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
G2c.0773 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 2 | 2 | 2 | 49 | 49 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0774 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 50 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0775 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 52
G2c.0776 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52
G2c.0777 | I | Number of water pipe bridge interventions | Number | O_HS1_M3 | MA003, MA016, MA025, MA070 | Baseline | G90 - Delivery Approval | 7 | 9 | 9 | 16 | 18 | 19 | 21 | 37 | 44 | 45 | 48 | 48 | 103 | 123 | 127 | 191 | 191 | 191 | 195 | 195 | 195 | 195 | 294 | 294 | 294 | 375
G2c.0778 | I | [5 empty] | SOS - Start On Site | 2 | 6 | 6 | 8 | 12 | 18 | 20 | 35 | 41 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
G2c.0779 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 6 | 10 | 13 | 23 | 35 | 41 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
G2c.0780 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 3 | 7 | 9 | 17 | 34 | 41 | 41 | 41 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
G2c.0781 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 7 | 9 | 9 | 16 | 18 | 19 | 21 | 37 | 44 | 45 | 48 | 48 | 103 | 123 | 127 | 191 | 191 | 191 | 195 | 195 | 195 | 195 | 294 | 294 | 294 | 375
G2c.0782 | I | [5 empty] | SOS - Start On Site | 2 | 5 | 8 | 10 | 14 | 16 | 19 | 34 | 41 | 43 | 45 | 47 | 47 | 105 | 123 | 127 | 191 | 191 | 191 | 195 | 195 | 195 | 195 | 294 | 294 | 375
G2c.0783 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 5 | 5 | 7 | 11 | 18 | 37 | 39 | 40 | 40 | 45 | 45 | 47 | 47 | 47 | 104 | 104 | 121 | 190 | 190 | 194 | 195 | 375
G2c.0784 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 8 | 15 | 33 | 35 | 36 | 38 | 40 | 43 | 44 | 46 | 47 | 47 | 97 | 104 | 104 | 121 | 190 | 194 | 375
G2c.0785 | I | Number of fixed wire electrical system or statutory maintenance asset interventions | Number | O_HS1_M4 | MA068 | Baseline | G90 - Delivery Approval | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2c.0786 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0787 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0788 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0789 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2c.0790 | I | [5 empty] | SOS - Start On Site | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2c.0791 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2c.0792 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824 | 824
G2c.0793 | I | Number of SCADA, HMI, PLC asset interventions | Number | O_HS1_M5 | MA022, MA091, MA095 | Baseline | G90 - Delivery Approval | 22 | 206 | 210 | 231 | 234 | 234 | 364 | 369 | 371 | 372 | 375 | 380 | 400 | 409 | 415 | 422 | 442 | 450 | 453 | 466 | 466 | 469 | 469 | 469 | 469 | 474
G2c.0794 | I | [5 empty] | SOS - Start On Site | 13 | 195 | 202 | 208 | 209 | 210 | 210 | 210 | 210 | 338 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 340 | 340 | 340 | 340 | 340 | 340 | 340
G2c.0795 | I | [5 empty] | G100 - Acceptance | 0 | 9 | 25 | 32 | 33 | 33 | 34 | 35 | 36 | 37 | 38 | 40 | 46 | 46 | 173 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 340
G2c.0796 | I | [5 empty] | G110 - Financial Closure | 0 | 8 | 24 | 29 | 30 | 30 | 33 | 33 | 34 | 35 | 35 | 35 | 36 | 44 | 46 | 173 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 339 | 340
G2c.0797 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 22 | 206 | 210 | 231 | 234 | 234 | 364 | 369 | 371 | 372 | 375 | 380 | 400 | 409 | 415 | 422 | 442 | 450 | 453 | 466 | 466 | 469 | 469 | 469 | 469 | 474
G2c.0798 | I | [5 empty] | SOS - Start On Site | 14 | 197 | 203 | 228 | 232 | 232 | 233 | 238 | 242 | 243 | 244 | 250 | 267 | 273 | 279 | 281 | 290 | 309 | 312 | 453 | 464 | 466 | 469 | 469 | 469 | 474
G2c.0799 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 9 | 41 | 51 | 52 | 54 | 55 | 60 | 67 | 67 | 73 | 76 | 82 | 83 | 251 | 253 | 257 | 258 | 269 | 273 | 290 | 300 | 305 | 447 | 474
G2c.0800 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 9 | 22 | 51 | 51 | 52 | 53 | 55 | 60 | 64 | 67 | 67 | 74 | 79 | 83 | 85 | 252 | 256 | 258 | 260 | 271 | 286 | 292 | 303 | 474
G2c.0801 | I | Number of WTW Chemical Storage and Dosing Vessel interventions | Number | O_HS1_M6 | MA046, MA095, MA096 | Baseline | G90 - Delivery Approval | 120 | 172 | 177 | 178 | 178 | 179 | 182 | 183 | 194 | 196 | 1104 | 1106 | 1109 | 1110 | 1111 | 1112 | 1112 | 1112 | 1112 | 1131 | 1131 | 1131 | 1131 | 1131 | 1131 | 1131
G2c.0802 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 55 | 57 | 59 | 63 | 66 | 67 | 73 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78
G2c.0803 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 3 | 6 | 6 | 56 | 58 | 62 | 65 | 69 | 69 | 72 | 72 | 75 | 75 | 75 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 78
G2c.0804 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 6 | 6 | 6 | 56 | 58 | 61 | 65 | 67 | 69 | 69 | 72 | 74 | 75 | 75 | 75 | 75 | 78 | 78 | 78 | 78 | 78 | 78 | 78
G2c.0805 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 120 | 172 | 177 | 178 | 178 | 179 | 182 | 183 | 194 | 196 | 1104 | 1106 | 1109 | 1110 | 1111 | 1112 | 1112 | 1112 | 1112 | 1131 | 1131 | 1131 | 1131 | 1131 | 1131 | 1131
G2c.0806 | I | [5 empty] | SOS - Start On Site | 116 | 118 | 170 | 172 | 174 | 177 | 182 | 183 | 189 | 194 | 196 | 550 | 1105 | 1109 | 1111 | 1111 | 1112 | 1112 | 1112 | 1112 | 1112 | 1131 | 1131 | 1131 | 1131 | 1131
G2c.0807 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 120 | 120 | 120 | 123 | 125 | 128 | 183 | 184 | 189 | 191 | 193 | 750 | 752 | 755 | 757 | 1111 | 1111 | 1112 | 1112 | 1112 | 1131 | 1131 | 1131
G2c.0808 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 4 | 119 | 120 | 121 | 123 | 123 | 130 | 134 | 184 | 184 | 192 | 192 | 747 | 747 | 753 | 757 | 1111 | 1111 | 1112 | 1112 | 1112 | 1131 | 1131
G2c.0809 | I | Number of street furniture interventions | Number | O_HS1_M7 | MA018 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0810 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0811 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0812 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0813 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0814 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0815 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0816 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.0817 | I | Number of high voltage system interventions | Number | O_HS1_M8 | MA058, MA091, MA092 | Baseline | G90 - Delivery Approval | 26 | 28 | 28 | 28 | 28 | 29 | 30 | 31 | 32 | 33 | 33 | 34 | 34 | 34 | 37 | 37 | 39 | 49 | 53 | 57 | 57 | 57 | 59 | 59 | 59 | 60
G2c.0818 | I | [5 empty] | SOS - Start On Site | 25 | 27 | 28 | 28 | 28 | 28 | 28 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0819 | I | [5 empty] | G100 - Acceptance | 0 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0820 | I | [5 empty] | G110 - Financial Closure | 0 | 23 | 24 | 25 | 25 | 26 | 26 | 26 | 29 | 29 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.0821 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 26 | 28 | 28 | 28 | 28 | 29 | 30 | 31 | 32 | 33 | 33 | 34 | 34 | 34 | 37 | 37 | 39 | 49 | 53 | 57 | 57 | 57 | 59 | 59 | 59 | 60
G2c.0822 | I | [5 empty] | SOS - Start On Site | 25 | 27 | 27 | 27 | 27 | 28 | 30 | 31 | 32 | 33 | 33 | 33 | 33 | 33 | 35 | 37 | 37 | 48 | 49 | 53 | 57 | 57 | 57 | 59 | 59 | 60
G2c.0823 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 7 | 31 | 31 | 33 | 33 | 33 | 33 | 33 | 33 | 36 | 36 | 45 | 45 | 46 | 46 | 46 | 51 | 60
G2c.0824 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 4 | 28 | 28 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 34 | 36 | 45 | 45 | 45 | 46 | 46 | 60
G2c.0825 | I | Number of water sites with Motor Control Centre interventions | Number | O_HS1_M9 | MA025, MA082, MA091, MA092, MA094 | Baseline | G90 - Delivery Approval | 1 | 5 | 107 | 107 | 108 | 255 | 255 | 255 | 258 | 258 | 259 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 261 | 261 | 268
G2c.0826 | I | [5 empty] | SOS - Start On Site | 1 | 4 | 4 | 6 | 107 | 107 | 107 | 240 | 240 | 240 | 240 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241
G2c.0827 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 4 | 4 | 5 | 6 | 6 | 107 | 107 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 241 | 241 | 241 | 241 | 241 | 241 | 241 | 241
G2c.0828 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 107 | 107 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 241 | 241 | 241 | 241 | 241
G2c.0829 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 5 | 107 | 107 | 108 | 255 | 255 | 255 | 258 | 258 | 259 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 261 | 261 | 268
G2c.0830 | I | [5 empty] | SOS - Start On Site | 1 | 4 | 4 | 105 | 107 | 121 | 122 | 255 | 256 | 256 | 257 | 259 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 261 | 268
G2c.0831 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 3 | 4 | 18 | 19 | 19 | 20 | 123 | 123 | 256 | 258 | 258 | 258 | 258 | 258 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 268
G2c.0832 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 3 | 3 | 5 | 18 | 19 | 20 | 21 | 21 | 122 | 256 | 257 | 258 | 258 | 258 | 258 | 259 | 259 | 259 | 259 | 259 | 259 | 259 | 268
G2c.0833 | I | Number of sites with water security enhancements | Number | O_HS2_E | MA089 | Baseline | G90 - Delivery Approval | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0834 | I | [5 empty] | SOS - Start On Site | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0835 | I | [5 empty] | G100 - Acceptance | 0 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0836 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0837 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0838 | I | [5 empty] | SOS - Start On Site | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0839 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0840 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 34 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G2c.0841 | I | Number of sites with reservoir drawdown enhancements | Number | O_HS3_E | MA004 | Baseline | G90 - Delivery Approval | 3 | 3 | 4 | 5 | 5 | 5 | 6 | 6 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 13 | 15 | 15 | 15 | 15 | 15
G2c.0842 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0843 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0844 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.0845 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 3 | 4 | 5 | 5 | 5 | 6 | 6 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 13 | 15 | 15 | 15 | 15 | 15
G2c.0846 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 4 | 4 | 5 | 5 | 5 | 6 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 13 | 15 | 15 | 15 | 15
G2c.0847 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 4 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 11 | 12 | 13 | 13 | 13 | 15
G2c.0848 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 5 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 15
G2c.0849 | I | Number of interventions to reduce risk of flooding from mains | Number | O_HS4_E | MA025, MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5
G2c.0850 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0851 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0852 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0853 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5
G2c.0854 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5
G2c.0855 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 5
G2c.0856 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5
G2c.0857 | I | Number of sites with catchment management safety interventions | Number | O_HS5_M | _MA_proj_app_W | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0858 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0859 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0860 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0861 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0862 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0863 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0864 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0865 | I | Number of innovation pilot programmes undertaken | Number | O_IN1_M | MA048, SR15 | Baseline | G90 - Delivery Approval | 35 | 155 | 155 | 155 | 155 | 156 | 156 | 156 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157
G2c.0866 | I | [5 empty] | SOS - Start On Site | 35 | 35 | 155 | 155 | 155 | 156 | 156 | 156 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157
G2c.0867 | I | [5 empty] | G100 - Acceptance | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 157
G2c.0868 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 157
G2c.0869 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 35 | 155 | 155 | 155 | 155 | 156 | 156 | 156 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157
G2c.0870 | I | [5 empty] | SOS - Start On Site | 35 | 35 | 155 | 155 | 155 | 156 | 156 | 156 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157 | 157
G2c.0871 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 157
G2c.0872 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 157
G2c.0873 | I | Number of Transformation activities enabled | Number | O_IN2_M | MA104 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 16 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G2c.0874 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.0875 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 9 | 12 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.0876 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 8 | 11 | 11 | 12 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.0877 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 16 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G2c.0878 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 8 | 16 | 18 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G2c.0879 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 16 | 19 | 19 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22
G2c.0880 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 15 | 16 | 18 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 22
G2c.0881 | I | Number of scientific services facilities upgraded | Number | O_JH1_M | _MA_proj_app_SS | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0882 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0883 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0884 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.0885 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0886 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0887 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3
G2c.0888 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3
G2c.0889 | I | Number of Phosphate Equipment asset interventions | Number | O_LD1_M | MA094 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0890 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0891 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0892 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0893 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0894 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0895 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0896 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.0897 | I | Number of Phosphate Equipment asset interventions | Number | O_LD1_M1 | MA046, MA094 | Baseline | G90 - Delivery Approval | 0 | 6 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0898 | I | [5 empty] | SOS - Start On Site | 0 | 6 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0899 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0900 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.0901 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 6 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0902 | I | [5 empty] | SOS - Start On Site | 0 | 6 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0903 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 7 | 7 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0904 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 4 | 6 | 6 | 6 | 7 | 7 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
G2c.0905 | I | Number of WTW Instrumentation interventions | Number | O_LD1_M2 | MA095 | Baseline | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0906 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0907 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0908 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0909 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0910 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0911 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0912 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.0913 | I | Number of vehicle or plant item interventions | Number | O_LV1_M | MA071 | Baseline | G90 - Delivery Approval | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782
G2c.0914 | I | [5 empty] | SOS - Start On Site | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608
G2c.0915 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608
G2c.0916 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608 | 1608
G2c.0917 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782
G2c.0918 | I | [5 empty] | SOS - Start On Site | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782 | 1782
G2c.0919 | I | [5 empty] | G100 - Acceptance | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 1782 | 1782 | 1782 | 1782
G2c.0920 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 174 | 1782 | 1782 | 1782
G2c.0921 | I | Number of existing meter interventions | Number | O_MR1_M | MA034 | Baseline | G90 - Delivery Approval | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0922 | I | [5 empty] | SOS - Start On Site | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0923 | I | [5 empty] | G100 - Acceptance | 0 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0924 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0925 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0926 | I | [5 empty] | SOS - Start On Site | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0927 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0928 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507 | 24507
G2c.0929 | I | Number of properties with meter installations for first time registered non domestic premises | Number | O_MR2_G | MA034 | Baseline | G90 - Delivery Approval | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0930 | I | [5 empty] | SOS - Start On Site | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0931 | I | [5 empty] | G100 - Acceptance | 0 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0932 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0933 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0934 | I | [5 empty] | SOS - Start On Site | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0935 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0936 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444 | 16444
G2c.0937 | I | Number of catchments with intelligent network technology | Number | O_NI1_E1 | MA104 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0938 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0939 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0940 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0941 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0942 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0943 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0944 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.0945 | I | Number of Event Duration Monitors (EDM) deployed | Number | O_NI1_E2 | MA104 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2c.0946 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0947 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0948 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.0949 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2c.0950 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2c.0951 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2c.0952 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
G2c.0953 | I | Number of Programme Overhead management lines | Number | O_OH1_M | SR21_Prog_Over | Baseline | G90 - Delivery Approval | 16 | 17 | 17 | 17 | 17 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0954 | I | [5 empty] | SOS - Start On Site | 11 | 16 | 16 | 16 | 16 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0955 | I | [5 empty] | G100 - Acceptance | 0 | 7 | 7 | 7 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 18 | 20
G2c.0956 | I | [5 empty] | G110 - Financial Closure | 0 | 5 | 5 | 5 | 5 | 7 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 18 | 20
G2c.0957 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 16 | 17 | 17 | 17 | 17 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0958 | I | [5 empty] | SOS - Start On Site | 13 | 16 | 16 | 16 | 16 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
G2c.0959 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 18 | 20
G2c.0960 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 18 | 20
G2c.0961 | I | Number of membranes replaced or maintained | Number | O_OM1_M1 | MA033, MA094 | Baseline | G90 - Delivery Approval | 60.7 | 61.7 | 61.7 | 63.7 | 143.7 | 144.7 | 161.7 | 184.7 | 219.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7
G2c.0962 | I | [5 empty] | SOS - Start On Site | 58.7 | 60.7 | 60.7 | 62.7 | 74.7 | 143.7 | 160.7 | 183.7 | 214.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7
G2c.0963 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 54.7 | 54.7 | 56.7 | 74.7 | 74.7 | 92.7 | 115.7 | 146.7 | 150.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7
G2c.0964 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 5 | 54.7 | 56.7 | 68.7 | 68.7 | 85.7 | 115.7 | 146.7 | 146.7 | 146.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7 | 218.7
G2c.0965 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 60.7 | 61.7 | 61.7 | 63.7 | 143.7 | 144.7 | 161.7 | 184.7 | 219.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 220.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7
G2c.0966 | I | [5 empty] | SOS - Start On Site | 58.7 | 60.7 | 60.7 | 62.7 | 74.7 | 143.7 | 160.7 | 183.7 | 214.7 | 219.7 | 219.7 | 219.7 | 219.7 | 219.7 | 219.7 | 219.7 | 219.7 | 220.7 | 220.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7 | 222.7
G2c.0967 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 4 | 7 | 14 | 16 | 78.7 | 92.7 | 139.7 | 146.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 152.7 | 220.7 | 220.7 | 220.7 | 221.7 | 222.7 | 222.7 | 222.7
G2c.0968 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 3 | 7 | 13 | 15 | 28 | 92.7 | 139.7 | 140.7 | 147.7 | 147.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 151.7 | 220.7 | 220.7 | 220.7 | 220.7 | 222.7 | 222.7
G2c.0969 | I | Number of WTW sand filters with media replaced | Number | O_OM1_M2 | MA033, MA094 | Baseline | G90 - Delivery Approval | 32 | 32 | 46 | 53 | 61 | 61 | 100 | 112 | 155 | 157 | 165 | 165 | 166 | 166 | 167 | 167 | 167 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 174
G2c.0970 | I | [5 empty] | SOS - Start On Site | 30 | 30 | 36 | 38 | 40 | 54 | 54 | 92 | 138 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147 | 147
G2c.0971 | I | [5 empty] | G100 - Acceptance | 6 | 10 | 20 | 26 | 27 | 27 | 39 | 44 | 54 | 54 | 54 | 54 | 66 | 104 | 104 | 104 | 104 | 104 | 138 | 138 | 138 | 138 | 138 | 147 | 147 | 147
G2c.0972 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 5 | 25 | 26 | 27 | 28 | 28 | 31 | 37 | 54 | 54 | 54 | 54 | 104 | 104 | 104 | 104 | 104 | 104 | 138 | 138 | 138 | 138 | 147 | 147
G2c.0973 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 32 | 32 | 46 | 53 | 61 | 61 | 100 | 112 | 155 | 157 | 165 | 165 | 166 | 166 | 167 | 167 | 167 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 174
G2c.0974 | I | [5 empty] | SOS - Start On Site | 30 | 30 | 38 | 40 | 53 | 55 | 56 | 96 | 130 | 153 | 158 | 165 | 165 | 166 | 166 | 167 | 167 | 167 | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 174
G2c.0975 | I | [5 empty] | G100 - Acceptance | 6 | 7 | 12 | 22 | 34 | 35 | 47 | 48 | 49 | 52 | 58 | 59 | 75 | 114 | 114 | 114 | 114 | 115 | 150 | 151 | 151 | 159 | 159 | 168 | 168 | 174
G2c.0976 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 8 | 28 | 28 | 31 | 32 | 48 | 51 | 51 | 52 | 59 | 59 | 113 | 114 | 114 | 114 | 115 | 115 | 150 | 151 | 159 | 159 | 168 | 174
G2c.0977 | I | Number of WTW Granular Activated Carbon (GAC) filters with media replaced | Number | O_OM1_M3 | MA033 | Baseline | G90 - Delivery Approval | 53 | 53 | 80 | 80 | 80 | 80 | 80 | 80 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0978 | I | [5 empty] | SOS - Start On Site | 53 | 53 | 80 | 80 | 80 | 80 | 80 | 80 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0979 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 53 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0980 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 52 | 52 | 53 | 53 | 53 | 54 | 54 | 54 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0981 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 53 | 53 | 80 | 80 | 80 | 80 | 80 | 80 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0982 | I | [5 empty] | SOS - Start On Site | 53 | 53 | 80 | 80 | 80 | 80 | 80 | 80 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0983 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 81 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0984 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 52 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 81 | 81 | 81 | 81 | 81 | 81 | 81
G2c.0985 | I | Number of WTW chemical storage and dosing interventions | Number | O_OM1_M4 | MA025, MA033, MA046 | Baseline | G90 - Delivery Approval | 816 | 963 | 1016 | 1058 | 1528 | 1548 | 1564 | 1584 | 1611 | 1627 | 1655 | 1674 | 1689 | 1711 | 1733 | 1734 | 1746 | 1759 | 1759 | 1759 | 1763 | 1764 | 1764 | 1765 | 1766 | 1767
G2c.0986 | I | [5 empty] | SOS - Start On Site | 777 | 825 | 871 | 1038 | 1429 | 1448 | 1470 | 1490 | 1510 | 1515 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516
G2c.0987 | I | [5 empty] | G100 - Acceptance | 677 | 708 | 750 | 790 | 840 | 1092 | 1129 | 1147 | 1172 | 1209 | 1511 | 1514 | 1515 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516
G2c.0988 | I | [5 empty] | G110 - Financial Closure | 677 | 707 | 742 | 782 | 825 | 927 | 1050 | 1127 | 1153 | 1189 | 1206 | 1508 | 1512 | 1515 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516 | 1516
G2c.0989 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 816 | 963 | 1016 | 1058 | 1528 | 1548 | 1564 | 1584 | 1611 | 1627 | 1655 | 1674 | 1689 | 1711 | 1733 | 1734 | 1746 | 1759 | 1759 | 1759 | 1763 | 1764 | 1764 | 1765 | 1766 | 1767
G2c.0990 | I | [5 empty] | SOS - Start On Site | 783 | 824 | 977 | 1037 | 1507 | 1528 | 1543 | 1565 | 1588 | 1603 | 1618 | 1644 | 1658 | 1676 | 1714 | 1725 | 1726 | 1747 | 1759 | 1759 | 1759 | 1763 | 1764 | 1764 | 1765 | 1767
G2c.0991 | I | [5 empty] | G100 - Acceptance | 0 | 13 | 57 | 86 | 853 | 1011 | 1050 | 1079 | 1108 | 1249 | 1571 | 1594 | 1610 | 1622 | 1633 | 1668 | 1671 | 1679 | 1715 | 1723 | 1734 | 1749 | 1751 | 1756 | 1756 | 1767
G2c.0992 | I | [5 empty] | G110 - Financial Closure | 0 | 12 | 50 | 82 | 806 | 902 | 940 | 1071 | 1095 | 1232 | 1245 | 1557 | 1573 | 1606 | 1615 | 1621 | 1643 | 1668 | 1673 | 1683 | 1716 | 1722 | 1746 | 1751 | 1755 | 1767
G2c.0993 | I | Number of Filtration and disinfection asset interventions | Number | O_OM1_M5 | MA033, MA093, MA094 | Baseline | G90 - Delivery Approval | 200 | 275 | 365 | 519 | 781 | 811 | 951 | 1156 | 1337 | 1347 | 1348 | 1349 | 1350 | 1351 | 1351 | 1351 | 1355 | 1360 | 1361 | 1361 | 1361 | 1361 | 1361 | 1361 | 1361 | 1369
G2c.0994 | I | [5 empty] | SOS - Start On Site | 173 | 247 | 329 | 480 | 739 | 784 | 939 | 1144 | 1324 | 1326 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327
G2c.0995 | I | [5 empty] | G100 - Acceptance | 0 | 160 | 236 | 340 | 487 | 740 | 783 | 943 | 1146 | 1324 | 1325 | 1325 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327
G2c.0996 | I | [5 empty] | G110 - Financial Closure | 0 | 160 | 236 | 337 | 483 | 733 | 766 | 923 | 1122 | 1305 | 1313 | 1324 | 1325 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327
G2c.0997 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 200 | 275 | 365 | 519 | 781 | 811 | 951 | 1156 | 1337 | 1347 | 1348 | 1349 | 1350 | 1351 | 1351 | 1351 | 1355 | 1360 | 1361 | 1361 | 1361 | 1361 | 1361 | 1361 | 1361 | 1369
G2c.0998 | I | [5 empty] | SOS - Start On Site | 175 | 249 | 335 | 488 | 754 | 786 | 927 | 1130 | 1328 | 1341 | 1344 | 1346 | 1346 | 1349 | 1349 | 1349 | 1349 | 1359 | 1360 | 1361 | 1361 | 1361 | 1361 | 1361 | 1361 | 1369
G2c.0999 | I | [5 empty] | G100 - Acceptance | 0 | 33 | 92 | 146 | 209 | 393 | 477 | 618 | 864 | 1305 | 1317 | 1336 | 1343 | 1345 | 1347 | 1347 | 1349 | 1349 | 1350 | 1352 | 1356 | 1357 | 1357 | 1360 | 1360 | 1369
G2c.1000 | I | [5 empty] | G110 - Financial Closure | 0 | 33 | 92 | 144 | 204 | 391 | 471 | 613 | 752 | 1288 | 1301 | 1314 | 1325 | 1338 | 1343 | 1345 | 1347 | 1347 | 1349 | 1349 | 1350 | 1352 | 1356 | 1357 | 1357 | 1369
G2c.1001 | I | Number of WTW instrumentation interventions | Number | O_OM1_M6 | MA095 | Baseline | G90 - Delivery Approval | 60 | 87 | 201 | 216 | 242 | 250 | 254 | 257 | 264 | 282 | 325 | 337 | 344 | 344 | 348 | 348 | 349 | 351 | 351 | 363 | 363 | 364 | 364 | 364 | 375 | 426
G2c.1002 | I | [5 empty] | SOS - Start On Site | 31 | 58 | 185 | 201 | 215 | 223 | 225 | 229 | 229 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 239 | 239 | 239 | 239 | 239 | 239 | 239 | 239 | 239 | 239
G2c.1003 | I | [5 empty] | G100 - Acceptance | 0 | 28 | 58 | 172 | 200 | 211 | 220 | 224 | 228 | 229 | 229 | 229 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 239 | 239 | 239 | 239 | 239 | 239
G2c.1004 | I | [5 empty] | G110 - Financial Closure | 0 | 28 | 56 | 170 | 187 | 207 | 214 | 219 | 223 | 227 | 227 | 228 | 229 | 230 | 238 | 238 | 238 | 238 | 238 | 238 | 238 | 239 | 239 | 239 | 239 | 239
G2c.1005 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 60 | 87 | 201 | 216 | 242 | 250 | 254 | 257 | 264 | 282 | 325 | 337 | 344 | 344 | 348 | 348 | 349 | 351 | 351 | 363 | 363 | 364 | 364 | 364 | 375 | 426
G2c.1006 | I | [5 empty] | SOS - Start On Site | 36 | 66 | 185 | 200 | 229 | 237 | 238 | 243 | 247 | 262 | 274 | 325 | 337 | 344 | 344 | 348 | 348 | 349 | 351 | 351 | 363 | 363 | 364 | 364 | 364 | 426
G2c.1007 | I | [5 empty] | G100 - Acceptance | 0 | 10 | 26 | 149 | 181 | 205 | 213 | 215 | 219 | 241 | 244 | 252 | 294 | 316 | 320 | 320 | 326 | 334 | 345 | 349 | 349 | 351 | 351 | 351 | 363 | 426
G2c.1008 | I | [5 empty] | G110 - Financial Closure | 0 | 10 | 23 | 146 | 180 | 203 | 211 | 214 | 216 | 240 | 240 | 242 | 243 | 253 | 305 | 309 | 320 | 320 | 328 | 334 | 348 | 349 | 351 | 351 | 351 | 426
G2c.1009 | I | Number of catchments managed to protect and improve water quality | Number | O_OM10_M | MA096 | Baseline | G90 - Delivery Approval | 6 | 7 | 9 | 9 | 10 | 10 | 38 | 39 | 44 | 45 | 45 | 47 | 47 | 47 | 49 | 49 | 50 | 53 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54
G2c.1010 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.1011 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.1012 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
G2c.1013 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 6 | 7 | 9 | 9 | 10 | 10 | 38 | 39 | 44 | 45 | 45 | 47 | 47 | 47 | 49 | 49 | 50 | 53 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54
G2c.1014 | I | [5 empty] | SOS - Start On Site | 0 | 1 | 2 | 2 | 3 | 4 | 5 | 35 | 39 | 42 | 45 | 46 | 46 | 47 | 49 | 49 | 49 | 49 | 53 | 53 | 53 | 53 | 53 | 53 | 54 | 54
G2c.1015 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 10 | 12 | 16 | 17 | 18 | 18 | 19 | 21 | 21 | 49 | 49 | 49 | 51 | 52 | 52 | 53 | 54
G2c.1016 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 12 | 13 | 17 | 17 | 18 | 19 | 21 | 21 | 21 | 49 | 49 | 51 | 52 | 52 | 54
G2c.1017 | I | Number of treated water storage or secondary disinfection asssets replaced or maintained | Number | O_OM2_M | MA025, MA037, MA081, MA106 | Baseline | G90 - Delivery Approval | 182 | 190 | 191 | 194 | 194 | 194 | 198 | 283 | 392 | 403 | 403 | 405 | 406 | 408 | 410 | 410 | 411 | 413 | 413 | 414 | 414 | 414 | 414 | 414 | 414 | 414
G2c.1018 | I | [5 empty] | SOS - Start On Site | 151 | 179 | 189 | 192 | 192 | 192 | 194 | 281 | 386 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389
G2c.1019 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 6 | 18 | 164 | 164 | 165 | 287 | 387 | 387 | 388 | 388 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389
G2c.1020 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 2 | 8 | 17 | 19 | 165 | 258 | 357 | 386 | 387 | 388 | 388 | 388 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389 | 389
G2c.1021 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 182 | 190 | 191 | 194 | 194 | 194 | 198 | 283 | 392 | 403 | 403 | 405 | 406 | 408 | 410 | 410 | 411 | 413 | 413 | 414 | 414 | 414 | 414 | 414 | 414 | 414
G2c.1022 | I | [5 empty] | SOS - Start On Site | 152 | 188 | 189 | 194 | 194 | 194 | 196 | 282 | 388 | 401 | 403 | 403 | 405 | 408 | 409 | 410 | 411 | 411 | 413 | 413 | 414 | 414 | 414 | 414 | 414 | 414
G2c.1023 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 15 | 111 | 247 | 255 | 258 | 259 | 259 | 404 | 404 | 404 | 408 | 409 | 410 | 411 | 413 | 413 | 413 | 414 | 414
G2c.1024 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 71 | 244 | 254 | 254 | 257 | 258 | 258 | 260 | 404 | 404 | 407 | 408 | 408 | 410 | 412 | 413 | 413 | 414
G2c.1025 | I | Number of treated water storage asset interventions | Number | O_OM2_M1 | MA037, MA046, MA095, MA106 | Baseline | G90 - Delivery Approval | 231 | 384 | 425 | 433 | 456 | 458 | 810 | 1006 | 1009 | 1011 | 1014 | 1016 | 1017 | 1025 | 1025 | 1025 | 1027 | 1028 | 1032 | 1034 | 1035 | 1036 | 1036 | 1036 | 1036 | 1040
G2c.1026 | I | [5 empty] | SOS - Start On Site | 139 | 285 | 313 | 330 | 360 | 368 | 552 | 903 | 914 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 915 | 917
G2c.1027 | I | [5 empty] | G100 - Acceptance | 0 | 82 | 107 | 139 | 194 | 253 | 262 | 351 | 472 | 473 | 485 | 485 | 581 | 738 | 745 | 746 | 746 | 771 | 771 | 915 | 915 | 915 | 915 | 915 | 915 | 917
G2c.1028 | I | [5 empty] | G110 - Financial Closure | 0 | 55 | 98 | 133 | 144 | 204 | 240 | 317 | 366 | 436 | 471 | 484 | 484 | 581 | 738 | 738 | 745 | 745 | 771 | 771 | 915 | 915 | 915 | 915 | 915 | 917
G2c.1029 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 231 | 384 | 425 | 433 | 456 | 458 | 810 | 1006 | 1009 | 1011 | 1014 | 1016 | 1017 | 1025 | 1025 | 1025 | 1027 | 1028 | 1032 | 1034 | 1035 | 1036 | 1036 | 1036 | 1036 | 1040
G2c.1030 | I | [5 empty] | SOS - Start On Site | 209 | 363 | 393 | 405 | 436 | 440 | 626 | 994 | 1005 | 1008 | 1010 | 1014 | 1015 | 1021 | 1024 | 1024 | 1025 | 1028 | 1028 | 1032 | 1034 | 1035 | 1036 | 1036 | 1036 | 1040
G2c.1031 | I | [5 empty] | G100 - Acceptance | 0 | 16 | 67 | 93 | 167 | 206 | 239 | 291 | 360 | 423 | 426 | 429 | 481 | 685 | 747 | 747 | 751 | 871 | 879 | 1026 | 1027 | 1027 | 1028 | 1029 | 1030 | 1040
G2c.1032 | I | [5 empty] | G110 - Financial Closure | 0 | 9 | 25 | 45 | 100 | 144 | 189 | 243 | 349 | 414 | 422 | 426 | 443 | 573 | 670 | 714 | 736 | 739 | 779 | 878 | 1024 | 1025 | 1026 | 1028 | 1028 | 1040
G2c.1033 | I | Number of sample point interventions | Number | O_OM2_M2 | MA081, MA092 | Baseline | G90 - Delivery Approval | 175 | 179 | 224 | 345 | 503 | 578 | 586 | 586 | 586 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588
G2c.1034 | I | [5 empty] | SOS - Start On Site | 77 | 79 | 124 | 124 | 124 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477 | 477
G2c.1035 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 18 | 22 | 22 | 84 | 84 | 84 | 124 | 185 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 477
G2c.1036 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 6 | 22 | 22 | 22 | 84 | 84 | 84 | 84 | 124 | 185 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 343 | 477
G2c.1037 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 175 | 179 | 224 | 345 | 503 | 578 | 586 | 586 | 586 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588
G2c.1038 | I | [5 empty] | SOS - Start On Site | 150 | 178 | 223 | 224 | 225 | 578 | 586 | 586 | 586 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588
G2c.1039 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 3 | 8 | 12 | 12 | 82 | 122 | 147 | 149 | 236 | 514 | 514 | 514 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588
G2c.1040 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 8 | 12 | 12 | 20 | 20 | 60 | 149 | 149 | 149 | 356 | 514 | 514 | 514 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 587 | 588
G2c.1041 | I | Number of secondary disinfection asset interventions | Number | O_OM2_M3 | MA037, MA106 | Baseline | G90 - Delivery Approval | 0 | 0 | 2 | 6 | 20 | 21 | 21 | 24 | 26 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1042 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 6 | 20 | 20 | 20 | 23 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1043 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 6 | 20 | 20 | 20 | 24 | 24 | 24 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1044 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 6 | 20 | 20 | 20 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1045 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 2 | 6 | 20 | 21 | 21 | 24 | 26 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1046 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 2 | 6 | 20 | 21 | 21 | 24 | 25 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1047 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 13 | 25 | 25 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1048 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 10 | 13 | 25 | 25 | 25 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1049 | I | Number of WTW sites made compliant with standards | Number | O_OM3_E | MA100 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 148 | 148 | 148 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149
G2c.1050 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.1051 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.1052 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.1053 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 148 | 148 | 148 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149
G2c.1054 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 86 | 86 | 86 | 86 | 148 | 148 | 148 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149 | 149
G2c.1055 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 148 | 148 | 148 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149 | 149
G2c.1056 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 148 | 148 | 149 | 149 | 149 | 149 | 149 | 149
G2c.1057 | I | Numberof treated water storage operability (by-pass) interventions | Number | O_OM6_E | MA037 | Baseline | G90 - Delivery Approval | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 59 | 59 | 60 | 61 | 61 | 62 | 64 | 65 | 65 | 67 | 68 | 69 | 70 | 70 | 71 | 71 | 72 | 72
G2c.1058 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 40 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1059 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 22 | 57 | 57 | 57 | 57
G2c.1060 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 22 | 57 | 57 | 57 | 57
G2c.1061 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 59 | 59 | 60 | 61 | 61 | 62 | 64 | 65 | 65 | 67 | 68 | 69 | 70 | 70 | 71 | 71 | 72 | 72
G2c.1062 | I | [5 empty] | SOS - Start On Site | 1 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 41 | 42 | 42 | 60 | 61 | 62 | 63 | 64 | 65 | 65 | 67 | 69 | 69 | 70 | 70 | 71 | 71 | 72
G2c.1063 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 10 | 11 | 12 | 12 | 13 | 30 | 68 | 69 | 70 | 72
G2c.1064 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 11 | 11 | 12 | 30 | 30 | 66 | 70 | 72
G2c.1065 | I | Number of treated water storage by-pass interventions | Number | O_OM6_M | MA037 | Baseline | G90 - Delivery Approval | 95 | 102 | 108 | 109 | 109 | 109 | 109 | 110 | 143 | 149 | 156 | 158 | 158 | 159 | 162 | 163 | 164 | 166 | 167 | 168 | 170 | 170 | 171 | 171 | 172 | 187
G2c.1066 | I | [5 empty] | SOS - Start On Site | 74 | 74 | 84 | 88 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
G2c.1067 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 7 | 10 | 24 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
G2c.1068 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 3 | 4 | 6 | 10 | 21 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
G2c.1069 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 95 | 102 | 108 | 109 | 109 | 109 | 109 | 110 | 143 | 149 | 156 | 158 | 158 | 159 | 162 | 163 | 164 | 166 | 167 | 168 | 170 | 170 | 171 | 171 | 172 | 187
G2c.1070 | I | [5 empty] | SOS - Start On Site | 86 | 90 | 97 | 103 | 106 | 109 | 109 | 109 | 127 | 132 | 135 | 155 | 157 | 158 | 160 | 161 | 162 | 163 | 165 | 167 | 167 | 169 | 169 | 170 | 170 | 187
G2c.1071 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 9 | 15 | 22 | 24 | 26 | 34 | 106 | 115 | 115 | 115 | 115 | 117 | 117 | 120 | 121 | 123 | 123 | 124 | 139 | 159 | 166 | 167 | 187
G2c.1072 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 5 | 6 | 8 | 9 | 10 | 19 | 97 | 106 | 107 | 110 | 114 | 114 | 115 | 117 | 117 | 121 | 122 | 123 | 138 | 138 | 156 | 160 | 187
G2c.1073 | I | Number ATOM water asset interventions | Number | O_OM9_M | MA068 | Baseline | G90 - Delivery Approval | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1074 | I | [5 empty] | SOS - Start On Site | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1075 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1076 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1077 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1078 | I | [5 empty] | SOS - Start On Site | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1079 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1080 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1081 | I | Number of property asset interventions | Number | O_PE1_M | MA029, MA096 | Baseline | G90 - Delivery Approval | 119 | 359 | 362 | 362 | 367 | 367 | 367 | 367 | 367 | 368 | 375 | 376 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 379 | 379 | 379 | 379 | 379 | 379 | 379
G2c.1082 | I | [5 empty] | SOS - Start On Site | 114 | 354 | 356 | 357 | 360 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1083 | I | [5 empty] | G100 - Acceptance | 0 | 112 | 113 | 114 | 114 | 360 | 360 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1084 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 112 | 113 | 114 | 117 | 358 | 360 | 360 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1085 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 119 | 359 | 362 | 362 | 367 | 367 | 367 | 367 | 367 | 368 | 375 | 376 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 379 | 379 | 379 | 379 | 379 | 379 | 379
G2c.1086 | I | [5 empty] | SOS - Start On Site | 119 | 359 | 361 | 362 | 365 | 365 | 367 | 367 | 367 | 367 | 367 | 376 | 376 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 378 | 379 | 379 | 379 | 379 | 379
G2c.1087 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 114 | 116 | 118 | 121 | 122 | 122 | 123 | 123 | 125 | 127 | 127 | 135 | 376 | 377 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 379 | 379 | 379
G2c.1088 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 3 | 8 | 13 | 120 | 120 | 120 | 120 | 123 | 124 | 125 | 127 | 133 | 374 | 376 | 376 | 377 | 377 | 378 | 378 | 378 | 378 | 378 | 379
G2c.1089 | I | Revised Bathing Water Directive (proposed) | Number | O_pEC16 | MA049 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1090 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1091 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1092 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1093 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1094 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1095 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1096 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
G2c.1097 | I | Length of trunk mains replaced or maintained | Metres | O_SA1_M | MA001, MA025 | Baseline | G90 - Delivery Approval | 0 | 0 | 5100 | 5100 | 5200 | 5200 | 5200 | 17143 | 24865 | 24906.55 | 24906.55 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9
G2c.1098 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | 17142 | 17414 | 17464 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864
G2c.1099 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | 5472 | 5522 | 5522 | 5522 | 12922 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864
G2c.1100 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 372 | 5522 | 5522 | 5522 | 5522 | 12922 | 12922 | 12922 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864 | 24864
G2c.1101 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 5100 | 5100 | 5200 | 5200 | 5200 | 17143 | 24865 | 24906.55 | 24906.55 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9
G2c.1102 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 5100 | 5100 | 5100 | 17143 | 17143 | 17487 | 24906.55 | 24906.55 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.6 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9 | 24906.9
G2c.1103 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5200 | 5200 | 5222 | 5544 | 5545 | 5545 | 12945.05 | 24887.05 | 24887.05 | 24887.05 | 24887.05 | 24887.05 | 24906.6 | 24906.6 | 24906.6 | 24906.9 | 24906.9 | 24906.9
G2c.1104 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 5200 | 5200 | 5200 | 5544 | 5545 | 5545 | 5545 | 12945.05 | 12945.05 | 12945.05 | 24887.05 | 24887.05 | 24887.05 | 24906.6 | 24906.6 | 24906.9 | 24906.9
G2c.1105 | I | Length of trunk main interventions to address recurring customer interruptions to supply | Metres | O_SA1_M1 | MA001, MA025 | Baseline | G90 - Delivery Approval | 4992 | 4992 | 4992 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2c.1106 | I | [5 empty] | SOS - Start On Site | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992
G2c.1107 | I | [5 empty] | G100 - Acceptance | 0 | 1260 | 1260 | 1260 | 1260 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992
G2c.1108 | I | [5 empty] | G110 - Financial Closure | 0 | 370 | 370 | 370 | 1260 | 1260 | 1260 | 1260 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992
G2c.1109 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4992 | 4992 | 4992 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2c.1110 | I | [5 empty] | SOS - Start On Site | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2c.1111 | I | [5 empty] | G100 - Acceptance | 0 | 890 | 1260 | 1260 | 1260 | 1260 | 4992 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2c.1112 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1260 | 1260 | 1260 | 1260 | 1260 | 4992 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792 | 6792
G2c.1113 | I | Length of trunk main interventions | Metres | O_SA1_M2 | MA025 | Baseline | G90 - Delivery Approval | 101 | 101 | 514 | 14556 | 14764 | 14764 | 14765 | 53703 | 60376 | 60376 | 77078 | 77079 | 77079 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79630
G2c.1114 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 261 | 261 | 265 | 267 | 272 | 274 | 34112 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212
G2c.1115 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 161 | 261 | 264 | 265 | 268 | 271 | 274 | 9112 | 9112 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212
G2c.1116 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 161 | 161 | 264 | 264 | 265 | 266 | 271 | 273 | 9111 | 9112 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212 | 39212
G2c.1117 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 101 | 101 | 514 | 14556 | 14764 | 14764 | 14765 | 53703 | 60376 | 60376 | 77078 | 77079 | 77079 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79630
G2c.1118 | I | [5 empty] | SOS - Start On Site | 1 | 101 | 511 | 14552 | 14757 | 14758 | 14759 | 14762 | 44863 | 45136 | 68239 | 77077 | 77078 | 77139 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79630
G2c.1119 | I | [5 empty] | G100 - Acceptance | 0 | 100 | 100 | 260 | 14550 | 14750 | 14751 | 14752 | 14753 | 14756 | 14758 | 15033 | 31735 | 65577 | 77078 | 77079 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79629 | 79629 | 79630
G2c.1120 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 100 | 260 | 14550 | 14750 | 14751 | 14752 | 14752 | 14755 | 14756 | 14757 | 15031 | 15033 | 56736 | 70677 | 77079 | 77139 | 77139 | 77139 | 77139 | 79629 | 79629 | 79629 | 79629 | 79630
G2c.1121 | I | Number of water demand management interventions | Number | O_SA10_M | MA099 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 101 | 101 | 101 | 102 | 102 | 103 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
G2c.1122 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
G2c.1123 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
G2c.1124 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
G2c.1125 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 101 | 101 | 101 | 102 | 102 | 103 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
G2c.1126 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 101 | 101 | 101 | 102 | 102 | 102 | 103 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
G2c.1127 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 103 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
G2c.1128 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 104 | 104
G2c.1129 | I | Number of plans to improve customer experience | Number | O_SA12_E | MA001 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1130 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1131 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1132 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1133 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1134 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1135 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1136 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1137 | I | Number of raw water intake interventions | Number | O_SA2_M | MA025 | Baseline | G90 - Delivery Approval | 4 | 8 | 12 | 15 | 20 | 20 | 319 | 321 | 333 | 336 | 343 | 346 | 346 | 349 | 349 | 349 | 349 | 351 | 352 | 352 | 352 | 352 | 352 | 352 | 352 | 353
G2c.1138 | I | [5 empty] | SOS - Start On Site | 2 | 3 | 6 | 6 | 10 | 16 | 21 | 321 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331
G2c.1139 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 5 | 7 | 9 | 9 | 16 | 22 | 34 | 34 | 34 | 34 | 34 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331
G2c.1140 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 5 | 6 | 9 | 9 | 12 | 16 | 29 | 33 | 33 | 34 | 34 | 34 | 34 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331
G2c.1141 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 8 | 12 | 15 | 20 | 20 | 319 | 321 | 333 | 336 | 343 | 346 | 346 | 349 | 349 | 349 | 349 | 351 | 352 | 352 | 352 | 352 | 352 | 352 | 352 | 353
G2c.1142 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 7 | 7 | 11 | 14 | 16 | 316 | 326 | 327 | 340 | 342 | 344 | 345 | 348 | 348 | 348 | 350 | 351 | 352 | 352 | 352 | 352 | 352 | 352 | 353
G2c.1143 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 6 | 7 | 9 | 10 | 11 | 14 | 27 | 27 | 31 | 38 | 45 | 342 | 345 | 348 | 348 | 348 | 349 | 350 | 350 | 351 | 352 | 352 | 353
G2c.1144 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 4 | 6 | 6 | 9 | 10 | 14 | 27 | 27 | 27 | 30 | 35 | 42 | 45 | 342 | 344 | 345 | 348 | 349 | 350 | 350 | 351 | 352 | 353
G2c.1145 | I | Number of treated water pump interventions | Number | O_SA3_M1 | MA015, MA058 | Baseline | G90 - Delivery Approval | 162 | 180 | 200 | 214 | 241 | 242 | 252 | 281 | 305 | 308 | 310 | 310 | 314 | 315 | 315 | 321 | 321 | 352 | 352 | 352 | 352 | 353 | 353 | 353 | 353 | 356
G2c.1146 | I | [5 empty] | SOS - Start On Site | 40 | 57 | 150 | 161 | 173 | 179 | 205 | 231 | 257 | 259 | 259 | 259 | 259 | 259 | 259 | 259 | 259 | 259 | 260 | 260 | 260 | 260 | 260 | 260 | 260 | 260
G2c.1147 | I | [5 empty] | G100 - Acceptance | 0 | 16 | 35 | 51 | 148 | 161 | 170 | 180 | 206 | 235 | 237 | 242 | 243 | 243 | 243 | 258 | 258 | 258 | 258 | 258 | 258 | 259 | 259 | 259 | 259 | 260
G2c.1148 | I | [5 empty] | G110 - Financial Closure | 0 | 16 | 32 | 48 | 60 | 148 | 150 | 172 | 197 | 229 | 232 | 235 | 235 | 238 | 243 | 243 | 243 | 243 | 258 | 258 | 258 | 258 | 259 | 259 | 259 | 260
G2c.1149 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 162 | 180 | 200 | 214 | 241 | 242 | 252 | 281 | 305 | 308 | 310 | 310 | 314 | 315 | 315 | 321 | 321 | 352 | 352 | 352 | 352 | 353 | 353 | 353 | 353 | 356
G2c.1150 | I | [5 empty] | SOS - Start On Site | 81 | 100 | 120 | 131 | 143 | 144 | 173 | 198 | 225 | 228 | 231 | 233 | 308 | 314 | 315 | 315 | 321 | 352 | 352 | 352 | 352 | 352 | 353 | 353 | 353 | 356
G2c.1151 | I | [5 empty] | G100 - Acceptance | 0 | 9 | 22 | 32 | 45 | 55 | 61 | 74 | 130 | 182 | 185 | 190 | 193 | 202 | 307 | 311 | 314 | 314 | 314 | 315 | 321 | 321 | 321 | 321 | 321 | 356
G2c.1152 | I | [5 empty] | G110 - Financial Closure | 0 | 8 | 19 | 28 | 41 | 52 | 57 | 72 | 90 | 178 | 180 | 183 | 186 | 193 | 195 | 214 | 222 | 308 | 314 | 314 | 314 | 321 | 321 | 321 | 321 | 356
G2c.1153 | I | Number of raw water pump interventions | Number | O_SA3_M2 | MA058, MA096 | Baseline | G90 - Delivery Approval | 15 | 15 | 20 | 23 | 28 | 29 | 32 | 36 | 48 | 48 | 48 | 49 | 50 | 50 | 50 | 50 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53
G2c.1154 | I | [5 empty] | SOS - Start On Site | 14 | 15 | 20 | 22 | 27 | 27 | 30 | 35 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
G2c.1155 | I | [5 empty] | G100 - Acceptance | 0 | 14 | 14 | 19 | 22 | 27 | 27 | 30 | 34 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
G2c.1156 | I | [5 empty] | G110 - Financial Closure | 0 | 11 | 11 | 15 | 21 | 27 | 27 | 30 | 34 | 45 | 45 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
G2c.1157 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 15 | 15 | 20 | 23 | 28 | 29 | 32 | 36 | 48 | 48 | 48 | 49 | 50 | 50 | 50 | 50 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53
G2c.1158 | I | [5 empty] | SOS - Start On Site | 14 | 15 | 20 | 23 | 28 | 28 | 31 | 35 | 47 | 48 | 48 | 49 | 49 | 50 | 50 | 50 | 50 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53
G2c.1159 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 8 | 12 | 17 | 20 | 23 | 27 | 33 | 46 | 46 | 46 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 52 | 53
G2c.1160 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 8 | 12 | 16 | 17 | 19 | 23 | 32 | 45 | 46 | 46 | 46 | 48 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 53
G2c.1161 | I | Length of raw water mains interventions | Metres | O_SA4_M | MA025 | Baseline | G90 - Delivery Approval | 2 | 4300 | 4409 | 4410 | 4410 | 4411 | 4762 | 9008 | 9008 | 9018 | 9018 | 9028 | 9028 | 9029 | 9029 | 9029 | 9029 | 9034 | 9035 | 9035 | 9035 | 9035 | 9035 | 9035 | 9035 | 9036
G2c.1162 | I | [5 empty] | SOS - Start On Site | 0 | 382 | 4342 | 4342 | 4342 | 4343 | 4345 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346
G2c.1163 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 421 | 424 | 425 | 425 | 426 | 4343 | 4343 | 4345 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346
G2c.1164 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 381 | 384 | 424 | 425 | 426 | 426 | 426 | 4343 | 4345 | 4345 | 4345 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346 | 4346
G2c.1165 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 4300 | 4409 | 4410 | 4410 | 4411 | 4762 | 9008 | 9008 | 9018 | 9018 | 9028 | 9028 | 9029 | 9029 | 9029 | 9029 | 9034 | 9035 | 9035 | 9035 | 9035 | 9035 | 9035 | 9035 | 9036
G2c.1166 | I | [5 empty] | SOS - Start On Site | 3917 | 4299 | 4408 | 4408 | 4408 | 4409 | 4759 | 9006 | 9007 | 9007 | 9017 | 9017 | 9027 | 9027 | 9028 | 9028 | 9028 | 9034 | 9034 | 9035 | 9035 | 9035 | 9035 | 9035 | 9035 | 9036
G2c.1167 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 41 | 395 | 491 | 492 | 842 | 842 | 4759 | 4759 | 4760 | 4761 | 4761 | 4771 | 4771 | 9027 | 9027 | 9028 | 9028 | 9034 | 9034 | 9034 | 9035 | 9035 | 9035 | 9036
G2c.1168 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 354 | 451 | 452 | 452 | 492 | 492 | 492 | 4409 | 4409 | 4410 | 4411 | 4411 | 4411 | 4431 | 4431 | 4431 | 8678 | 8679 | 8679 | 8684 | 8684 | 8685 | 9036
G2c.1169 | I | Length of aqueducts or tunnel interventions | Metres | O_SA5_M | MA025 | Baseline | G90 - Delivery Approval | 36200 | 36200 | 36250 | 36250 | 36251 | 42251 | 42327 | 43201 | 43202 | 45303 | 45304 | 45312 | 330312 | 358663 | 358664 | 358664 | 358664 | 358666 | 358666 | 358669 | 358669 | 358669 | 358669 | 358669 | 358669 | 358669
G2c.1170 | I | [5 empty] | SOS - Start On Site | 0 | 36200 | 36250 | 36250 | 36251 | 36251 | 42327 | 43197 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202
G2c.1171 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 50 | 36250 | 36250 | 36250 | 36251 | 41051 | 42251 | 43125 | 43126 | 43126 | 43126 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202
G2c.1172 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 50 | 50 | 50 | 36250 | 36250 | 36251 | 36251 | 36251 | 42251 | 43125 | 43126 | 43126 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202 | 43202
G2c.1173 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 36200 | 36200 | 36250 | 36250 | 36251 | 42251 | 42327 | 43201 | 43202 | 45303 | 45304 | 45312 | 330312 | 358663 | 358664 | 358664 | 358664 | 358666 | 358666 | 358669 | 358669 | 358669 | 358669 | 358669 | 358669 | 358669
G2c.1174 | I | [5 empty] | SOS - Start On Site | 0 | 36200 | 36250 | 36250 | 36251 | 36251 | 42327 | 42327 | 43202 | 45303 | 45303 | 45311 | 45311 | 330313 | 330664 | 330664 | 330664 | 358666 | 358666 | 358666 | 358669 | 358669 | 358669 | 358669 | 358669 | 358669
G2c.1175 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36200 | 36251 | 36251 | 43127 | 45227 | 45235 | 45311 | 45313 | 330313 | 330664 | 330664 | 330664 | 330666 | 330666 | 330666 | 330668 | 330668 | 358669
G2c.1176 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36250 | 36250 | 36250 | 36251 | 43127 | 45227 | 45303 | 45312 | 45313 | 330313 | 330664 | 330664 | 330666 | 330666 | 330666 | 330668 | 358669
G2c.1177 | I | Length of new or enhanced distribution mains | Metres | O_SA6_E | MA001, MA015, MA037, MA087 | Baseline | G90 - Delivery Approval | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2c.1178 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.1179 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.1180 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370 | 370
G2c.1181 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2c.1182 | I | [5 empty] | SOS - Start On Site | 1500 | 1500 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2c.1183 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2c.1184 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 370 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1870 | 1873.45 | 1873.45 | 1873.45 | 1873.45
G2c.1185 | I | Length of distribution mains interventions | Metres | O_SA6_M1 | MA001, MA015 | Baseline | G90 - Delivery Approval | 9542 | 10542 | 15578 | 15582 | 15637 | 37536 | 40640 | 40641 | 40962 | 41268 | 41868 | 43868 | 45068 | 45068 | 45068 | 45068 | 45068 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730 | 46730
G2c.1186 | I | [5 empty] | SOS - Start On Site | 8907 | 9307 | 9667 | 14921 | 15463 | 15514 | 15917 | 19019 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154 | 19154
G2c.1187 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 404 | 4034 | 4037 | 4417 | 15253 | 15767 | 15818 | 16037 | 16038 | 16039 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154
G2c.1188 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 404 | 514 | 3787 | 3791 | 9975 | 12960 | 15268 | 15818 | 15818 | 15938 | 16039 | 16039 | 16039 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154
G2c.1189 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9542 | 10542 | 15578 | 15582 | 15637 | 37536 | 40640 | 40641 | 40962 | 41268 | 41868 | 43868 | 45068 | 45068 | 45068 | 45068 | 45068 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730 | 46730
G2c.1190 | I | [5 empty] | SOS - Start On Site | 8915 | 9315 | 9675 | 12299 | 15535 | 15600 | 37512 | 40614 | 40934 | 41239 | 41366 | 41866 | 43866 | 45067 | 45067 | 45067 | 45067 | 45069 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730
G2c.1191 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 250 | 250 | 4034 | 7469 | 29070 | 37387 | 37654 | 40754 | 41051 | 41351 | 41852 | 41852 | 41852 | 43852 | 45052 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 45215 | 46730
G2c.1192 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 250 | 663 | 677 | 779 | 7123 | 15934 | 37534 | 40753 | 41024 | 41150 | 41651 | 41851 | 41852 | 43852 | 43852 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 46730
G2c.1193 | I | Length of distribution mains interventions | Number | O_SA6_M1 | MA001, MA015 | Baseline | G90 - Delivery Approval | 9542 | 10542 | 15578 | 15582 | 15637 | 37536 | 40640 | 40641 | 40962 | 41268 | 41868 | 43868 | 45068 | 45068 | 45068 | 45068 | 45068 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730 | 46730
G2c.1194 | I | [5 empty] | SOS - Start On Site | 8907 | 9307 | 9667 | 14921 | 15463 | 15514 | 15917 | 19019 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154 | 19154
G2c.1195 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 404 | 4034 | 4037 | 4417 | 15253 | 15767 | 15818 | 16037 | 16038 | 16039 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154
G2c.1196 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 404 | 514 | 3787 | 3791 | 9975 | 12960 | 15268 | 15818 | 15818 | 15938 | 16039 | 16039 | 16039 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19139 | 19154
G2c.1197 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 9542 | 10542 | 15578 | 15582 | 15637 | 37536 | 40640 | 40641 | 40962 | 41268 | 41868 | 43868 | 45068 | 45068 | 45068 | 45068 | 45068 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730 | 46730
G2c.1198 | I | [5 empty] | SOS - Start On Site | 8915 | 9315 | 9675 | 12299 | 15535 | 15600 | 37512 | 40614 | 40934 | 41239 | 41366 | 41866 | 43866 | 45067 | 45067 | 45067 | 45067 | 45069 | 45230 | 45230 | 45230 | 45230 | 46730 | 46730 | 46730 | 46730
G2c.1199 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 250 | 250 | 4034 | 7469 | 29070 | 37387 | 37654 | 40754 | 41051 | 41351 | 41852 | 41852 | 41852 | 43852 | 45052 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 45215 | 46730
G2c.1200 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 250 | 663 | 677 | 779 | 7123 | 15934 | 37534 | 40753 | 41024 | 41150 | 41651 | 41851 | 41852 | 43852 | 43852 | 45052 | 45053 | 45054 | 45215 | 45215 | 45215 | 46730
G2c.1201 | I | Length of distribution mains interventions to address recurring customer interruptions to supply | Metres | O_SA6_M2 | MA001, MA015, MA016, MA037, SR15 | Baseline | G90 - Delivery Approval | 112250 | 119633 | 147155 | 180918.18 | 237122.88 | 267295.88 | 281096.88 | 351061.18 | 372422.91 | 433564.91 | 509014.01 | 619749.01 | 727128.01 | 732692.01 | 732692.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01
G2c.1202 | I | [5 empty] | SOS - Start On Site | 98070 | 109435 | 118236 | 164188.48 | 184386.18 | 221773.88 | 267316.88 | 299942.88 | 358296.81 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91
G2c.1203 | I | [5 empty] | G100 - Acceptance | 0 | 35643 | 42131 | 68534 | 78640 | 100500 | 109712 | 134528.18 | 140208.18 | 156506.18 | 176565.18 | 209396.98 | 251657.98 | 302123.08 | 326887.08 | 345799.71 | 356334.71 | 356334.71 | 356334.71 | 356334.71 | 356334.71 | 365402.91 | 365402.91 | 365402.91 | 365402.91 | 365402.91
G2c.1204 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1738 | 32428 | 43165 | 60175 | 74622 | 88228 | 103691 | 114762 | 140787.48 | 146792.48 | 173250.58 | 178264.28 | 214162.98 | 251657.98 | 302123.08 | 326887.08 | 345799.71 | 356334.71 | 356334.71 | 356334.71 | 356334.71 | 356334.71 | 365402.91 | 365402.91
G2c.1205 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 112250 | 119633 | 147155 | 180918.18 | 237122.88 | 267295.88 | 281096.88 | 351061.18 | 372422.91 | 433564.91 | 509014.01 | 619749.01 | 727128.01 | 732692.01 | 732692.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01
G2c.1206 | I | [5 empty] | SOS - Start On Site | 107819 | 112035 | 121195 | 164580 | 185676.7 | 215897.7 | 274142.88 | 317044.88 | 368944.81 | 396594.91 | 492634.91 | 508262.91 | 631691.01 | 732691.01 | 732692.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 738773.01 | 743673.01 | 743673.01 | 743673.01 | 743673.01
G2c.1207 | I | [5 empty] | G100 - Acceptance | 0 | 21244 | 31136 | 60922 | 89127 | 91620 | 104741 | 115301 | 161137.88 | 194955.88 | 243085.88 | 264772.98 | 296956.98 | 358028.98 | 394306.08 | 421278.28 | 480447.28 | 620843.28 | 632756.28 | 667961.91 | 716276.91 | 738771.91 | 738773.01 | 738773.01 | 738773.01 | 743673.01
G2c.1208 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 3780 | 27573 | 61141 | 76388 | 83426 | 91725 | 137696.7 | 162211.7 | 175051.4 | 183335.88 | 238639.98 | 278820.98 | 297724.98 | 324001.98 | 373483.98 | 420899.28 | 497735.28 | 601398.28 | 613311.28 | 669250.91 | 716276.91 | 725578.01 | 725578.01 | 743673.01
G2c.1209 | I | Length of mains with pressure management intervention | Metres | O_SA6_M3 | MA015 | Baseline | G90 - Delivery Approval | 2 | 2 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1210 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1211 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1212 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1213 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1214 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 362 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1215 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1216 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1217 | I | Length of mains with pressure management intervention | Number | O_SA6_M3 | MA015 | Baseline | G90 - Delivery Approval | 2 | 2 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1218 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1219 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1220 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362 | 362
G2c.1221 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1222 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 362 | 363 | 363 | 363 | 363 | 363 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1223 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 363 | 363 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1224 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 362 | 362 | 362 | 362 | 362 | 362 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963 | 9963
G2c.1225 | I | Number of properties where persistent low pressure is resolved | Number | O_SA7_E | MA001, MA070 | Baseline | G90 - Delivery Approval | 1 | 10 | 113 | 113 | 130 | 130 | 133 | 133 | 153.4 | 154.4 | 156.4 | 156.4 | 156.4 | 171.4 | 171.4 | 171.4 | 171.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4
G2c.1226 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 3 | 10 | 113 | 113 | 117 | 133 | 133 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4 | 135.4
G2c.1227 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 2 | 8 | 8 | 112 | 115 | 115 | 132 | 132 | 132 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 135.4
G2c.1228 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 2 | 8 | 113 | 113 | 115 | 132 | 132 | 132 | 132 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 134.4 | 135.4
G2c.1229 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 10 | 113 | 113 | 130 | 130 | 133 | 133 | 153.4 | 154.4 | 156.4 | 156.4 | 156.4 | 171.4 | 171.4 | 171.4 | 171.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4
G2c.1230 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 103 | 110 | 113 | 114 | 117 | 117 | 151 | 154.4 | 156.4 | 156.4 | 156.4 | 171.4 | 171.4 | 171.4 | 171.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4 | 174.4
G2c.1231 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 7 | 8 | 11 | 11 | 12 | 16 | 16 | 35 | 37.4 | 38.4 | 56.4 | 62.4 | 70.4 | 70.4 | 70.4 | 70.4 | 73.4 | 73.4 | 73.4 | 73.4 | 73.4 | 174.4
G2c.1232 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 9 | 13 | 14 | 16 | 35 | 35 | 38.4 | 44.4 | 62.4 | 70.4 | 70.4 | 70.4 | 70.4 | 73.4 | 73.4 | 73.4 | 73.4 | 174.4
G2c.1233 | I | Number of borehole interventions | Number | O_SA8_M | MA080 | Baseline | G90 - Delivery Approval | 21 | 28 | 35 | 168 | 172 | 194 | 199 | 209 | 214 | 216 | 227 | 233 | 246 | 284 | 284 | 284 | 284 | 284 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.1234 | I | [5 empty] | SOS - Start On Site | 21 | 27 | 29 | 162 | 171 | 172 | 177 | 188 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193
G2c.1235 | I | [5 empty] | G100 - Acceptance | 0 | 12 | 17 | 32 | 37 | 44 | 168 | 175 | 179 | 192 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193
G2c.1236 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 17 | 20 | 26 | 41 | 41 | 46 | 176 | 189 | 191 | 191 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193 | 193
G2c.1237 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 21 | 28 | 35 | 168 | 172 | 194 | 199 | 209 | 214 | 216 | 227 | 233 | 246 | 284 | 284 | 284 | 284 | 284 | 291 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.1238 | I | [5 empty] | SOS - Start On Site | 21 | 28 | 30 | 165 | 172 | 193 | 198 | 209 | 214 | 216 | 218 | 228 | 233 | 246 | 284 | 284 | 284 | 284 | 284 | 291 | 291 | 291 | 291 | 291 | 291 | 291
G2c.1239 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 4 | 8 | 36 | 59 | 60 | 64 | 72 | 89 | 90 | 217 | 218 | 228 | 228 | 246 | 250 | 250 | 284 | 284 | 284 | 284 | 291 | 291 | 291 | 291
G2c.1240 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 6 | 23 | 46 | 51 | 63 | 68 | 80 | 86 | 89 | 92 | 217 | 228 | 228 | 241 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 291 | 291
G2c.1241 | I | Number of sub-sea main interventions | Number | O_SA9_M | MA025 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1242 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1243 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1244 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1245 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1246 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1247 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4
G2c.1248 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4
G2c.1249 | I | Number of scientific equipment instruments replaced | Number | O_SC1_M | MA053 | Baseline | G90 - Delivery Approval | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2c.1250 | I | [5 empty] | SOS - Start On Site | 0 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148
G2c.1251 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148
G2c.1252 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148 | 148
G2c.1253 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2c.1254 | I | [5 empty] | SOS - Start On Site | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2c.1255 | I | [5 empty] | G100 - Acceptance | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2c.1256 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 262
G2c.1257 | I | Number of sites assessed for renewable energy generation | Number | O_SE2_E2 | SR15 | Baseline | G90 - Delivery Approval | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1258 | I | [5 empty] | SOS - Start On Site | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1259 | I | [5 empty] | G100 - Acceptance | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1260 | I | [5 empty] | G110 - Financial Closure | 0 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1261 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1262 | I | [5 empty] | SOS - Start On Site | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1263 | I | [5 empty] | G100 - Acceptance | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1264 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
G2c.1265 | I | Length of critical sewers interventions | Metres | O_SN1_M1 | MA002, MA012, MA014 | Baseline | G90 - Delivery Approval | 46692 | 170367 | 171249 | 171259 | 171262 | 171266 | 171278 | 171417.01 | 171423.01 | 171425.01 | 171426.01 | 171856.01 | 174736.01 | 175114.05 | 178293.05 | 180593.05 | 180593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05
G2c.1266 | I | [5 empty] | SOS - Start On Site | 43523 | 44904 | 168571 | 168573 | 169135 | 169464 | 169469 | 169612 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622
G2c.1267 | I | [5 empty] | G100 - Acceptance | 0 | 500 | 6505 | 10586 | 44543 | 44910 | 95111 | 95113 | 169476 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622
G2c.1268 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 11 | 4041 | 5411 | 41478 | 44546 | 44924 | 94560 | 95249 | 169619 | 169621 | 169621 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622 | 169622
G2c.1269 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 46692 | 170367 | 171249 | 171259 | 171262 | 171266 | 171278 | 171417.01 | 171423.01 | 171425.01 | 171426.01 | 171856.01 | 174736.01 | 175114.05 | 178293.05 | 180593.05 | 180593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05
G2c.1270 | I | [5 empty] | SOS - Start On Site | 44326 | 46703 | 170371 | 170372 | 170933 | 170937 | 171266 | 171409.01 | 171420.01 | 171421.01 | 171424.01 | 171426.01 | 174451.01 | 174793.05 | 178012.05 | 178293.05 | 180593.05 | 180593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05
G2c.1271 | I | [5 empty] | G100 - Acceptance | 0 | 500 | 1309 | 1692 | 1694 | 2939 | 2943 | 55011.01 | 164577.01 | 171271.01 | 171404.01 | 171412.01 | 171425.01 | 171856.01 | 171856.01 | 171857.01 | 174452.01 | 174974.05 | 174975.05 | 175395.05 | 175395.05 | 177695.05 | 184593.05 | 184593.05 | 184593.05 | 184593.05
G2c.1272 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 6 | 13 | 514 | 514 | 518 | 2566.01 | 55707.01 | 89671.01 | 166969.01 | 170528.01 | 170529.01 | 170871.01 | 171304.01 | 171855.01 | 171856.01 | 171856.01 | 174631.01 | 174974.05 | 175115.05 | 175395.05 | 177695.05 | 184593.05 | 184593.05 | 184593.05
G2c.1273 | I | Number of Legacy sewage pumping stations improved to meet appropriate standard | Number | O_SN1_M10 | MA023 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1274 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1275 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1276 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1277 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1278 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1279 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3
G2c.1280 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3
G2c.1281 | I | Number of wastewater Network Motor Control Centre interventions | Number | O_SN1_M11 | MA011, MA023 | Baseline | G90 - Delivery Approval | 14 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20
G2c.1282 | I | [5 empty] | SOS - Start On Site | 14 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1283 | I | [5 empty] | G100 - Acceptance | 0 | 13 | 13 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1284 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 13 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.1285 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 14 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20
G2c.1286 | I | [5 empty] | SOS - Start On Site | 14 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20
G2c.1287 | I | [5 empty] | G100 - Acceptance | 0 | 6 | 6 | 13 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 20
G2c.1288 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 6 | 6 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20
G2c.1289 | I | Number of sites with wastewater pipebridge interventions | Number | O_SN1_M12 | MA003, MA014, MA062 | Baseline | G90 - Delivery Approval | 15 | 15 | 20 | 21 | 27 | 30 | 30 | 31 | 33 | 36 | 36 | 41 | 41 | 59 | 61 | 62 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63
G2c.1290 | I | [5 empty] | SOS - Start On Site | 5 | 6 | 16 | 16 | 20 | 24 | 28 | 28 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
G2c.1291 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 13 | 15 | 18 | 21 | 23 | 25 | 28 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
G2c.1292 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 3 | 3 | 3 | 5 | 7 | 11 | 22 | 25 | 25 | 27 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
G2c.1293 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 15 | 15 | 20 | 21 | 27 | 30 | 30 | 31 | 33 | 36 | 36 | 41 | 41 | 59 | 61 | 62 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63
G2c.1294 | I | [5 empty] | SOS - Start On Site | 5 | 6 | 16 | 16 | 23 | 24 | 25 | 27 | 29 | 33 | 34 | 34 | 40 | 44 | 58 | 61 | 62 | 62 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63
G2c.1295 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 10 | 17 | 18 | 20 | 23 | 26 | 28 | 28 | 32 | 33 | 33 | 35 | 41 | 41 | 46 | 58 | 61 | 62 | 62 | 63 | 63 | 63 | 63
G2c.1296 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 5 | 7 | 7 | 10 | 14 | 15 | 17 | 19 | 22 | 24 | 33 | 34 | 35 | 41 | 42 | 49 | 58 | 62 | 62 | 63 | 63 | 63
G2c.1297 | I | Number of screw pumps intervention | Number | O_SN1_M13 | MA023, MA036 | Baseline | G90 - Delivery Approval | 5 | 7 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1298 | I | [5 empty] | SOS - Start On Site | 1 | 6 | 8 | 8 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1299 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 4 | 4 | 8 | 8 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1300 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 4 | 4 | 5 | 5 | 8 | 9 | 9 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1301 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5 | 7 | 10 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1302 | I | [5 empty] | SOS - Start On Site | 2 | 7 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1303 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 3 | 5 | 5 | 5 | 8 | 11 | 11 | 11 | 11 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1304 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 5 | 5 | 9 | 10 | 11 | 11 | 12 | 12 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1305 | I | Number of sites with sewage pumping station interventions | Number | O_SN1_M14 | MA012, MA017, MA023, MA043, MA057, MA062 | Baseline | G90 - Delivery Approval | 441 | 580 | 679 | 756 | 900 | 902 | 994 | 1166 | 1362 | 1401 | 1411 | 1419 | 1421 | 1424 | 1426 | 1426 | 1426 | 1433 | 1433 | 1435 | 1435 | 1437 | 1439 | 1440 | 1442 | 1444
G2c.1306 | I | [5 empty] | SOS - Start On Site | 419 | 557 | 652 | 727 | 870 | 879 | 972 | 1147 | 1336 | 1341 | 1344 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345
G2c.1307 | I | [5 empty] | G100 - Acceptance | 0 | 204 | 350 | 455 | 530 | 867 | 870 | 968 | 1143 | 1331 | 1335 | 1339 | 1344 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345
G2c.1308 | I | [5 empty] | G110 - Financial Closure | 0 | 198 | 341 | 440 | 519 | 654 | 861 | 957 | 1133 | 1319 | 1323 | 1328 | 1332 | 1340 | 1342 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345 | 1345
G2c.1309 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 441 | 580 | 679 | 756 | 900 | 902 | 994 | 1166 | 1362 | 1401 | 1411 | 1419 | 1421 | 1424 | 1426 | 1426 | 1426 | 1433 | 1433 | 1435 | 1435 | 1437 | 1439 | 1440 | 1442 | 1444
G2c.1310 | I | [5 empty] | SOS - Start On Site | 429 | 569 | 665 | 740 | 884 | 892 | 981 | 1156 | 1348 | 1365 | 1398 | 1405 | 1413 | 1419 | 1424 | 1424 | 1424 | 1429 | 1432 | 1432 | 1435 | 1436 | 1437 | 1439 | 1440 | 1444
G2c.1311 | I | [5 empty] | G100 - Acceptance | 0 | 91 | 215 | 329 | 397 | 530 | 593 | 679 | 776 | 1129 | 1143 | 1162 | 1171 | 1176 | 1208 | 1215 | 1419 | 1422 | 1425 | 1429 | 1429 | 1430 | 1432 | 1433 | 1435 | 1444
G2c.1312 | I | [5 empty] | G110 - Financial Closure | 0 | 85 | 207 | 323 | 380 | 516 | 578 | 663 | 759 | 1111 | 1124 | 1145 | 1152 | 1160 | 1167 | 1178 | 1208 | 1217 | 1418 | 1423 | 1424 | 1429 | 1429 | 1432 | 1433 | 1444
G2c.1313 | I | Number of wastewater network models maintained | Number | O_SN1_M15 | MA054 | Baseline | G90 - Delivery Approval | 0 | 83 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1314 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 124 | 124 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1315 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 58 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1316 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1317 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 83 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1318 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 135 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
G2c.1319 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207
G2c.1320 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207
G2c.1321 | I | Number of storm tank interventions | Number | O_SN1_M16 | MA039, MA062 | Baseline | G90 - Delivery Approval | 1 | 5 | 7 | 8 | 13 | 13 | 15 | 19 | 28 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66 | 66 | 66 | 66 | 66
G2c.1322 | I | [5 empty] | SOS - Start On Site | 0 | 5 | 6 | 7 | 13 | 13 | 15 | 18 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1323 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 4 | 6 | 7 | 12 | 12 | 15 | 18 | 26 | 26 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1324 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 5 | 7 | 12 | 12 | 14 | 18 | 26 | 26 | 26 | 26 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1325 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 5 | 7 | 8 | 13 | 13 | 15 | 19 | 28 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66 | 66 | 66 | 66 | 66
G2c.1326 | I | [5 empty] | SOS - Start On Site | 0 | 5 | 7 | 8 | 13 | 13 | 15 | 18 | 28 | 28 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66 | 66 | 66 | 66
G2c.1327 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 3 | 4 | 4 | 11 | 12 | 13 | 15 | 25 | 25 | 26 | 27 | 28 | 28 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66
G2c.1328 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 3 | 4 | 4 | 10 | 12 | 13 | 15 | 25 | 25 | 25 | 25 | 26 | 27 | 27 | 27 | 61 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 66
G2c.1329 | I | Number of sites with sewer structure syphons interventions | Number | O_SN1_M17 | MA062 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1330 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1331 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1332 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1333 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1334 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1335 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1336 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G2c.1337 | I | Number of wastewater property operational building interventions | Number | O_SN1_M18 | MA096 | Baseline | G90 - Delivery Approval | 0 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1338 | I | [5 empty] | SOS - Start On Site | 0 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1339 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1340 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1341 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1342 | I | [5 empty] | SOS - Start On Site | 0 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1343 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1344 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1345 | I | Length of wastewater pumping main interventions | Metres | O_SN1_M2 | MA012 | Baseline | G90 - Delivery Approval | 836 | 4337 | 5639 | 5732 | 7164 | 11246 | 11248 | 11284.32 | 13084.32 | 14010.32 | 15810.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32
G2c.1346 | I | [5 empty] | SOS - Start On Site | 456 | 837 | 4339 | 5721 | 5722 | 5735 | 7746 | 7781 | 9582 | 9583.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32
G2c.1347 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 456 | 919 | 920 | 5721 | 5722 | 5723 | 7767 | 7780 | 8582.32 | 8583.32 | 8584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32
G2c.1348 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 2 | 4 | 386 | 921 | 4422 | 4422 | 5755 | 7767 | 7769 | 8581 | 8584.32 | 8584.32 | 8584.32 | 8584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32 | 9584.32
G2c.1349 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 836 | 4337 | 5639 | 5732 | 7164 | 11246 | 11248 | 11284.32 | 13084.32 | 14010.32 | 15810.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32
G2c.1350 | I | [5 empty] | SOS - Start On Site | 456 | 837 | 4339 | 5732 | 5733 | 9235 | 11247 | 11281 | 13084.32 | 13135.32 | 15810.32 | 15810.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32 | 17390.32
G2c.1351 | I | [5 empty] | G100 - Acceptance | 0 | 455 | 457 | 838 | 919 | 2221 | 5723 | 10653 | 11238 | 11273 | 12073 | 12084 | 13085.32 | 14210.32 | 16040.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32
G2c.1352 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 3 | 4 | 457 | 839 | 841 | 841 | 9142 | 11267 | 11269 | 12072 | 12073 | 12084 | 13210.32 | 15040.32 | 16040.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 16090.32 | 17390.32
G2c.1353 | I | Number of Sustainable Drainage system interventions | Number | O_SN1_M20 | MA062 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1354 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1355 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1356 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1357 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1358 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1359 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1360 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1361 | I | Number of high voltage system interventions | Number | O_SN1_M22 | MA091 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1362 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1363 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1364 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1365 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1366 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1367 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7 | 7
G2c.1368 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 5 | 7
G2c.1369 | I | Length of sea outfalls replaced or maintained | Metres | O_SN1_M3 | MA035 | Baseline | G90 - Delivery Approval | 14 | 80 | 94 | 109 | 110 | 359 | 642 | 643 | 643 | 643 | 644 | 666 | 682 | 792 | 992 | 994 | 1099 | 1201 | 1326 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327
G2c.1370 | I | [5 empty] | SOS - Start On Site | 2 | 68 | 72 | 85 | 85 | 186 | 542 | 543 | 543 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643
G2c.1371 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 3 | 7 | 73 | 186 | 527 | 528 | 543 | 543 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643
G2c.1372 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 3 | 5 | 5 | 105 | 185 | 196 | 379 | 381 | 529 | 543 | 543 | 543 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643 | 643
G2c.1373 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 14 | 80 | 94 | 109 | 110 | 359 | 642 | 643 | 643 | 643 | 644 | 666 | 682 | 792 | 992 | 994 | 1099 | 1201 | 1326 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327 | 1327
G2c.1374 | I | [5 empty] | SOS - Start On Site | 2 | 68 | 82 | 83 | 84 | 185 | 516 | 517 | 517 | 617 | 632 | 635 | 654 | 670 | 980 | 982 | 1087 | 1189 | 1189 | 1314 | 1315 | 1315 | 1315 | 1327 | 1327 | 1327
G2c.1375 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 2 | 12 | 15 | 17 | 118 | 515 | 517 | 517 | 517 | 631 | 635 | 636 | 654 | 670 | 670 | 980 | 1085 | 1185 | 1189 | 1189 | 1189 | 1326 | 1327 | 1327
G2c.1376 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 2 | 15 | 16 | 16 | 116 | 184 | 367 | 367 | 515 | 529 | 534 | 535 | 653 | 670 | 670 | 980 | 980 | 1085 | 1088 | 1189 | 1189 | 1326 | 1327
G2c.1377 | I | Length of non-critical sewer interventions | Metres | O_SN1_M4 | MA002, MA003, MA012, MA014, MA062 | Baseline | G90 - Delivery Approval | 5172.5 | 5991.5 | 6386.5 | 6714.5 | 6775 | 7425 | 8126 | 8814 | 10182 | 11035 | 11957 | 12989 | 13018 | 14284 | 16455.01 | 17856.01 | 20116.01 | 20119.01 | 20250.01 | 20250.01 | 20250.01 | 20250.01 | 20250.01 | 20325.01 | 20325.01 | 20326.01
G2c.1378 | I | [5 empty] | SOS - Start On Site | 4638 | 4764 | 5066 | 5209 | 5352 | 6244.5 | 6650 | 7380 | 7700 | 8165 | 8966 | 8967 | 8967 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 9209
G2c.1379 | I | [5 empty] | G100 - Acceptance | 0 | 3303 | 3519 | 4684 | 4846 | 5050 | 5161 | 6175.5 | 6366.5 | 7665 | 7667 | 8132 | 8133 | 8134 | 8934 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 9209
G2c.1380 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 107 | 1901 | 3745 | 3936 | 4790 | 4923 | 5949 | 6157.5 | 7004 | 7621 | 8099 | 8099 | 8099 | 8934 | 8935 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 8968 | 9209
G2c.1381 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 5172.5 | 5991.5 | 6386.5 | 6714.5 | 6775 | 7425 | 8126 | 8814 | 10182 | 11035 | 11957 | 12989 | 13018 | 14284 | 16455.01 | 17856.01 | 20116.01 | 20119.01 | 20250.01 | 20250.01 | 20250.01 | 20250.01 | 20250.01 | 20325.01 | 20325.01 | 20326.01
G2c.1382 | I | [5 empty] | SOS - Start On Site | 4718 | 4845 | 5590 | 5994 | 6110 | 6820 | 7762 | 8290 | 8921 | 9083 | 11433 | 11909 | 12470 | 13985 | 14241.01 | 16119.01 | 19760.01 | 20071.01 | 20074.01 | 20205.01 | 20205.01 | 20205.01 | 20205.01 | 20205.01 | 20280.01 | 20326.01
G2c.1383 | I | [5 empty] | G100 - Acceptance | 0 | 629 | 905 | 2498 | 2875 | 3056 | 4752 | 4827 | 7868 | 8931 | 9600 | 10069 | 10502 | 10647 | 12207 | 14006 | 14166 | 14270.01 | 16339.01 | 16617.01 | 17007.01 | 18618.01 | 18619.01 | 18750.01 | 18750.01 | 20326.01
G2c.1384 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 86 | 339 | 2150 | 2171 | 2712 | 3477 | 6235 | 7219 | 8090 | 8498 | 9632 | 10302 | 10493 | 11562 | 12634 | 13959 | 14122.01 | 14224.01 | 16294.01 | 16671.01 | 18572.01 | 18572.01 | 18704.01 | 20326.01
G2c.1385 | I | Number of street furniture interventions | Number | O_SN1_M5 | MA018 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 3 | 3 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1386 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 3 | 3 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1387 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 3 | 4 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1388 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 3 | 4 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1389 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 3 | 3 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1390 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 3 | 3 | 11 | 20 | 27 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1391 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 4 | 8 | 16 | 21 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1392 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 4 | 8 | 16 | 21 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G2c.1393 | I | Number of air valves interventions at wastewater pumping mains | Number | O_SN1_M6 | MA012 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1394 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1395 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1396 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1397 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1398 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37 | 37 | 37 | 37 | 37 | 37
G2c.1399 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37 | 37
G2c.1400 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 37 | 37
G2c.1401 | I | Number of sites with sewer structures APNRV intervention | Number | O_SN1_M7 | MA062 | Baseline | G90 - Delivery Approval | 1 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1402 | I | [5 empty] | SOS - Start On Site | 1 | 6 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1403 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 6 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1404 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1405 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1406 | I | [5 empty] | SOS - Start On Site | 1 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1407 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1408 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 5 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1409 | I | Number of Combined Storm Overflow (CSO) screen interventions | Number | O_SN1_M8 | MA017, MA023, MA039, MA043, MA062 | Baseline | G90 - Delivery Approval | 4 | 7 | 8 | 9 | 12 | 12 | 14 | 14 | 23 | 27 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32
G2c.1410 | I | [5 empty] | SOS - Start On Site | 3 | 6 | 7 | 8 | 10 | 10 | 11 | 11 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.1411 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 6 | 7 | 8 | 10 | 10 | 11 | 11 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.1412 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 6 | 7 | 8 | 10 | 10 | 11 | 11 | 19 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
G2c.1413 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 7 | 8 | 9 | 12 | 12 | 14 | 14 | 23 | 27 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32
G2c.1414 | I | [5 empty] | SOS - Start On Site | 4 | 7 | 8 | 9 | 12 | 12 | 13 | 13 | 22 | 26 | 28 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32
G2c.1415 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 7 | 8 | 8 | 10 | 12 | 13 | 21 | 24 | 24 | 28 | 28 | 29 | 30 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 32
G2c.1416 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 3 | 6 | 7 | 8 | 10 | 12 | 13 | 21 | 22 | 23 | 25 | 25 | 26 | 28 | 29 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 32
G2c.1417 | I | Number of fixed wire electrical system or statutory maintenance asset interventions | Number | O_SN1_M9 | MA068 | Baseline | G90 - Delivery Approval | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1418 | I | [5 empty] | SOS - Start On Site | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1419 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1420 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1421 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1422 | I | [5 empty] | SOS - Start On Site | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1423 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1424 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260 | 4260
G2c.1425 | I | Number of unsatisfactory intermittent discharges (UID) improved or removed for water quality | Number | O_SN2_E2 | SR15 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1426 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1427 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1428 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1429 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1430 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1431 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1432 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1433 | I | Number of Transformation initiatives implemented | Number | O_TF1_E | MA104 | Baseline | G90 - Delivery Approval | 1 | 4 | 6 | 11 | 19 | 43 | 49 | 49 | 53 | 62 | 65 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 67
G2c.1434 | I | [5 empty] | SOS - Start On Site | 0 | 3 | 4 | 8 | 16 | 29 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
G2c.1435 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 8 | 10 | 14 | 15 | 16 | 17 | 18 | 23 | 25 | 27 | 27 | 27 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 36 | 38
G2c.1436 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 14 | 15 | 16 | 16 | 17 | 19 | 24 | 25 | 27 | 27 | 28 | 29 | 29 | 29 | 29 | 29 | 35 | 38
G2c.1437 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 4 | 6 | 11 | 19 | 43 | 49 | 49 | 53 | 62 | 65 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 67
G2c.1438 | I | [5 empty] | SOS - Start On Site | 0 | 4 | 6 | 11 | 19 | 39 | 49 | 49 | 53 | 59 | 65 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 67
G2c.1439 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 2 | 10 | 12 | 13 | 18 | 24 | 34 | 36 | 43 | 46 | 48 | 50 | 54 | 56 | 57 | 57 | 58 | 58 | 58 | 58 | 65 | 67
G2c.1440 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 12 | 13 | 17 | 25 | 33 | 35 | 38 | 45 | 47 | 47 | 50 | 55 | 56 | 56 | 57 | 57 | 57 | 64 | 67
G2c.1441 | I | Number of sites with emergency planning equipment installed | Number | O_WR1_E1 | MA098 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1442 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1443 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1444 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1445 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1446 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1447 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1448 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1449 | I | Number of sites with standby power equipment installed | Number | O_WR1_E2 | MA092 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1450 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1451 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1452 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1453 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1454 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1455 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1456 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1457 | I | Number of sites with emergency planning equipment interventions | Number | O_WR1_M | MA098 | Baseline | G90 - Delivery Approval | 0 | 0 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1458 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 4 | 4 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G2c.1459 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G2c.1460 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 56
G2c.1461 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1462 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 4 | 4 | 5 | 5 | 6 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1463 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 4 | 5 | 5 | 6 | 6 | 6 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1464 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
G2c.1465 | I | Number of strategic network valve interventions | Number | O_WR2_M | MA060 | Baseline | G90 - Delivery Approval | 52003 | 52009 | 52026 | 52035 | 52040 | 52040 | 52040 | 52046 | 52052 | 52052 | 52915 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916
G2c.1466 | I | [5 empty] | SOS - Start On Site | 52002 | 52007 | 52009 | 52028 | 52029 | 52029 | 52036 | 52042 | 52048 | 52048 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052
G2c.1467 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 52005 | 52010 | 52012 | 52013 | 52013 | 52016 | 52026 | 52033 | 52048 | 52048 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052
G2c.1468 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 52005 | 52009 | 52012 | 52012 | 52013 | 52015 | 52019 | 52031 | 52033 | 52033 | 52048 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052 | 52052
G2c.1469 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 52003 | 52009 | 52026 | 52035 | 52040 | 52040 | 52040 | 52046 | 52052 | 52052 | 52915 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916
G2c.1470 | I | [5 empty] | SOS - Start On Site | 52002 | 52007 | 52009 | 52027 | 52028 | 52028 | 52028 | 52040 | 52046 | 52047 | 52047 | 52049 | 52050 | 52054 | 52054 | 52054 | 52054 | 52054 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916 | 52916
G2c.1471 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 4 | 6 | 6 | 52009 | 52009 | 52010 | 52013 | 52024 | 52031 | 52032 | 52032 | 52034 | 52034 | 52035 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52916 | 52916
G2c.1472 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 6 | 6 | 8 | 52008 | 52009 | 52012 | 52023 | 52023 | 52031 | 52032 | 52032 | 52033 | 52034 | 52034 | 52050 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52054 | 52916
G2c.1473 | I | Number of water hydraulic models maintained | Number | O_WR4_M | MA054 | Baseline | G90 - Delivery Approval | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1474 | I | [5 empty] | SOS - Start On Site | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1475 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 11 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1476 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 11 | 11 | 11 | 11 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1477 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1478 | I | [5 empty] | SOS - Start On Site | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1479 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 59 | 59 | 59 | 59 | 59 | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1480 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 59 | 59 | 59 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
G2c.1481 | I | Number of WTW's with capacity restored | Number | O_WR7_E | MA087 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1482 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1483 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1484 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1485 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1486 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1487 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1488 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1489 | I | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1490 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1491 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1492 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1493 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1494 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1495 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1496 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1497 | I | Number of sites with security fending or gate interventions - wastewater | Metres | O_WW1_M1 | MA096 | Baseline | G90 - Delivery Approval | 3 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16
G2c.1498 | I | [5 empty] | SOS - Start On Site | 3 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1499 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1500 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
G2c.1501 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16
G2c.1502 | I | [5 empty] | SOS - Start On Site | 3 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16
G2c.1503 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 3 | 5 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16
G2c.1504 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 3 | 5 | 6 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16
G2c.1505 | I | Number of WWTW odour equipment asset interventions | Number | O_WW1_M10 | MA049, SR15 | Baseline | G90 - Delivery Approval | 3.01 | 5.01 | 13.01 | 15.01 | 17.01 | 17.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2c.1506 | I | [5 empty] | SOS - Start On Site | 3 | 4 | 11 | 12 | 14 | 14 | 15 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.1507 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 5 | 11 | 12 | 12 | 12 | 14 | 15 | 46 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.1508 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 5 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 44 | 46 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G2c.1509 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3.01 | 5.01 | 13.01 | 15.01 | 17.01 | 17.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2c.1510 | I | [5 empty] | SOS - Start On Site | 3.01 | 5.01 | 12.01 | 13.01 | 14.01 | 15.01 | 45.01 | 47.01 | 48.01 | 48.01 | 48.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2c.1511 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 4 | 7 | 10 | 10 | 11 | 14 | 16 | 46 | 46 | 47 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2c.1512 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 2 | 6 | 9 | 10 | 10 | 12 | 13 | 13 | 14 | 44 | 45 | 46 | 47 | 48 | 49 | 49 | 49 | 49 | 49 | 49.01 | 49.01 | 49.01 | 49.01 | 49.01
G2c.1513 | I | Number of WWTW primary treatment asset interventions | Number | O_WW1_M11 | MA013, MA017, MA039, MA042, MA043 | Baseline | G90 - Delivery Approval | 40 | 105 | 130 | 138 | 156 | 158 | 176 | 198 | 392 | 393 | 398 | 398 | 399 | 403 | 403 | 403 | 404 | 404 | 404 | 406 | 406 | 409 | 409 | 411 | 412 | 414
G2c.1514 | I | [5 empty] | SOS - Start On Site | 36 | 95 | 119 | 128 | 147 | 149 | 168 | 190 | 242 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384
G2c.1515 | I | [5 empty] | G100 - Acceptance | 0 | 34 | 93 | 113 | 125 | 144 | 145 | 165 | 190 | 230 | 230 | 231 | 231 | 233 | 233 | 245 | 245 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384 | 384
G2c.1516 | I | [5 empty] | G110 - Financial Closure | 0 | 31 | 90 | 112 | 122 | 138 | 138 | 159 | 186 | 228 | 228 | 228 | 231 | 231 | 231 | 233 | 233 | 233 | 245 | 384 | 384 | 384 | 384 | 384 | 384 | 384
G2c.1517 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 40 | 105 | 130 | 138 | 156 | 158 | 176 | 198 | 392 | 393 | 398 | 398 | 399 | 403 | 403 | 403 | 404 | 404 | 404 | 406 | 406 | 409 | 409 | 411 | 412 | 414
G2c.1518 | I | [5 empty] | SOS - Start On Site | 37 | 100 | 127 | 135 | 152 | 153 | 173 | 196 | 249 | 392 | 392 | 395 | 395 | 399 | 401 | 402 | 402 | 404 | 404 | 404 | 406 | 407 | 409 | 409 | 411 | 414
G2c.1519 | I | [5 empty] | G100 - Acceptance | 0 | 17 | 60 | 99 | 113 | 134 | 147 | 163 | 180 | 235 | 235 | 237 | 240 | 242 | 244 | 258 | 259 | 399 | 400 | 400 | 400 | 402 | 402 | 402 | 405 | 414
G2c.1520 | I | [5 empty] | G110 - Financial Closure | 0 | 14 | 55 | 97 | 112 | 133 | 140 | 156 | 174 | 232 | 232 | 233 | 234 | 235 | 239 | 241 | 243 | 255 | 257 | 398 | 399 | 400 | 401 | 402 | 402 | 414
G2c.1521 | I | Number of redundant or abandoned assets interventions - WWTW | Number | O_WW1_M12 | MA011, MA096 | Baseline | G90 - Delivery Approval | 3 | 4 | 29 | 29 | 29 | 29 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.1522 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 3 | 3 | 4 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.1523 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.1524 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 7 | 7 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
G2c.1525 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 3 | 4 | 29 | 29 | 29 | 29 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.1526 | I | [5 empty] | SOS - Start On Site | 1 | 2 | 2 | 3 | 4 | 4 | 7 | 12 | 12 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39
G2c.1527 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 9 | 9 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39
G2c.1528 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 4 | 4 | 4 | 9 | 9 | 9 | 9 | 34 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 39
G2c.1529 | I | Number of WWTW secondary treatment asset interventions | Number | O_WW1_M13 | MA017, MA024, MA035, MA036, MA042, MA043, MA057 | Baseline | G90 - Delivery Approval | 244 | 330 | 475 | 535 | 625 | 639 | 705 | 841 | 1356 | 1370 | 1380 | 1386 | 1387 | 1394 | 1396 | 1399 | 1440 | 1448 | 1450 | 1452 | 1452 | 1453 | 1454 | 1455 | 1457 | 1459
G2c.1530 | I | [5 empty] | SOS - Start On Site | 201 | 280 | 402 | 474 | 563 | 568 | 636 | 774 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908
G2c.1531 | I | [5 empty] | G100 - Acceptance | 0 | 176 | 254 | 399 | 451 | 542 | 556 | 627 | 766 | 897 | 901 | 906 | 906 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908
G2c.1532 | I | [5 empty] | G110 - Financial Closure | 0 | 156 | 228 | 364 | 433 | 524 | 537 | 610 | 752 | 886 | 890 | 900 | 902 | 902 | 906 | 906 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908 | 908
G2c.1533 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 244 | 330 | 475 | 535 | 625 | 639 | 705 | 841 | 1356 | 1370 | 1380 | 1386 | 1387 | 1394 | 1396 | 1399 | 1440 | 1448 | 1450 | 1452 | 1452 | 1453 | 1454 | 1455 | 1457 | 1459
G2c.1534 | I | [5 empty] | SOS - Start On Site | 230 | 320 | 448 | 508 | 614 | 617 | 697 | 831 | 968 | 1358 | 1371 | 1378 | 1382 | 1387 | 1394 | 1396 | 1398 | 1443 | 1447 | 1449 | 1451 | 1451 | 1452 | 1453 | 1454 | 1459
G2c.1535 | I | [5 empty] | G100 - Acceptance | 0 | 93 | 199 | 291 | 342 | 452 | 516 | 597 | 696 | 932 | 951 | 970 | 981 | 985 | 1000 | 1000 | 1007 | 1392 | 1393 | 1396 | 1402 | 1402 | 1408 | 1409 | 1411 | 1459
G2c.1536 | I | [5 empty] | G110 - Financial Closure | 0 | 70 | 171 | 271 | 325 | 430 | 498 | 579 | 668 | 902 | 913 | 945 | 962 | 980 | 990 | 995 | 998 | 1005 | 1008 | 1392 | 1392 | 1397 | 1400 | 1407 | 1409 | 1459
G2c.1537 | I | Number of site welfare facilities interventions - WWTW | Number | O_WW1_M14 | MA096 | Baseline | G90 - Delivery Approval | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12
G2c.1538 | I | [5 empty] | SOS - Start On Site | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1539 | I | [5 empty] | G100 - Acceptance | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1540 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1541 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12
G2c.1542 | I | [5 empty] | SOS - Start On Site | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12
G2c.1543 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 7 | 7 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 12
G2c.1544 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 12
G2c.1545 | I | Number of WWTW sites with temporary process unit interventions | Number | O_WW1_M15 | MA021, MA043, MA057 | Baseline | G90 - Delivery Approval | 15 | 16 | 17 | 17 | 24 | 24 | 24 | 24 | 26 | 26 | 27 | 27 | 29 | 29 | 29 | 30 | 31 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1546 | I | [5 empty] | SOS - Start On Site | 15 | 16 | 17 | 17 | 17 | 17 | 24 | 24 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1547 | I | [5 empty] | G100 - Acceptance | 5 | 13 | 14 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 19 | 19 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1548 | I | [5 empty] | G110 - Financial Closure | 5 | 12 | 13 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 19 | 24 | 24 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1549 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 15 | 16 | 17 | 17 | 24 | 24 | 24 | 24 | 26 | 26 | 27 | 27 | 29 | 29 | 29 | 30 | 31 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1550 | I | [5 empty] | SOS - Start On Site | 15 | 16 | 17 | 17 | 17 | 17 | 24 | 24 | 25 | 26 | 26 | 26 | 28 | 29 | 29 | 29 | 30 | 31 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1551 | I | [5 empty] | G100 - Acceptance | 0 | 3 | 4 | 4 | 10 | 10 | 15 | 15 | 16 | 16 | 16 | 18 | 24 | 24 | 25 | 27 | 28 | 29 | 29 | 29 | 31 | 32 | 33 | 33 | 33 | 34
G2c.1552 | I | [5 empty] | G110 - Financial Closure | 0 | 3 | 4 | 4 | 10 | 10 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 23 | 24 | 25 | 27 | 27 | 29 | 29 | 29 | 30 | 32 | 33 | 33 | 34
G2c.1553 | I | Number of WWTW treatment ancillaries asset interventions | Number | O_WW1_M16 | MA011, MA023, MA024, MA039, MA043, MA057, MA096 | Baseline | G90 - Delivery Approval | 369 | 585 | 758 | 1107 | 1539 | 1613 | 1908 | 2956 | 3453 | 3471 | 3476 | 3479 | 3481 | 3489 | 3491 | 3493 | 3493 | 3500 | 3520 | 3820 | 3821 | 3821 | 3821 | 3822 | 3823 | 3826
G2c.1554 | I | [5 empty] | SOS - Start On Site | 352 | 555 | 724 | 1078 | 1509 | 1573 | 1820 | 2242 | 3309 | 3312 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313 | 3313
G2c.1555 | I | [5 empty] | G100 - Acceptance | 0 | 123 | 322 | 509 | 1089 | 1504 | 1572 | 1833 | 2190 | 2584 | 2584 | 2589 | 2589 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 3312 | 3312 | 3312 | 3313
G2c.1556 | I | [5 empty] | G110 - Financial Closure | 0 | 122 | 316 | 506 | 854 | 1266 | 1556 | 1826 | 2184 | 2575 | 2580 | 2581 | 2587 | 2589 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 2640 | 3312 | 3313
G2c.1557 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 369 | 585 | 758 | 1107 | 1539 | 1613 | 1908 | 2956 | 3453 | 3471 | 3476 | 3479 | 3481 | 3489 | 3491 | 3493 | 3493 | 3500 | 3520 | 3820 | 3821 | 3821 | 3821 | 3822 | 3823 | 3826
G2c.1558 | I | [5 empty] | SOS - Start On Site | 357 | 567 | 742 | 1094 | 1528 | 1593 | 1839 | 2261 | 3332 | 3453 | 3470 | 3473 | 3476 | 3479 | 3488 | 3490 | 3491 | 3496 | 3500 | 3520 | 3520 | 3821 | 3821 | 3821 | 3823 | 3826
G2c.1559 | I | [5 empty] | G100 - Acceptance | 1 | 73 | 220 | 381 | 776 | 1136 | 1311 | 1517 | 1803 | 2604 | 2618 | 2641 | 2645 | 2700 | 2702 | 2704 | 2709 | 2811 | 2816 | 2818 | 2822 | 2825 | 3499 | 3800 | 3800 | 3826
G2c.1560 | I | [5 empty] | G110 - Financial Closure | 1 | 72 | 219 | 377 | 537 | 895 | 1297 | 1505 | 1790 | 2591 | 2603 | 2621 | 2627 | 2637 | 2640 | 2697 | 2701 | 2706 | 2709 | 2812 | 2816 | 2818 | 2822 | 2826 | 3800 | 3826
G2c.1561 | I | Number of high voltage system interventions | Number | O_WW1_M17 | MA091 | Baseline | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
G2c.1562 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1563 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1564 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1565 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
G2c.1566 | I | [5 empty] | SOS - Start On Site | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4
G2c.1567 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4
G2c.1568 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4
G2c.1569 | I | Number of WWTW statutory maintenance asset interventions | Number | O_WW1_M18 | MA068 | Baseline | G90 - Delivery Approval | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1570 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1571 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1572 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1573 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1574 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1575 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1576 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1577 | I | Number of fixed wire electrical system asset interventions | Number | O_WW1_M2 | MA068 | Baseline | G90 - Delivery Approval | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2c.1578 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1579 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1580 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1581 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2c.1582 | I | [5 empty] | SOS - Start On Site | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2c.1583 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2c.1584 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565 | 1565
G2c.1585 | I | Number of WWTW Motor Control Centre interventions | Number | O_WW1_M3 | MA011 | Baseline | G90 - Delivery Approval | 210 | 220 | 226 | 228 | 468 | 468 | 468 | 469 | 470 | 473 | 477 | 486 | 486 | 486 | 489 | 489 | 489 | 489 | 491 | 493 | 493 | 493 | 493 | 493 | 493 | 494
G2c.1586 | I | [5 empty] | SOS - Start On Site | 202 | 206 | 221 | 223 | 226 | 463 | 463 | 463 | 463 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465
G2c.1587 | I | [5 empty] | G100 - Acceptance | 0 | 201 | 206 | 212 | 216 | 220 | 226 | 226 | 226 | 463 | 463 | 464 | 464 | 464 | 464 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465
G2c.1588 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 4 | 11 | 215 | 218 | 220 | 226 | 226 | 226 | 226 | 463 | 463 | 464 | 464 | 464 | 464 | 464 | 465 | 465 | 465 | 465 | 465 | 465 | 465 | 465
G2c.1589 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 210 | 220 | 226 | 228 | 468 | 468 | 468 | 469 | 470 | 473 | 477 | 486 | 486 | 486 | 489 | 489 | 489 | 489 | 491 | 493 | 493 | 493 | 493 | 493 | 493 | 494
G2c.1590 | I | [5 empty] | SOS - Start On Site | 207 | 213 | 225 | 227 | 467 | 467 | 468 | 468 | 469 | 469 | 470 | 473 | 484 | 484 | 486 | 486 | 486 | 489 | 489 | 491 | 493 | 493 | 493 | 493 | 493 | 494
G2c.1591 | I | [5 empty] | G100 - Acceptance | 0 | 5 | 11 | 12 | 13 | 218 | 219 | 225 | 225 | 466 | 466 | 468 | 468 | 469 | 474 | 474 | 476 | 476 | 476 | 476 | 479 | 479 | 479 | 486 | 486 | 494
G2c.1592 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 7 | 8 | 9 | 13 | 215 | 215 | 225 | 229 | 229 | 467 | 467 | 468 | 468 | 469 | 474 | 474 | 476 | 476 | 476 | 479 | 479 | 479 | 479 | 494
G2c.1593 | I | Number of wastewater SCADA interventions | Number | O_WW1_M4 | MA011, MA013, MA023 | Baseline | G90 - Delivery Approval | 17 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 24 | 24 | 39 | 40 | 40 | 41 | 42 | 46 | 47 | 48 | 48 | 48 | 48 | 50 | 50
G2c.1594 | I | [5 empty] | SOS - Start On Site | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1595 | I | [5 empty] | G100 - Acceptance | 0 | 2 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1596 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1597 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 17 | 19 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 24 | 24 | 39 | 40 | 40 | 41 | 42 | 46 | 47 | 48 | 48 | 48 | 48 | 50 | 50
G2c.1598 | I | [5 empty] | SOS - Start On Site | 16 | 18 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 24 | 38 | 39 | 40 | 41 | 42 | 46 | 47 | 48 | 48 | 48 | 48 | 50
G2c.1599 | I | [5 empty] | G100 - Acceptance | 0 | 15 | 17 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 22 | 22 | 24 | 26 | 26 | 38 | 40 | 42 | 42 | 42 | 50
G2c.1600 | I | [5 empty] | G110 - Financial Closure | 0 | 2 | 4 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 23 | 25 | 26 | 38 | 39 | 41 | 42 | 50
G2c.1601 | I | Number of screw pumps intervention | Number | O_WW1_M5 | MA036 | Baseline | G90 - Delivery Approval | 17 | 26 | 29 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.1602 | I | [5 empty] | SOS - Start On Site | 12 | 24 | 26 | 26 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1603 | I | [5 empty] | G100 - Acceptance | 0 | 10 | 20 | 26 | 26 | 26 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1604 | I | [5 empty] | G110 - Financial Closure | 0 | 8 | 17 | 20 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1605 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 17 | 26 | 29 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33 | 33
G2c.1606 | I | [5 empty] | SOS - Start On Site | 14 | 26 | 28 | 28 | 29 | 29 | 29 | 29 | 30 | 30 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 33
G2c.1607 | I | [5 empty] | G100 - Acceptance | 0 | 8 | 17 | 21 | 28 | 28 | 28 | 28 | 30 | 30 | 30 | 30 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33 | 33
G2c.1608 | I | [5 empty] | G110 - Financial Closure | 0 | 4 | 14 | 18 | 23 | 23 | 25 | 28 | 29 | 29 | 30 | 30 | 30 | 30 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 33
G2c.1609 | I | Number of wastewater telemetry interventions | Number | O_WW1_M6 | MA044 | Baseline | G90 - Delivery Approval | 526 | 529 | 537 | 537 | 539 | 539 | 861 | 863 | 1002 | 1418 | 1418 | 1419 | 1419 | 1419 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511
G2c.1610 | I | [5 empty] | SOS - Start On Site | 518 | 521 | 529 | 536 | 538 | 538 | 538 | 538 | 539 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540
G2c.1611 | I | [5 empty] | G100 - Acceptance | 0 | 121 | 125 | 320 | 321 | 538 | 538 | 538 | 538 | 538 | 539 | 539 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540
G2c.1612 | I | [5 empty] | G110 - Financial Closure | 0 | 58 | 124 | 132 | 321 | 322 | 531 | 531 | 538 | 538 | 538 | 538 | 539 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540
G2c.1613 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 526 | 529 | 537 | 537 | 539 | 539 | 861 | 863 | 1002 | 1418 | 1418 | 1419 | 1419 | 1419 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511
G2c.1614 | I | [5 empty] | SOS - Start On Site | 519 | 522 | 530 | 537 | 539 | 539 | 539 | 862 | 1001 | 1153 | 1329 | 1329 | 1330 | 1330 | 1330 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511
G2c.1615 | I | [5 empty] | G100 - Acceptance | 1 | 63 | 117 | 128 | 128 | 339 | 533 | 536 | 536 | 540 | 540 | 541 | 542 | 542 | 719 | 1008 | 1139 | 1139 | 1330 | 1419 | 1511 | 1511 | 1511 | 1511 | 1511 | 1511
G2c.1616 | I | [5 empty] | G110 - Financial Closure | 1 | 1 | 116 | 127 | 128 | 130 | 526 | 529 | 536 | 540 | 540 | 540 | 541 | 542 | 542 | 719 | 719 | 1008 | 1139 | 1139 | 1419 | 1419 | 1511 | 1511 | 1511 | 1511
G2c.1617 | I | Number of wastewater property operational building interventions | Number | O_WW1_M7 | MA096 | Baseline | G90 - Delivery Approval | 78 | 124 | 143 | 160 | 170 | 173 | 204 | 204 | 204 | 224 | 228 | 228 | 229 | 232 | 232 | 234 | 234 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237
G2c.1618 | I | [5 empty] | SOS - Start On Site | 69 | 114 | 136 | 153 | 165 | 170 | 171 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172
G2c.1619 | I | [5 empty] | G100 - Acceptance | 0 | 52 | 99 | 137 | 151 | 164 | 166 | 169 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172
G2c.1620 | I | [5 empty] | G110 - Financial Closure | 0 | 52 | 92 | 118 | 138 | 159 | 163 | 164 | 168 | 170 | 170 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172 | 172
G2c.1621 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 78 | 124 | 143 | 160 | 170 | 173 | 204 | 204 | 204 | 224 | 228 | 228 | 229 | 232 | 232 | 234 | 234 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237
G2c.1622 | I | [5 empty] | SOS - Start On Site | 69 | 117 | 138 | 155 | 166 | 170 | 173 | 203 | 203 | 203 | 224 | 228 | 228 | 231 | 231 | 233 | 234 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237
G2c.1623 | I | [5 empty] | G100 - Acceptance | 0 | 15 | 60 | 96 | 112 | 126 | 135 | 147 | 155 | 164 | 173 | 174 | 197 | 199 | 199 | 199 | 203 | 203 | 233 | 236 | 237 | 237 | 237 | 237 | 237 | 237
G2c.1624 | I | [5 empty] | G110 - Financial Closure | 0 | 14 | 57 | 84 | 101 | 125 | 133 | 139 | 150 | 158 | 158 | 162 | 171 | 193 | 197 | 198 | 198 | 202 | 203 | 204 | 233 | 234 | 236 | 237 | 237 | 237
G2c.1625 | I | Number of WWTW inlet works asset interventions | Number | O_WW1_M9 | MA011, MA017, MA023, MA042, MA043 | Baseline | G90 - Delivery Approval | 145 | 193 | 239 | 264 | 321 | 322 | 345 | 416 | 735 | 755.01 | 759.01 | 766.01 | 767.01 | 778.01 | 780.01 | 780.01 | 780.01 | 781.01 | 787.01 | 787.01 | 787.01 | 788.01 | 789.01 | 790.01 | 790.01 | 791.01
G2c.1626 | I | [5 empty] | SOS - Start On Site | 132 | 175 | 215 | 244 | 305 | 306 | 329 | 403 | 471 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472
G2c.1627 | I | [5 empty] | G100 - Acceptance | 0 | 41 | 96 | 139 | 167 | 268 | 274 | 316 | 385 | 466 | 470 | 470 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472
G2c.1628 | I | [5 empty] | G110 - Financial Closure | 0 | 34 | 83 | 122 | 151 | 207 | 266 | 292 | 362 | 431 | 453 | 457 | 469 | 470 | 471 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472 | 472
G2c.1629 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 145 | 193 | 239 | 264 | 321 | 322 | 345 | 416 | 735 | 755.01 | 759.01 | 766.01 | 767.01 | 778.01 | 780.01 | 780.01 | 780.01 | 781.01 | 787.01 | 787.01 | 787.01 | 788.01 | 789.01 | 790.01 | 790.01 | 791.01
G2c.1630 | I | [5 empty] | SOS - Start On Site | 139 | 184 | 229 | 255 | 314 | 317 | 338 | 409 | 480 | 741.01 | 754.01 | 759.01 | 764.01 | 767.01 | 768.01 | 780.01 | 780.01 | 781.01 | 781.01 | 787.01 | 787.01 | 787.01 | 788.01 | 789.01 | 790.01 | 791.01
G2c.1631 | I | [5 empty] | G100 - Acceptance | 0 | 23 | 67 | 113 | 127 | 220 | 242 | 272 | 328 | 441 | 464 | 470.01 | 476.01 | 484.01 | 486.01 | 496.01 | 507.01 | 757.01 | 769.01 | 781.01 | 781.01 | 781.01 | 781.01 | 781.01 | 781.01 | 791.01
G2c.1632 | I | [5 empty] | G110 - Financial Closure | 0 | 19 | 62 | 98 | 118 | 165 | 185 | 262 | 319 | 430 | 436 | 463 | 468.01 | 471.01 | 476.01 | 485.01 | 492.01 | 497.01 | 508.01 | 759.01 | 771.01 | 781.01 | 781.01 | 781.01 | 781.01 | 791.01
G2c.1633 | I | Number of WWTW continuous discharges improved or removed | Number | O_WW2_E | MA014, MA049 | Baseline | G90 - Delivery Approval | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01
G2c.1634 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1635 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1636 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1637 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01
G2c.1638 | I | [5 empty] | SOS - Start On Site | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01
G2c.1639 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01 | 1.01 | 1.01
G2c.1640 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.01 | 1.01 | 1.01
G2c.1641 | I | Number of studies complete | Number | O_WW3_E | MA017, MA039 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1642 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1643 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1644 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1645 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1646 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1647 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1648 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Supporting Sustainable Economic Growth |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1649 | I | Number of Asset Inspections completed | Number | O_AI1_M | MA065, MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1650 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1651 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1652 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1653 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1654 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1655 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1656 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1657 | I | Number of sludge treatment centre asset interventions | Number | O_BR1_M | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1658 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1659 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1660 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1661 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1662 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1663 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.1664 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.1665 | I | Investigation | Number | O_DW5A | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1666 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1667 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1668 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.1669 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1670 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1671 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1672 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1673 | I | Number of WWTW sites requiring RRR activities to support Part 4 Growth | Number | O_ED1_M | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 5029 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838
G2c.1674 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1675 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1676 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G2c.1677 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 5029 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838
G2c.1678 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 1 | 1 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 5029 | 5029 | 5029 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838 | 15838
G2c.1679 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 5027 | 5027 | 5027 | 5027 | 5027 | 5028 | 5028 | 5029 | 5029 | 15838
G2c.1680 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 26 | 26 | 26 | 27 | 27 | 27 | 5027 | 5027 | 5027 | 5027 | 5027 | 5028 | 5028 | 5029 | 15838
G2c.1681 | I | Increase in Part 4 capacity to meet strategic growth requirements | Population Equivalent | O_ED2_G | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998
G2c.1682 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1683 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1684 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1685 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998
G2c.1686 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 25476 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998 | 27998
G2c.1687 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 25476 | 27998
G2c.1688 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25476 | 25476 | 25476 | 25476 | 27998
G2c.1689 | I | Increase in Part 4 capacity to meet local growth requirements | Population Equivalent | O_ED3_G | MA026 | Baseline | G90 - Delivery Approval | 22720 | 22720 | 33463 | 33592 | 34099 | 38896 | 146481.01 | 149270.11 | 152523.17 | 153330.28 | 156039.28 | 161263.28 | 165232.28 | 171536.28 | 173009.28 | 179115.28 | 179115.28 | 179711.28 | 179985.28 | 197901.28 | 204583.28 | 206843.28 | 206843.28 | 211335.28 | 211435.28 | 255674.28
G2c.1690 | I | [5 empty] | SOS - Start On Site | 21314 | 21721 | 33340 | 33430 | 33880 | 33913 | 36092 | 142876 | 146632.03 | 146632.03 | 148033.03 | 148440.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03
G2c.1691 | I | [5 empty] | G100 - Acceptance | 0 | 151 | 2745 | 7270 | 10215 | 11447 | 21721 | 21722 | 21723 | 23482 | 24898.03 | 27639.03 | 28268.03 | 133213.03 | 147987.03 | 148394.03 | 148440.03 | 148440.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03
G2c.1692 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 151 | 2745 | 7270 | 10216 | 11449 | 21723 | 21723 | 21756.02 | 21846.03 | 24898.03 | 29817.03 | 31891.03 | 135391.03 | 147987.03 | 148394.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03 | 148569.03
G2c.1693 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 22720 | 22720 | 33463 | 33592 | 34099 | 38896 | 146481.01 | 149270.11 | 152523.17 | 153330.28 | 156039.28 | 161263.28 | 165232.28 | 171536.28 | 173009.28 | 179115.28 | 179115.28 | 179711.28 | 179985.28 | 197901.28 | 204583.28 | 206843.28 | 206843.28 | 211335.28 | 211435.28 | 255674.28
G2c.1694 | I | [5 empty] | SOS - Start On Site | 21314 | 21721 | 32374 | 32464 | 33970 | 38138 | 144087.01 | 147459.11 | 150586.17 | 151331.28 | 152923.28 | 153904.28 | 157868.28 | 169449.28 | 171169.28 | 173009.28 | 173789.28 | 179115.28 | 179658.28 | 179985.28 | 197901.28 | 204583.28 | 206843.28 | 206843.28 | 211335.28 | 255674.28
G2c.1695 | I | [5 empty] | G100 - Acceptance | 0 | 151 | 2745 | 2745 | 3699 | 3805 | 12044 | 21110.1 | 21787.11 | 26905.14 | 29646.17 | 30275.28 | 133865.28 | 138462.28 | 152091.28 | 153775.28 | 156969.28 | 158401.28 | 162606.28 | 162682.28 | 162922.28 | 163825.28 | 165833.28 | 172067.28 | 173457.28 | 255674.28
G2c.1696 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 151 | 2745 | 2801 | 3699 | 4075 | 17945.11 | 17946.12 | 22700.13 | 23150.16 | 27376.28 | 28005.28 | 136030.28 | 150326.28 | 152092.28 | 154260.28 | 157647.28 | 162335.28 | 162606.28 | 162813.28 | 163977.28 | 165833.28 | 172067.28 | 255674.28
G2c.1697 | I | Additional Capacity enabled from strategic wastewater network reinforcement | Population Equivalent | O_ED4_G | MA032 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 3600 | 3600 | 4766 | 4766 | 5683 | 5683 | 5683 | 20010 | 20010 | 21691 | 21692 | 28487 | 44877 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297
G2c.1698 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 4766 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683 | 5683
G2c.1699 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3707 | 3707 | 3707 | 3707 | 3707 | 3707 | 3707 | 3707 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 5683
G2c.1700 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3707 | 3707 | 3707 | 3707 | 3707 | 3707 | 3707 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 4517 | 5683
G2c.1701 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 3600 | 3600 | 4766 | 4766 | 5683 | 5683 | 5683 | 20010 | 20010 | 21691 | 21692 | 28487 | 44877 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297
G2c.1702 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1166 | 1166 | 2083 | 2083 | 2083 | 2083 | 16410 | 20010 | 21691 | 21692 | 28487 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297 | 60297
G2c.1703 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 107 | 107 | 107 | 107 | 13996 | 16396 | 16396 | 18886 | 18887 | 18888 | 27321 | 27323 | 59131 | 59131 | 59131 | 60297
G2c.1704 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 107 | 107 | 3707 | 9396 | 13996 | 17206 | 18886 | 18887 | 18888 | 20526 | 27322 | 42743 | 59131 | 60297
G2c.1705 | I | Number of schemes supported by Reasonable Cost Contributions | Number | O_ED5_G | MA065 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1706 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1707 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1708 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.1709 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1710 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1711 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1712 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
G2c.1713 | I | Increase in Part 4 capacity to meet commercial growth requirements | Population Equivalent | O_ED6_G | MA026 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265
G2c.1714 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1715 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1716 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1717 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265
G2c.1718 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265 | 5265
G2c.1719 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 3065 | 3065 | 3065 | 5265 | 5265 | 5265
G2c.1720 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3065 | 3065 | 3065 | 3065 | 3065 | 3065 | 3065 | 5265
G2c.1721 | I | Number of service relocations | Number | O_EG1_G | MA065 | Baseline | G90 - Delivery Approval | 1000 | 1001 | 1002 | 1128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1178 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186 | 1186 | 1186 | 1186 | 1186 | 1186
G2c.1722 | I | [5 empty] | SOS - Start On Site | 1000 | 1000 | 1001 | 1127 | 1128 | 1128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129
G2c.1723 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 128 | 1128 | 1128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129
G2c.1724 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 128 | 128 | 128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129 | 1129
G2c.1725 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1000 | 1001 | 1002 | 1128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1178 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186 | 1186 | 1186 | 1186 | 1186 | 1186
G2c.1726 | I | [5 empty] | SOS - Start On Site | 1000 | 1000 | 1001 | 1127 | 1128 | 1128 | 1128 | 1129 | 1129 | 1129 | 1178 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186 | 1186 | 1186 | 1186
G2c.1727 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1129 | 1129 | 1129 | 1176 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186 | 1186
G2c.1728 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 129 | 1129 | 1129 | 1129 | 1176 | 1178 | 1178 | 1178 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1180 | 1186 | 1186
G2c.1729 | I | Population benefiting from strategic network reinforcement | Population Equivalent | O_EG2_G | MA032 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 3745 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 45746 | 45746 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747
G2c.1730 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745
G2c.1731 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745
G2c.1732 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745 | 3745
G2c.1733 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 3745 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 45746 | 45746 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747
G2c.1734 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 33685 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 35745 | 45746 | 45746 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747 | 45747
G2c.1735 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 35745 | 35745 | 35745 | 35745 | 45745 | 45745 | 45745 | 45746 | 45747
G2c.1736 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685 | 1685 | 1685 | 1685 | 3745 | 3745 | 3745 | 3745 | 3745 | 35745 | 35745 | 35745 | 35745 | 45745 | 45745 | 45745 | 45747
G2c.1737 | I | Additional Capacity enabled from strategic water network reinforcement | Population Equivalent | O_WR10_G1 | MA032, MA065 | Baseline | G90 - Delivery Approval | 19359 | 19359 | 20265 | 23391 | 25838 | 43538 | 45956 | 45956 | 48016 | 99578 | 99578 | 129078 | 129702 | 129977 | 129977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977
G2c.1738 | I | [5 empty] | SOS - Start On Site | 14849 | 18749 | 18749 | 18749 | 20210 | 27831 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649 | 43649
G2c.1739 | I | [5 empty] | G100 - Acceptance | 0 | 1320 | 2649 | 10149 | 13989 | 16889 | 17889 | 31624 | 31624 | 32374 | 32374 | 34789 | 34789 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 37049 | 37049 | 43649
G2c.1740 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 5160 | 5160 | 12660 | 12778 | 16584 | 29295 | 30045 | 30045 | 32460 | 32460 | 33789 | 33789 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 36189 | 37049 | 37049 | 43649
G2c.1741 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 19359 | 19359 | 20265 | 23391 | 25838 | 43538 | 45956 | 45956 | 48016 | 99578 | 99578 | 129078 | 129702 | 129977 | 129977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977
G2c.1742 | I | [5 empty] | SOS - Start On Site | 15459 | 19359 | 20265 | 20265 | 23391 | 30138 | 45956 | 45956 | 45956 | 65956 | 99578 | 99578 | 129078 | 129977 | 129977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977 | 177977
G2c.1743 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 1320 | 11665 | 11665 | 12525 | 13236 | 14933 | 19283 | 24716 | 48556 | 61132 | 64178 | 85578 | 90750 | 124250 | 125702 | 125702 | 125702 | 173702 | 173702 | 173702 | 173702 | 173977 | 177977
G2c.1744 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 2226 | 2226 | 3086 | 11915 | 12626 | 17533 | 18401 | 24656 | 47556 | 64178 | 64178 | 84178 | 90750 | 124250 | 125187 | 125702 | 125702 | 173702 | 173702 | 173702 | 173702 | 177977
G2c.1745 | I | Number of WTW with increased capacity | Population Equivalent | O_WR8_G1 | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1746 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1747 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1748 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1749 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1750 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1751 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1752 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1753 | I | Number of resilience improvements via Water Efficiency campaigns | Number | O_WR8_G2 | MA087 | Baseline | G90 - Delivery Approval | 0 | 0 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1754 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1755 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1756 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1757 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1758 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1759 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1760 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G2c.1761 | I | Number of resilience improvements at rural supply hubs to provide capacity for new demand | Number | O_WR8_G3 | MA087 | Baseline | G90 - Delivery Approval | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 1120 | 1120 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.1762 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1763 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1764 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1765 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 1120 | 1120 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.1766 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 1120 | 1120 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.1767 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.1768 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 1121 | 1121 | 1121 | 1121 | 1121 | 1121
G2c.1769 | I | Number of tanker fill points installed | Number | O_WR8_G4 | MA087 | Baseline | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1770 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1771 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1772 | I | [5 empty] | G110 - Financial Closure | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1773 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1774 | I | [5 empty] | SOS - Start On Site | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1775 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1776 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1777 | I | Length of service relocations - water mains | Metres | O_WR9_G1 | MA065 | Baseline | G90 - Delivery Approval | 24983 | 25655 | 25757 | 25933 | 25938 | 30338 | 30339 | 30340 | 30340 | 30410 | 30440 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585
G2c.1778 | I | [5 empty] | SOS - Start On Site | 7972 | 7972 | 8317 | 8379 | 8386 | 12786 | 12786 | 12787 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792
G2c.1779 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1077 | 5078 | 7970 | 7971 | 8315 | 8377 | 12777 | 12778 | 12791 | 12791 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792
G2c.1780 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 1 | 1077 | 1077 | 1077 | 5079 | 8315 | 8377 | 12777 | 12778 | 12784 | 12791 | 12791 | 12791 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792 | 12792
G2c.1781 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 24983 | 25655 | 25757 | 25933 | 25938 | 30338 | 30339 | 30340 | 30340 | 30410 | 30440 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585
G2c.1782 | I | [5 empty] | SOS - Start On Site | 24982 | 24982 | 25754 | 25923 | 25933 | 30333 | 30333 | 30334 | 30335 | 30375 | 30410 | 30440 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585
G2c.1783 | I | [5 empty] | G100 - Acceptance | 0 | 1 | 1077 | 7970 | 7973 | 7973 | 7973 | 8401 | 25509 | 25669 | 25675 | 25755 | 25756 | 26032 | 30440 | 30775 | 30775 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585 | 31585
G2c.1784 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 1076 | 7972 | 7973 | 7973 | 7973 | 8083 | 12509 | 25669 | 25675 | 25686 | 26002 | 26002 | 30433 | 30440 | 30775 | 30775 | 30775 | 30775 | 30775 | 31585 | 31585 | 31585 | 31585
G2c.1785 | I | Number of WWTW secondary treatment asset interventions | Number | O_WW1_M13 | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1786 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1787 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1788 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1789 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1790 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.1791 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3
G2c.1792 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3
G2c.1793 | I | Number of WWTW inlet works asset interventions | Number | O_WW1_M9 | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1794 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1795 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1796 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1797 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1798 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.1799 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
G2c.1800 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G2c.1801 | I | Number of studies complete | Number | O_WW3_E | MA026 | Baseline | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1802 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1803 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1804 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1805 | I |  |  |  |  | Forecast Actual | G90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1806 | I | [5 empty] | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1807 | I | [5 empty] | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1808 | I | [5 empty] | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
SR10 Completion Projects |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1809 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1810 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1811 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1812 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1813 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1814 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1815 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1816 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1817 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1818 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1819 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1820 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1821 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1822 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1823 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1824 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1825 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1826 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1827 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1828 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1829 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1830 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1831 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1832 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1833 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1834 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1835 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1836 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1837 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1838 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1839 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1840 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1841 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1842 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1843 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1844 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1845 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1846 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1847 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1848 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1849 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1850 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1851 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1852 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1853 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1854 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1855 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1856 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1857 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1858 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1859 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1860 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1861 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1862 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1863 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1864 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1865 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1866 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1867 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1868 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1869 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1870 | I | [5 empty] | MS2 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1871 | I | [5 empty] | MS3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1872 | I | [5 empty] | MS4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1873 | I | [5 empty] | MS5 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1874 | I |  |  |  |  | Forecast Actual | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1875 | I | [5 empty] | MS2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1876 | I | [5 empty] | MS3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1877 | I | [5 empty] | MS4 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1878 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.1879 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1880 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1881 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1882 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1883 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1884 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1885 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1886 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1887 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1888 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1889 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1890 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1891 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1892 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1893 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1894 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1895 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1896 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1897 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1898 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1899 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1900 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1901 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1902 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1903 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1904 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1905 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1906 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1907 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1908 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1909 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1910 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1911 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1912 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1913 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1914 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1915 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1916 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1917 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1918 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1919 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1920 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1921 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1922 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1923 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1924 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1925 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1926 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1927 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1928 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1929 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1930 | I | [5 empty] | MS2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1931 | I | [5 empty] | MS3 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1932 | I | [5 empty] | MS4 | 6 | 6 | 22 | 26 | 26 | 26 | 26 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1933 | I | [5 empty] | MS5 | 0 | 4 | 4 | 20 | 24 | 24 | 24 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1934 | I |  |  |  |  | Forecast Actual | MS1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1935 | I | [5 empty] | MS2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1936 | I | [5 empty] | MS3 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1937 | I | [5 empty] | MS4 | 6 | 8 | 18 | 18 | 22 | 22 | 22 | 22 | 22 | 22 | 26 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.1938 | I | [5 empty] | MS5 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 20 | 20 | 24 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 28
G2c.1939 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1940 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1941 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1942 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1943 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1944 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1945 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1946 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1947 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1948 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1949 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1950 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1951 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1952 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1953 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1954 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1955 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1956 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1957 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1958 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1959 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1960 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1961 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1962 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1963 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1964 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1965 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1966 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1967 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1968 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1969 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1970 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1971 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1972 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1973 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1974 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1975 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1976 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1977 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1978 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.1979 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1980 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1981 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1982 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1983 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1984 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1985 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1986 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1987 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2
G2c.1988 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2
SR15 Completion Projects |  | 7: Number of Outputs
[8 empty] | Pre 2021-22 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | Post 2026-27
Line Ref | Field type | Output Description | Output Units | Output Code | Management Approach Reference(s) | Type | Gate |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
G2c.1989 | I | Number of water treatment works improved | No. | 1 |  | Committed List Baseline | MS1 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.1990 | I | [5 empty] | MS2 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G2c.1991 | I | [5 empty] | MS3 | 30 | 30 | 30 | 30 | 30 | 30 | 32 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1992 | I | [5 empty] | MS4 | 8 | 10 | 12 | 14 | 20 | 24 | 24 | 24 | 30 | 30 | 30 | 30 | 32 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1993 | I | [5 empty] | MS5 | 0 | 0 | 2 | 6 | 8 | 14 | 16 | 18 | 18 | 24 | 28 | 28 | 32 | 32 | 32 | 32 | 32 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
G2c.1994 | I |  |  |  |  | Forecast Actual | MS1 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1995 | I | [5 empty] | MS2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1996 | I | [5 empty] | MS3 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1997 | I | [5 empty] | MS4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1998 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 4 | 4 | 6 | 7 | 7 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11
G2c.1999 | I | Number of zones made compliant with iron & manganese standards | No. | 2 |  | Committed List Baseline | MS1 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2000 | I | [5 empty] | MS2 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2001 | I | [5 empty] | MS3 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2002 | I | [5 empty] | MS4 | 12 | 18 | 20 | 40 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2003 | I | [5 empty] | MS5 | 0 | 8 | 14 | 32 | 32 | 38 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2004 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2005 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2006 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2007 | I | [5 empty] | MS4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2008 | I | [5 empty] | MS5 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2009 | I | Improvements to reliability of drinking water (catchments and treatment) | No. | 3 |  | Committed List Baseline | MS1 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2010 | I | [5 empty] | MS2 | 44 | 46 | 48 | 48 | 48 | 48 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.2011 | I | [5 empty] | MS3 | 44 | 44 | 48 | 48 | 48 | 48 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2012 | I | [5 empty] | MS4 | 8 | 14 | 18 | 30 | 36 | 38 | 42 | 44 | 46 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2013 | I | [5 empty] | MS5 | 0 | 8 | 12 | 18 | 30 | 34 | 38 | 40 | 44 | 48 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2014 | I |  |  |  |  | Forecast Actual | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2015 | I | [5 empty] | MS2 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2016 | I | [5 empty] | MS3 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2017 | I | [5 empty] | MS4 | 3 | 6 | 7 | 8 | 9 | 9 | 9 | 10 | 10 | 13 | 13 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2018 | I | [5 empty] | MS5 | 0 | 1 | 2 | 3 | 6 | 7 | 7 | 7 | 7 | 9 | 12 | 12 | 14 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18
G2c.2019 | I | Improvements to reliability of drinking water (networks and storage) | No. | 4 |  | Committed List Baseline | MS1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.2020 | I | [5 empty] | MS2 | 38 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.2021 | I | [5 empty] | MS3 | 38 | 38 | 38 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2022 | I | [5 empty] | MS4 | 8 | 26 | 32 | 32 | 34 | 38 | 38 | 38 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2023 | I | [5 empty] | MS5 | 0 | 20 | 28 | 32 | 32 | 34 | 36 | 38 | 40 | 40 | 40 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
G2c.2024 | I |  |  |  |  | Forecast Actual | MS1 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.2025 | I | [5 empty] | MS2 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.2026 | I | [5 empty] | MS3 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.2027 | I | [5 empty] | MS4 | 2 | 11 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.2028 | I | [5 empty] | MS5 | 0 | 7 | 8 | 10 | 13 | 13 | 13 | 13 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G2c.2029 | I | Distribution mains cleaned (km) | km | 5 |  | Committed List Baseline | MS1 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076
G2c.2030 | I | [5 empty] | MS2 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076
G2c.2031 | I | [5 empty] | MS3 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076
G2c.2032 | I | [5 empty] | MS4 | 96.8 | 527.516 | 4831.864 | 4831.864 | 4831.864 | 4831.864 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076
G2c.2033 | I | [5 empty] | MS5 | 0 | 96.8 | 395.956 | 419.076 | 550.636 | 901.036 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076 | 5388.076
G2c.2034 | I |  |  |  |  | Forecast Actual | MS1 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.2035 | I | [5 empty] | MS2 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.2036 | I | [5 empty] | MS3 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.2037 | I | [5 empty] | MS4 | 48.4 | 48.4 | 289.38 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.2038 | I | [5 empty] | MS5 | 0 | 0 | 65.78 | 183.433 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633 | 358.633
G2c.2039 | I | Number of water quality etc studies to inform future periods | No. | 6 |  | Committed List Baseline | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2040 | I | [5 empty] | MS2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2041 | I | [5 empty] | MS3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2042 | I | [5 empty] | MS4 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2043 | I | [5 empty] | MS5 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2044 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2045 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2046 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2047 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2048 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2049 | I | 2010-15 outputs planned to complete in the 2015-21 period -DW | No. | 7 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2050 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2051 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2052 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2053 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2054 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2055 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2056 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2057 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2058 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2059 | I | Water supply resilience strategy and improvements made | No. | 8 |  | Committed List Baseline | MS1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2060 | I | [5 empty] | MS2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2061 | I | [5 empty] | MS3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2062 | I | [5 empty] | MS4 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2063 | I | [5 empty] | MS5 | 0 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2064 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2065 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2066 | I | [5 empty] | MS3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2067 | I | [5 empty] | MS4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2068 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2069 | I | Number of zones with improved security of supply (SOSI) | No. | 9 |  | Committed List Baseline | MS1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.2070 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.2071 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.2072 | I | [5 empty] | MS4 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.2073 | I | [5 empty] | MS5 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G2c.2074 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2075 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2076 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2077 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2078 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2079 | I | Number of security measures and improvements to the infrastructure of critical reservoirs | No. | 10 |  | Committed List Baseline | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2080 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2081 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2082 | I | [5 empty] | MS4 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2083 | I | [5 empty] | MS5 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2084 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2085 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2086 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2087 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2088 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2089 | I | Number of WWTWs improved to meet UWWTD | No. | 11 |  | Committed List Baseline | MS1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2090 | I | [5 empty] | MS2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2091 | I | [5 empty] | MS3 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2092 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2093 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2094 | I |  |  |  |  | Forecast Actual | MS1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2095 | I | [5 empty] | MS2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2096 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2097 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2098 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G2c.2099 | I | Number of waste water networks improved to meet UWWTD | No. | 12 |  | Committed List Baseline | MS1 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.2100 | I | [5 empty] | MS2 | 22 | 22 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.2101 | I | [5 empty] | MS3 | 22 | 22 | 22 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.2102 | I | [5 empty] | MS4 | 0 | 6 | 14 | 14 | 20 | 22 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.2103 | I | [5 empty] | MS5 | 0 | 0 | 6 | 14 | 14 | 14 | 22 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G2c.2104 | I |  |  |  |  | Forecast Actual | MS1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.2105 | I | [5 empty] | MS2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.2106 | I | [5 empty] | MS3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.2107 | I | [5 empty] | MS4 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.2108 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G2c.2109 | I | Number of improvements required to meet UWWTD - Glasgow completion | No. | 13 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2110 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2111 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2112 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2113 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2114 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2115 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2116 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2117 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2118 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2119 | I | Number of improvements required to meet the Water Framework Directive | No. | 14 |  | Committed List Baseline | MS1 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.2120 | I | [5 empty] | MS2 | 44 | 46 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G2c.2121 | I | [5 empty] | MS3 | 42 | 44 | 48 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2122 | I | [5 empty] | MS4 | 0 | 4 | 6 | 10 | 12 | 14 | 22 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2123 | I | [5 empty] | MS5 | 0 | 2 | 4 | 6 | 10 | 12 | 14 | 32 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
G2c.2124 | I |  |  |  |  | Forecast Actual | MS1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2125 | I | [5 empty] | MS2 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2126 | I | [5 empty] | MS3 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2127 | I | [5 empty] | MS4 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 9 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2128 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
G2c.2129 | I | Studies to inform requirements under the revised Bathing Waters Directive | No. | 15 |  | Committed List Baseline | MS1 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2130 | I | [5 empty] | MS2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2131 | I | [5 empty] | MS3 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2132 | I | [5 empty] | MS4 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2133 | I | [5 empty] | MS5 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
G2c.2134 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2135 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2136 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2137 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2138 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2139 | I | Number of environmental studies to inform future periods | No. | 16 |  | Committed List Baseline | MS1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2140 | I | [5 empty] | MS2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2141 | I | [5 empty] | MS3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2142 | I | [5 empty] | MS4 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2143 | I | [5 empty] | MS5 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G2c.2144 | I |  |  |  |  | Forecast Actual | MS1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2145 | I | [5 empty] | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2146 | I | [5 empty] | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2147 | I | [5 empty] | MS4 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2148 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G2c.2149 | I | Number of improvements required by the Compliance Assessment Scheme; odour reduction and sludge management | No. | 17 |  | Committed List Baseline | MS1 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.2150 | I | [5 empty] | MS2 | 84 | 84 | 84 | 84 | 84 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.2151 | I | [5 empty] | MS3 | 82 | 84 | 84 | 84 | 84 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.2152 | I | [5 empty] | MS4 | 6 | 6 | 62 | 82 | 84 | 84 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.2153 | I | [5 empty] | MS5 | 0 | 6 | 6 | 62 | 82 | 84 | 84 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86 | 86
G2c.2154 | I |  |  |  |  | Forecast Actual | MS1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.2155 | I | [5 empty] | MS2 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.2156 | I | [5 empty] | MS3 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G2c.2157 | I | [5 empty] | MS4 | 2 | 2 | 2 | 2 | 2 | 13 | 13 | 33 | 33 | 33 | 33 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40
G2c.2158 | I | [5 empty] | MS5 | 0 | 0 | 1 | 1 | 2 | 2 | 12 | 12 | 13 | 33 | 33 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40
G2c.2159 | I | 2010-15 outputs planned to complete in the 2015-21 period - WW | No. | 18 |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2160 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2161 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2162 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2163 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2164 | I |  |  |  |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2165 | I | [5 empty] | MS2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2166 | I | [5 empty] | MS3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2167 | I | [5 empty] | MS4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2c.2168 | I | [5 empty] | MS5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: |  | 5: Date:

## G3
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
Table G3: Number of needs or projects by milestone
Standards of Service |  |  |  |  | Confirmed on Committed List | [23 empty] | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.1 | I | 2: Baseline; 3: Gate 30 - Project Creation | 141 | 330 | 474 | 582 | 639 | 682 | 726 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 12 | 37 | 70 | 106 | 131 | 154 | 175 | 208 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 153 | 367 | 544 | 688 | 770 | 836 | 901 | 940 | 946 | 946 | 946 | 946 | 946 | 946 | 946 | 946 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948
G3.2 | I | 3: Gate 50 - Options Confirmed | 17 | 40 | 57 | 61 | 66 | 84 | 89 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 5 | 14 | 29 | 49 | 60 | 66 | 77 | 117 | 144 | 171 | 191 | 215 | 224 | 232 | 233 | 240 | 251 | 251 | 255 | 264 | 264 | 264 | 264 | 264 | 22 | 54 | 86 | 110 | 126 | 150 | 166 | 225 | 252 | 279 | 299 | 323 | 332 | 340 | 341 | 348 | 359 | 359 | 363 | 372 | 372 | 372 | 372 | 372
G3.3 | I | 3: Gate 70 - Option Selection | 59 | 85 | 125 | 142 | 166 | 202 | 219 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 1 | 11 | 21 | 30 | 33 | 46 | 59 | 76 | 114 | 154 | 175 | 208 | 249 | 262 | 268 | 273 | 282 | 289 | 297 | 308 | 309 | 309 | 309 | 310 | 60 | 96 | 146 | 172 | 199 | 248 | 278 | 319 | 357 | 397 | 418 | 451 | 492 | 505 | 511 | 516 | 525 | 532 | 540 | 551 | 552 | 552 | 552 | 553
G3.4 | I | 3: Gate 80 - Project Approval | 65 | 97 | 112 | 137 | 181 | 229 | 257 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 0 | 0 | 2 | 2 | 2 | 4 | 8 | 10 | 47 | 78 | 109 | 147 | 175 | 200 | 222 | 245 | 268 | 282 | 294 | 302 | 312 | 315 | 317 | 320 | 65 | 97 | 114 | 139 | 183 | 233 | 265 | 318 | 355 | 386 | 417 | 455 | 483 | 508 | 530 | 553 | 576 | 590 | 602 | 610 | 620 | 623 | 625 | 628
G3.5 | I |  |  | Gate 90 - Delivery Approval | 4 | 17 | 27 | 44 | 53 | 62 | 82 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 1000 | 1939 | 2863 | 4239 | 4473 | 5339 | 6779 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 75 | 109 | 143 | 174 | 194 | 209 | 231 | 246 | 264 | 286 | 294 | 306 | 314 | 319 | 324 | 1004 | 1956 | 2890 | 4283 | 4526 | 5401 | 6861 | 8368 | 8399 | 8443 | 8477 | 8511 | 8542 | 8562 | 8577 | 8599 | 8614 | 8632 | 8654 | 8662 | 8674 | 8682 | 8687 | 8692
G3.6 | I |  |  | SOS - Start on Site | 13 | 23 | 38 | 45 | 56 | 71 | 86 | 104 | 116 | 121 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 984 | 1874 | 2853 | 4283 | 4590 | 5542 | 7001 | 8464 | 8550 | 8571 | 8575 | 8575 | 8578 | 8580 | 8580 | 8581 | 8581 | 8582 | 8583 | 8583 | 8583 | 8583 | 8583 | 8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 1897 | 2891 | 4328 | 4646 | 5613 | 7087 | 8568 | 8666 | 8692 | 8699 | 8699 | 8702 | 8704 | 8704 | 8705 | 8705 | 8706 | 8707 | 8707 | 8707 | 8707 | 8707 | 8708
G3.7 | I |  |  | G100 - Project Acceptance | 47 | 89 | 119 | 144 | 164 | 182 | 197 | 204 | 211 | 227 | 238 | 255 | 269 | 275 | 288 | 292 | 293 | 294 | 294 | 297 | 298 | 298 | 298 | 298 | 1522 | 2509 | 3436 | 4380 | 5791 | 6105 | 7068 | 8538 | 10024 | 10094 | 10181 | 10234 | 10256 | 10271 | 10280 | 10286 | 10290 | 10296 | 10299 | 10303 | 10305 | 10307 | 10310 | 10335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569 | 2598 | 3555 | 4524 | 5955 | 6287 | 7265 | 8742 | 10235 | 10321 | 10419 | 10489 | 10525 | 10546 | 10568 | 10578 | 10583 | 10590 | 10593 | 10600 | 10603 | 10605 | 10608 | 10633
G3.8 | I |  |  | G110 - Financial Closure | 4 | 4 | 32 | 68 | 103 | 138 | 170 | 191 | 211 | 226 | 232 | 243 | 257 | 270 | 283 | 297 | 304 | 316 | 320 | 321 | 322 | 322 | 325 | 326 | 1464 | 2432 | 3356 | 4250 | 5641 | 5927 | 6902 | 8379 | 9860 | 9990 | 10120 | 10214 | 10286 | 10323 | 10344 | 10358 | 10366 | 10370 | 10375 | 10380 | 10386 | 10388 | 10389 | 10414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1468 | 2436 | 3388 | 4318 | 5744 | 6065 | 7072 | 8570 | 10071 | 10216 | 10352 | 10457 | 10543 | 10593 | 10627 | 10655 | 10670 | 10686 | 10695 | 10701 | 10708 | 10710 | 10714 | 10740
G3.9 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 141 | 330 | 474 | 582 | 639 | 682 | 726 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 732 | 12 | 37 | 70 | 106 | 131 | 154 | 175 | 208 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 214 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 153 | 367 | 544 | 688 | 770 | 836 | 901 | 940 | 946 | 946 | 946 | 946 | 946 | 946 | 946 | 946 | 948 | 948 | 948 | 948 | 948 | 948 | 948 | 948
G3.10 | I | 3: Gate 50 - Options Confirmed | 17 | 40 | 57 | 61 | 66 | 84 | 89 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 5 | 14 | 29 | 49 | 60 | 66 | 77 | 117 | 144 | 171 | 191 | 215 | 224 | 232 | 233 | 240 | 251 | 251 | 255 | 264 | 264 | 264 | 264 | 264 | 22 | 54 | 86 | 110 | 126 | 150 | 166 | 225 | 252 | 279 | 299 | 323 | 332 | 340 | 341 | 348 | 359 | 359 | 363 | 372 | 372 | 372 | 372 | 372
G3.11 | I | 3: Gate 70 - Option Selection | 59 | 85 | 125 | 142 | 166 | 202 | 219 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 243 | 1 | 11 | 21 | 30 | 33 | 46 | 59 | 76 | 114 | 154 | 175 | 208 | 249 | 262 | 268 | 273 | 282 | 289 | 297 | 308 | 309 | 309 | 309 | 310 | 60 | 96 | 146 | 172 | 199 | 248 | 278 | 319 | 357 | 397 | 418 | 451 | 492 | 505 | 511 | 516 | 525 | 532 | 540 | 551 | 552 | 552 | 552 | 553
G3.12 | I | 3: Gate 80 - Project Approval | 65 | 97 | 112 | 137 | 181 | 229 | 257 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 308 | 0 | 0 | 2 | 2 | 2 | 4 | 8 | 10 | 47 | 78 | 109 | 147 | 175 | 200 | 222 | 245 | 268 | 282 | 294 | 302 | 312 | 315 | 317 | 320 | 65 | 97 | 114 | 139 | 183 | 233 | 265 | 318 | 355 | 386 | 417 | 455 | 483 | 508 | 530 | 553 | 576 | 590 | 602 | 610 | 620 | 623 | 625 | 628
G3.13 | I |  |  | Gate 90 - Delivery Approval | 4 | 17 | 27 | 44 | 53 | 62 | 82 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 107 | 1000 | 1939 | 2863 | 4239 | 4473 | 5339 | 6779 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 8261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 75 | 109 | 143 | 174 | 194 | 209 | 231 | 246 | 264 | 286 | 294 | 306 | 314 | 319 | 324 | 1004 | 1956 | 2890 | 4283 | 4526 | 5401 | 6861 | 8368 | 8399 | 8443 | 8477 | 8511 | 8542 | 8562 | 8577 | 8599 | 8614 | 8632 | 8654 | 8662 | 8674 | 8682 | 8687 | 8692
G3.14 | I |  |  | SOS - Start on Site | 13 | 23 | 36 | 49 | 58 | 73 | 86 | 111 | 118 | 121 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 1000 | 1872 | 2812 | 4233 | 4477 | 5388 | 6841 | 8346 | 8425 | 8482 | 8505 | 8510 | 8526 | 8530 | 8530 | 8530 | 8543 | 8544 | 8548 | 8548 | 8548 | 8548 | 8549 | 8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 53 | 72 | 107 | 141 | 174 | 193 | 209 | 228 | 244 | 264 | 287 | 295 | 306 | 314 | 320 | 1013 | 1895 | 2848 | 4282 | 4535 | 5461 | 6927 | 8457 | 8558 | 8656 | 8701 | 8741 | 8791 | 8828 | 8847 | 8863 | 8895 | 8912 | 8936 | 8959 | 8967 | 8978 | 8987 | 8993
G3.15 | I |  |  | G100 - Project Acceptance | 38 | 71 | 94 | 121 | 128 | 143 | 161 | 189 | 206 | 225 | 246 | 259 | 271 | 283 | 286 | 289 | 292 | 292 | 296 | 297 | 297 | 298 | 298 | 298 | 621 | 1519 | 2398 | 2960 | 4096 | 4716 | 5582 | 6781 | 9655 | 9783 | 10008 | 10090 | 10177 | 10223 | 10244 | 10256 | 10271 | 10283 | 10298 | 10301 | 10304 | 10307 | 10311 | 10340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 8 | 17 | 26 | 44 | 61 | 79 | 109 | 131 | 154 | 177 | 196 | 221 | 235 | 256 | 659 | 1590 | 2492 | 3081 | 4224 | 4859 | 5743 | 6970 | 9862 | 10010 | 10262 | 10366 | 10474 | 10550 | 10591 | 10624 | 10672 | 10706 | 10748 | 10775 | 10797 | 10826 | 10844 | 10894
G3.16 | I |  |  | G110 - Financial Closure | 4 | 14 | 45 | 101 | 114 | 128 | 146 | 192 | 195 | 220 | 244 | 261 | 281 | 289 | 297 | 307 | 313 | 318 | 320 | 322 | 325 | 325 | 325 | 326 | 598 | 1415 | 2279 | 2821 | 3928 | 4540 | 5425 | 6608 | 9459 | 9587 | 9783 | 9933 | 10075 | 10171 | 10254 | 10301 | 10325 | 10343 | 10352 | 10369 | 10377 | 10381 | 10383 | 10412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 14 | 26 | 37 | 46 | 67 | 88 | 119 | 135 | 162 | 183 | 204 | 225 | 602 | 1429 | 2324 | 2922 | 4042 | 4668 | 5571 | 6800 | 9655 | 9808 | 10029 | 10199 | 10370 | 10486 | 10588 | 10654 | 10705 | 10749 | 10791 | 10826 | 10864 | 10889 | 10912 | 10963
G3.17 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.18 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Asset Maintenance |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.19 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.20 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.21 | I | 3: Gate 70 - Option Selection | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.22 | I | 3: Gate 80 - Project Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.23 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.24 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.25 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.26 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.27 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.28 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.29 | I | 3: Gate 70 - Option Selection | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.30 | I | 3: Gate 80 - Project Approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.31 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.32 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.33 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.34 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.35 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.36 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supporting Sustainable Economic Growth |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.37 | I | 2: Baseline; 3: Gate 30 - Project Creation | 2 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 5 | 11 | 15 | 16 | 16 | 16 | 21 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 3 | 11 | 18 | 22 | 23 | 24 | 24 | 29 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G3.38 | I | 3: Gate 50 - Options Confirmed | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 10 | 17 | 18 | 21 | 26 | 29 | 31 | 39 | 44 | 48 | 50 | 50 | 51 | 54 | 58 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 0 | 5 | 12 | 19 | 20 | 24 | 29 | 32 | 34 | 42 | 47 | 51 | 53 | 53 | 54 | 57 | 61 | 62 | 62 | 62 | 62 | 62 | 62 | 62
G3.39 | I | 3: Gate 70 - Option Selection | 3 | 12 | 16 | 20 | 29 | 32 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 2 | 2 | 10 | 11 | 14 | 14 | 17 | 19 | 25 | 33 | 39 | 46 | 50 | 55 | 56 | 57 | 57 | 59 | 61 | 65 | 65 | 65 | 65 | 65 | 5 | 14 | 26 | 31 | 43 | 46 | 51 | 54 | 60 | 68 | 74 | 81 | 85 | 90 | 91 | 92 | 92 | 94 | 96 | 100 | 100 | 100 | 100 | 100
G3.40 | I | 3: Gate 80 - Project Approval | 4 | 12 | 22 | 27 | 30 | 40 | 43 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 9 | 17 | 29 | 33 | 43 | 46 | 50 | 58 | 61 | 66 | 66 | 68 | 69 | 72 | 73 | 74 | 4 | 12 | 22 | 28 | 32 | 42 | 45 | 51 | 57 | 65 | 77 | 81 | 91 | 94 | 98 | 106 | 109 | 114 | 114 | 116 | 117 | 120 | 121 | 122
G3.41 | I |  |  | Gate 90 - Delivery Approval | 0 | 2 | 3 | 5 | 8 | 9 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 18 | 27 | 33 | 41 | 51 | 57 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 20 | 26 | 40 | 44 | 49 | 53 | 56 | 59 | 63 | 65 | 67 | 69 | 71 | 72 | 6 | 20 | 30 | 38 | 49 | 60 | 68 | 80 | 85 | 86 | 100 | 106 | 120 | 124 | 129 | 133 | 136 | 139 | 143 | 145 | 147 | 149 | 151 | 152
G3.42 | I |  |  | SOS - Start on Site | 2 | 4 | 5 | 6 | 7 | 8 | 11 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 4 | 17 | 20 | 28 | 40 | 49 | 55 | 69 | 69 | 69 | 69 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 21 | 25 | 34 | 47 | 57 | 66 | 82 | 83 | 85 | 86 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
G3.43 | I |  |  | G100 - Project Acceptance | 4 | 8 | 12 | 21 | 24 | 28 | 28 | 30 | 32 | 35 | 36 | 38 | 41 | 46 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 10 | 12 | 16 | 23 | 28 | 36 | 46 | 52 | 62 | 73 | 75 | 75 | 79 | 80 | 81 | 81 | 82 | 83 | 83 | 83 | 83 | 83 | 84 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 20 | 28 | 44 | 52 | 64 | 74 | 82 | 94 | 108 | 111 | 113 | 120 | 126 | 128 | 129 | 130 | 131 | 131 | 131 | 131 | 131 | 132 | 133
G3.44 | I |  |  | G110 - Financial Closure | 0 | 0 | 2 | 6 | 8 | 12 | 19 | 23 | 27 | 28 | 30 | 32 | 36 | 38 | 40 | 43 | 48 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 9 | 13 | 16 | 20 | 26 | 30 | 38 | 49 | 57 | 63 | 72 | 78 | 79 | 82 | 86 | 87 | 88 | 88 | 89 | 89 | 89 | 89 | 90 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 13 | 18 | 26 | 34 | 42 | 57 | 72 | 84 | 91 | 102 | 110 | 115 | 120 | 126 | 130 | 136 | 137 | 139 | 139 | 139 | 139 | 140 | 141
G3.45 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 2 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 5 | 11 | 15 | 16 | 16 | 16 | 21 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 3 | 11 | 18 | 22 | 23 | 24 | 24 | 29 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
G3.46 | I | 3: Gate 50 - Options Confirmed | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 10 | 17 | 18 | 21 | 26 | 29 | 31 | 39 | 44 | 48 | 50 | 50 | 51 | 54 | 58 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 0 | 5 | 12 | 19 | 20 | 24 | 29 | 32 | 34 | 42 | 47 | 51 | 53 | 53 | 54 | 57 | 61 | 62 | 62 | 62 | 62 | 62 | 62 | 62
G3.47 | I | 3: Gate 70 - Option Selection | 3 | 12 | 16 | 20 | 29 | 32 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 2 | 2 | 10 | 11 | 14 | 14 | 17 | 19 | 25 | 33 | 39 | 46 | 50 | 55 | 56 | 57 | 57 | 59 | 61 | 65 | 65 | 65 | 65 | 65 | 5 | 14 | 26 | 31 | 43 | 46 | 51 | 54 | 60 | 68 | 74 | 81 | 85 | 90 | 91 | 92 | 92 | 94 | 96 | 100 | 100 | 100 | 100 | 100
G3.48 | I | 3: Gate 80 - Project Approval | 4 | 12 | 22 | 27 | 30 | 40 | 43 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 9 | 17 | 29 | 33 | 43 | 46 | 50 | 58 | 61 | 66 | 66 | 68 | 69 | 72 | 73 | 74 | 4 | 12 | 22 | 28 | 32 | 42 | 45 | 51 | 57 | 65 | 77 | 81 | 91 | 94 | 98 | 106 | 109 | 114 | 114 | 116 | 117 | 120 | 121 | 122
G3.49 | I |  |  | Gate 90 - Delivery Approval | 0 | 2 | 3 | 5 | 8 | 9 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 18 | 27 | 33 | 41 | 51 | 57 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 20 | 26 | 40 | 44 | 49 | 53 | 56 | 59 | 63 | 65 | 67 | 69 | 71 | 72 | 6 | 20 | 30 | 38 | 49 | 60 | 68 | 80 | 85 | 86 | 100 | 106 | 120 | 124 | 129 | 133 | 136 | 139 | 143 | 145 | 147 | 149 | 151 | 152
G3.50 | I |  |  | SOS - Start on Site | 2 | 3 | 5 | 7 | 9 | 11 | 13 | 14 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 4 | 18 | 21 | 29 | 38 | 49 | 53 | 67 | 69 | 69 | 69 | 69 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 7 | 19 | 32 | 39 | 44 | 47 | 54 | 56 | 59 | 63 | 65 | 67 | 69 | 71 | 6 | 21 | 26 | 36 | 47 | 60 | 66 | 81 | 86 | 90 | 93 | 105 | 119 | 126 | 131 | 134 | 141 | 143 | 146 | 150 | 152 | 154 | 156 | 158
G3.51 | I |  |  | G100 - Project Acceptance | 3 | 5 | 8 | 15 | 16 | 17 | 19 | 24 | 29 | 31 | 33 | 36 | 41 | 45 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 3 | 7 | 10 | 14 | 17 | 19 | 25 | 32 | 46 | 59 | 64 | 66 | 76 | 82 | 83 | 83 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 9 | 19 | 24 | 27 | 34 | 37 | 42 | 49 | 53 | 6 | 12 | 18 | 29 | 33 | 36 | 44 | 56 | 75 | 90 | 97 | 102 | 117 | 131 | 137 | 140 | 152 | 157 | 160 | 167 | 170 | 175 | 182 | 187
G3.52 | I |  |  | G110 - Financial Closure | 0 | 1 | 3 | 10 | 10 | 12 | 15 | 20 | 23 | 30 | 31 | 33 | 38 | 42 | 46 | 47 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 2 | 7 | 10 | 15 | 17 | 22 | 22 | 29 | 35 | 49 | 62 | 66 | 74 | 78 | 84 | 87 | 89 | 89 | 89 | 89 | 90 | 90 | 90 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 9 | 15 | 22 | 24 | 29 | 37 | 41 | 47 | 2 | 8 | 13 | 25 | 27 | 34 | 37 | 49 | 58 | 79 | 93 | 99 | 112 | 120 | 133 | 139 | 148 | 154 | 161 | 163 | 169 | 177 | 181 | 189
G3.53 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.54 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Circular Economy |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.55 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.56 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.57 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.58 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.59 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.60 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.61 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.62 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.63 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.64 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.65 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.66 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.67 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.68 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.69 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.70 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.71 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.72 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drinking Water |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.73 | I | 2: Baseline; 3: Gate 30 - Project Creation | 7 | 9 | 12 | 13 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 3 | 5 | 20 | 32 | 35 | 38 | 39 | 45 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 10 | 14 | 32 | 45 | 51 | 55 | 56 | 62 | 63 | 63 | 63 | 63 | 63 | 64 | 64 | 64 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G3.74 | I | 3: Gate 50 - Options Confirmed | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 6 | 7 | 9 | 13 | 18 | 22 | 30 | 36 | 37 | 40 | 50 | 53 | 53 | 54 | 61 | 61 | 62 | 65 | 65 | 66 | 66 | 66 | 2 | 3 | 9 | 10 | 13 | 17 | 22 | 26 | 34 | 40 | 41 | 44 | 54 | 57 | 57 | 58 | 65 | 65 | 66 | 69 | 69 | 70 | 70 | 70
G3.75 | I | 3: Gate 70 - Option Selection | 1 | 3 | 3 | 4 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 1 | 2 | 2 | 3 | 3 | 3 | 8 | 11 | 19 | 27 | 32 | 37 | 41 | 45 | 51 | 53 | 59 | 61 | 63 | 67 | 68 | 68 | 68 | 69 | 2 | 5 | 5 | 7 | 9 | 11 | 17 | 20 | 28 | 36 | 41 | 46 | 50 | 54 | 60 | 62 | 68 | 70 | 72 | 76 | 77 | 77 | 77 | 78
G3.76 | I | 3: Gate 80 - Project Approval | 1 | 2 | 2 | 3 | 5 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 8 | 13 | 18 | 24 | 31 | 36 | 41 | 43 | 49 | 59 | 60 | 61 | 62 | 63 | 64 | 1 | 2 | 2 | 3 | 5 | 7 | 11 | 12 | 15 | 18 | 23 | 28 | 34 | 41 | 46 | 51 | 53 | 59 | 69 | 70 | 71 | 72 | 73 | 74
G3.77 | I |  |  | Gate 90 - Delivery Approval | 2 | 2 | 3 | 4 | 7 | 7 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 9 | 11 | 13 | 16 | 22 | 26 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 15 | 19 | 23 | 27 | 33 | 36 | 41 | 47 | 51 | 52 | 53 | 53 | 53 | 8 | 11 | 14 | 17 | 23 | 29 | 37 | 47 | 51 | 52 | 56 | 62 | 66 | 70 | 74 | 80 | 83 | 88 | 94 | 98 | 99 | 100 | 100 | 100
G3.78 | I |  |  | SOS - Start on Site | 1 | 1 | 1 | 2 | 5 | 7 | 8 | 13 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 1 | 9 | 15 | 17 | 26 | 27 | 29 | 39 | 41 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 16 | 19 | 31 | 34 | 37 | 52 | 55 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
G3.79 | I |  |  | G100 - Project Acceptance | 0 | 1 | 2 | 2 | 4 | 5 | 7 | 11 | 14 | 14 | 16 | 17 | 18 | 22 | 22 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 7 | 9 | 16 | 20 | 23 | 25 | 34 | 36 | 39 | 42 | 45 | 49 | 50 | 50 | 51 | 51 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 10 | 18 | 22 | 27 | 30 | 41 | 47 | 53 | 56 | 61 | 66 | 68 | 72 | 73 | 73 | 75 | 76 | 76 | 77 | 77 | 77 | 77 | 83
G3.80 | I |  |  | G110 - Financial Closure | 1 | 1 | 1 | 2 | 3 | 4 | 4 | 4 | 5 | 9 | 14 | 16 | 16 | 18 | 20 | 20 | 24 | 24 | 24 | 24 | 25 | 25 | 26 | 26 | 3 | 8 | 14 | 16 | 20 | 21 | 26 | 29 | 37 | 39 | 42 | 44 | 50 | 51 | 51 | 51 | 52 | 52 | 54 | 54 | 54 | 54 | 54 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 15 | 18 | 23 | 25 | 30 | 33 | 42 | 48 | 56 | 60 | 66 | 69 | 71 | 71 | 76 | 76 | 78 | 78 | 79 | 79 | 80 | 86
G3.81 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 7 | 9 | 12 | 13 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 3 | 5 | 20 | 32 | 35 | 38 | 39 | 45 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 10 | 14 | 32 | 45 | 51 | 55 | 56 | 62 | 63 | 63 | 63 | 63 | 63 | 64 | 64 | 64 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
G3.82 | I | 3: Gate 50 - Options Confirmed | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 6 | 7 | 9 | 13 | 18 | 22 | 30 | 36 | 37 | 40 | 50 | 53 | 53 | 54 | 61 | 61 | 62 | 65 | 65 | 66 | 66 | 66 | 2 | 3 | 9 | 10 | 13 | 17 | 22 | 26 | 34 | 40 | 41 | 44 | 54 | 57 | 57 | 58 | 65 | 65 | 66 | 69 | 69 | 70 | 70 | 70
G3.83 | I | 3: Gate 70 - Option Selection | 1 | 3 | 3 | 4 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 1 | 2 | 2 | 3 | 3 | 3 | 8 | 11 | 19 | 27 | 32 | 37 | 41 | 45 | 51 | 53 | 59 | 61 | 63 | 67 | 68 | 68 | 68 | 69 | 2 | 5 | 5 | 7 | 9 | 11 | 17 | 20 | 28 | 36 | 41 | 46 | 50 | 54 | 60 | 62 | 68 | 70 | 72 | 76 | 77 | 77 | 77 | 78
G3.84 | I | 3: Gate 80 - Project Approval | 1 | 2 | 2 | 3 | 5 | 7 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 8 | 13 | 18 | 24 | 31 | 36 | 41 | 43 | 49 | 59 | 60 | 61 | 62 | 63 | 64 | 1 | 2 | 2 | 3 | 5 | 7 | 11 | 12 | 15 | 18 | 23 | 28 | 34 | 41 | 46 | 51 | 53 | 59 | 69 | 70 | 71 | 72 | 73 | 74
G3.85 | I |  |  | Gate 90 - Delivery Approval | 2 | 2 | 3 | 4 | 7 | 7 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 6 | 9 | 11 | 13 | 16 | 22 | 26 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 15 | 19 | 23 | 27 | 33 | 36 | 41 | 47 | 51 | 52 | 53 | 53 | 53 | 8 | 11 | 14 | 17 | 23 | 29 | 37 | 47 | 51 | 52 | 56 | 62 | 66 | 70 | 74 | 80 | 83 | 88 | 94 | 98 | 99 | 100 | 100 | 100
G3.86 | I |  |  | SOS - Start on Site | 1 | 2 | 2 | 4 | 6 | 7 | 9 | 13 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 1 | 8 | 15 | 17 | 23 | 28 | 30 | 41 | 41 | 42 | 42 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 10 | 18 | 19 | 23 | 27 | 33 | 36 | 44 | 47 | 51 | 52 | 53 | 53 | 2 | 10 | 17 | 21 | 29 | 35 | 39 | 54 | 59 | 61 | 62 | 68 | 77 | 78 | 82 | 86 | 92 | 95 | 103 | 106 | 110 | 111 | 112 | 112
G3.87 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 7 | 11 | 16 | 18 | 21 | 21 | 21 | 21 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 3 | 5 | 10 | 12 | 14 | 15 | 18 | 26 | 30 | 38 | 44 | 49 | 50 | 52 | 53 | 54 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 8 | 10 | 11 | 12 | 15 | 17 | 19 | 24 | 29 | 3 | 5 | 10 | 13 | 15 | 16 | 19 | 31 | 37 | 49 | 60 | 67 | 72 | 75 | 78 | 83 | 89 | 90 | 91 | 94 | 96 | 98 | 103 | 112
G3.88 | I |  |  | G110 - Financial Closure | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 6 | 8 | 13 | 19 | 22 | 23 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 25 | 1 | 3 | 9 | 11 | 11 | 13 | 17 | 23 | 28 | 30 | 35 | 41 | 47 | 51 | 51 | 53 | 55 | 55 | 55 | 57 | 57 | 57 | 57 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 7 | 8 | 10 | 12 | 14 | 16 | 18 | 22 | 1 | 5 | 11 | 14 | 14 | 16 | 20 | 26 | 32 | 36 | 43 | 54 | 67 | 74 | 75 | 80 | 85 | 86 | 90 | 94 | 96 | 98 | 100 | 108
G3.89 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.90 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Environment |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.91 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 9 | 12 | 12 | 12 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 3 | 3 | 4 | 7 | 7 | 7 | 7 | 8 | 12 | 15 | 15 | 15 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
G3.92 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 9 | 9 | 10 | 15 | 19 | 22 | 22 | 22 | 31 | 32 | 32 | 32 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 9 | 9 | 10 | 15 | 19 | 22 | 22 | 22 | 31 | 32 | 32 | 32 | 32
G3.93 | I | 3: Gate 70 - Option Selection | 3 | 4 | 5 | 9 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 8 | 10 | 11 | 12 | 13 | 18 | 23 | 23 | 33 | 34 | 34 | 34 | 34 | 3 | 4 | 5 | 9 | 15 | 15 | 15 | 17 | 18 | 18 | 19 | 23 | 25 | 26 | 27 | 28 | 33 | 38 | 38 | 48 | 49 | 49 | 49 | 49
G3.94 | I | 3: Gate 80 - Project Approval | 3 | 4 | 10 | 14 | 16 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 5 | 6 | 6 | 7 | 7 | 9 | 14 | 14 | 19 | 22 | 23 | 23 | 25 | 31 | 4 | 5 | 11 | 15 | 17 | 20 | 23 | 23 | 25 | 27 | 27 | 28 | 28 | 29 | 29 | 31 | 36 | 36 | 41 | 44 | 45 | 45 | 47 | 53
G3.95 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 6 | 14 | 19 | 20 | 25 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 6 | 7 | 7 | 9 | 11 | 11 | 19 | 22 | 22 | 22 | 23 | 23 | 4 | 6 | 14 | 20 | 21 | 26 | 30 | 31 | 31 | 32 | 35 | 37 | 37 | 38 | 38 | 40 | 42 | 42 | 50 | 53 | 53 | 53 | 54 | 54
G3.96 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 16 | 24 | 28 | 31 | 34 | 39 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 16 | 24 | 28 | 32 | 35 | 40 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44
G3.97 | I |  |  | G100 - Project Acceptance | 1 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 13 | 17 | 25 | 27 | 36 | 39 | 41 | 45 | 47 | 51 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 21 | 26 | 34 | 37 | 46 | 49 | 51 | 55 | 57 | 63 | 64 | 64 | 65 | 65 | 65 | 65 | 66 | 66 | 66 | 66 | 66 | 66 | 66
G3.98 | I |  |  | G110 - Financial Closure | 0 | 0 | 2 | 3 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 7 | 7 | 10 | 13 | 23 | 24 | 31 | 35 | 42 | 46 | 49 | 50 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 12 | 16 | 33 | 35 | 42 | 47 | 54 | 58 | 61 | 62 | 66 | 68 | 69 | 69 | 69 | 69 | 69 | 69 | 70 | 70 | 70 | 70
G3.99 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 9 | 12 | 12 | 12 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 3 | 3 | 4 | 7 | 7 | 7 | 7 | 8 | 12 | 15 | 15 | 15 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
G3.100 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 9 | 9 | 10 | 15 | 19 | 22 | 22 | 22 | 31 | 32 | 32 | 32 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 5 | 9 | 9 | 10 | 15 | 19 | 22 | 22 | 22 | 31 | 32 | 32 | 32 | 32
G3.101 | I | 3: Gate 70 - Option Selection | 3 | 4 | 5 | 9 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 8 | 10 | 11 | 12 | 13 | 18 | 23 | 23 | 33 | 34 | 34 | 34 | 34 | 3 | 4 | 5 | 9 | 15 | 15 | 15 | 17 | 18 | 18 | 19 | 23 | 25 | 26 | 27 | 28 | 33 | 38 | 38 | 48 | 49 | 49 | 49 | 49
G3.102 | I | 3: Gate 80 - Project Approval | 3 | 4 | 10 | 14 | 16 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 5 | 5 | 6 | 6 | 7 | 7 | 9 | 14 | 14 | 19 | 22 | 23 | 23 | 25 | 31 | 4 | 5 | 11 | 15 | 17 | 20 | 23 | 23 | 25 | 27 | 27 | 28 | 28 | 29 | 29 | 31 | 36 | 36 | 41 | 44 | 45 | 45 | 47 | 53
G3.103 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 6 | 14 | 19 | 20 | 25 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 6 | 7 | 7 | 9 | 11 | 11 | 19 | 22 | 22 | 22 | 23 | 23 | 4 | 6 | 14 | 20 | 21 | 26 | 30 | 31 | 31 | 32 | 35 | 37 | 37 | 38 | 38 | 40 | 42 | 42 | 50 | 53 | 53 | 53 | 54 | 54
G3.104 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 12 | 21 | 26 | 30 | 34 | 38 | 40 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 6 | 6 | 7 | 8 | 10 | 11 | 12 | 19 | 22 | 22 | 22 | 23 | 9 | 12 | 21 | 27 | 31 | 35 | 39 | 42 | 43 | 45 | 46 | 48 | 51 | 51 | 52 | 53 | 55 | 56 | 57 | 64 | 67 | 67 | 67 | 68
G3.105 | I |  |  | G100 - Project Acceptance | 1 | 3 | 3 | 5 | 6 | 6 | 9 | 10 | 10 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 7 | 10 | 14 | 17 | 21 | 26 | 30 | 33 | 38 | 46 | 48 | 51 | 52 | 52 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 4 | 5 | 7 | 8 | 10 | 10 | 18 | 8 | 13 | 17 | 22 | 27 | 32 | 39 | 43 | 48 | 57 | 60 | 63 | 64 | 66 | 70 | 70 | 70 | 71 | 72 | 74 | 75 | 77 | 77 | 85
G3.106 | I |  |  | G110 - Financial Closure | 0 | 0 | 1 | 6 | 7 | 7 | 8 | 11 | 11 | 12 | 12 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 3 | 6 | 9 | 12 | 17 | 19 | 26 | 30 | 35 | 39 | 46 | 50 | 52 | 53 | 54 | 55 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 4 | 6 | 8 | 10 | 10 | 2 | 3 | 7 | 15 | 19 | 24 | 27 | 37 | 41 | 47 | 51 | 60 | 64 | 66 | 67 | 72 | 73 | 74 | 75 | 75 | 77 | 79 | 81 | 81
G3.107 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.108 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flooding and Surface Water Management |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.109 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.110 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.111 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.112 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.113 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.114 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.115 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.116 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.117 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.118 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.119 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.120 | I | 3: Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.121 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.122 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.123 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.124 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.125 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.126 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Security & Resilience |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.127 | I | 2: Baseline; 3: Gate 30 - Project Creation | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 1 | 2 | 4 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 3 | 10 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G3.128 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G3.129 | I | 3: Gate 70 - Option Selection | 0 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 1 | 4 | 4 | 4 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 2 | 5 | 10 | 10 | 10 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G3.130 | I | 3: Gate 80 - Project Approval | 0 | 0 | 1 | 2 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 1 | 2 | 5 | 5 | 5 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G3.131 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 8 | 10 | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 4 | 4 | 8 | 10 | 11 | 12 | 15 | 18 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G3.132 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 7 | 11 | 11 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 7 | 11 | 12 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G3.133 | I |  |  | G100 - Project Acceptance | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 9 | 11 | 11 | 11 | 12 | 14 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 16 | 16 | 16 | 17 | 19 | 22 | 22 | 23 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 27
G3.134 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 9 | 11 | 11 | 11 | 11 | 12 | 14 | 16 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 11 | 11 | 16 | 16 | 17 | 19 | 21 | 22 | 23 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27
G3.135 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 1 | 2 | 4 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 3 | 10 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G3.136 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
G3.137 | I | 3: Gate 70 - Option Selection | 0 | 2 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 1 | 4 | 4 | 4 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 2 | 5 | 10 | 10 | 10 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G3.138 | I | 3: Gate 80 - Project Approval | 0 | 0 | 1 | 2 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 1 | 2 | 5 | 5 | 5 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G3.139 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 8 | 10 | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 4 | 4 | 8 | 10 | 11 | 12 | 15 | 18 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
G3.140 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 5 | 7 | 9 | 10 | 10 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 4 | 5 | 7 | 9 | 10 | 11 | 14 | 16 | 19 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
G3.141 | I |  |  | G100 - Project Acceptance | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 7 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 7 | 13 | 15 | 16 | 16 | 17 | 17 | 18 | 21 | 25 | 25 | 25 | 25 | 27 | 28 | 32 | 32 | 34 | 34 | 34 | 34 | 34 | 34
G3.142 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 7 | 9 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 17 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 5 | 5 | 6 | 7 | 7 | 7 | 2 | 7 | 9 | 15 | 16 | 16 | 16 | 17 | 17 | 19 | 19 | 24 | 24 | 25 | 26 | 26 | 26 | 27 | 30 | 32 | 33 | 34 | 34 | 34
G3.143 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.144 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate Change, Adaptation and Mitigation |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.145 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G3.146 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G3.147 | I | 3: Gate 70 - Option Selection | 2 | 6 | 14 | 16 | 24 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 2 | 9 | 17 | 19 | 27 | 32 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G3.148 | I | 3: Gate 80 - Project Approval | 2 | 4 | 5 | 14 | 23 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 2 | 4 | 5 | 14 | 23 | 28 | 29 | 29 | 31 | 35 | 35 | 35 | 36 | 36 | 36 | 37 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40
G3.149 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 7 | 9 | 17 | 24 | 31 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 5 | 7 | 9 | 17 | 24 | 31 | 33 | 35 | 37 | 42 | 42 | 42 | 43 | 43 | 43 | 44 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47
G3.150 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 4 | 4 | 13 | 17 | 23 | 29 | 32 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 13 | 17 | 23 | 29 | 33 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
G3.151 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 7 | 8 | 11 | 14 | 20 | 22 | 22 | 24 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 7 | 8 | 11 | 14 | 20 | 22 | 23 | 25 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 38
G3.152 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 7 | 8 | 12 | 14 | 18 | 22 | 22 | 24 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 4 | 7 | 8 | 12 | 14 | 18 | 22 | 22 | 24 | 25 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G3.153 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G3.154 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
G3.155 | I | 3: Gate 70 - Option Selection | 2 | 6 | 14 | 16 | 24 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 2 | 9 | 17 | 19 | 27 | 32 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
G3.156 | I | 3: Gate 80 - Project Approval | 2 | 4 | 5 | 14 | 23 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 2 | 4 | 5 | 14 | 23 | 28 | 29 | 29 | 31 | 35 | 35 | 35 | 36 | 36 | 36 | 37 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40
G3.157 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 7 | 9 | 17 | 24 | 31 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 5 | 7 | 9 | 17 | 24 | 31 | 33 | 35 | 37 | 42 | 42 | 42 | 43 | 43 | 43 | 44 | 46 | 46 | 46 | 46 | 46 | 46 | 47 | 47
G3.158 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 6 | 6 | 15 | 20 | 24 | 27 | 30 | 31 | 32 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 7 | 8 | 8 | 8 | 9 | 9 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 3 | 6 | 6 | 15 | 20 | 24 | 28 | 31 | 32 | 34 | 39 | 41 | 42 | 42 | 43 | 44 | 44 | 45 | 46 | 46 | 46 | 46 | 46 | 47
G3.159 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 5 | 13 | 17 | 17 | 19 | 20 | 22 | 22 | 22 | 23 | 24 | 25 | 25 | 25 | 25 | 25 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 11 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 5 | 13 | 18 | 18 | 20 | 22 | 27 | 29 | 31 | 32 | 33 | 35 | 35 | 35 | 36 | 36 | 45
G3.160 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 6 | 12 | 14 | 16 | 16 | 18 | 19 | 19 | 21 | 21 | 21 | 22 | 22 | 22 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6 | 7 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 6 | 13 | 15 | 17 | 18 | 23 | 26 | 27 | 30 | 30 | 31 | 32 | 32 | 33 | 34
G3.161 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.162 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Private Finance Initiative Funded Projects |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes) | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Pre Committed Named + Non Named
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.163 | I | 2: Baseline; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.164 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G3.165 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.166 | I | 3: Gate 80 - Project Approval | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.167 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5
G3.168 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.169 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3
G3.170 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3
G3.171 | I | 2: Forecast Actual; 3: Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.172 | I | 3: Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G3.173 | I | 3: Gate 70 - Option Selection | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
G3.174 | I | 3: Gate 80 - Project Approval | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G3.175 | I |  |  | Gate 90 - Delivery Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5
G3.176 | I |  |  | SOS - Start on Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5
G3.177 | I |  |  | G100 - Project Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4
G3.178 | I |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4
G3.179 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.180 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR10 Completion Projects |  | 4: Confirmed on Committed List
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
G3.181 | I |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.182 | I |  |  | MS2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.183 | I |  |  | MS3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.184 | I |  |  | MS4 | 14 | 6 | 4 | 4 | 4 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.185 | I |  |  | MS5 | 17 | 16 | 7 | 5 | 5 | 5 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.186 | I |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.187 | I |  |  | MS2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.188 | I |  |  | MS3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.189 | I |  |  | MS4 | 15 | 10 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
G3.190 | I |  |  | MS5 | 19 | 16 | 16 | 14 | 14 | 14 | 14 | 14 | 7 | 7 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1
SR15 Completion Projects |  | 4: Confirmed on Committed List
[5 empty] | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
G3.191 | I |  | Committed List Baseline | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.192 | I |  |  | MS2 | 10 | 7 | 6 | 4 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.193 | I |  |  | MS3 | 18 | 12 | 10 | 8 | 6 | 4 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.194 | I |  |  | MS4 | 90 | 60 | 44 | 33 | 25 | 18 | 15 | 10 | 6 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.195 | I |  |  | MS5 | 107 | 96 | 73 | 60 | 47 | 27 | 21 | 16 | 11 | 6 | 4 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.196 | I |  | Forecast Actual | MS1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.197 | I |  |  | MS2 | 16 | 16 | 13 | 9 | 7 | 7 | 7 | 5 | 5 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.198 | I |  |  | MS3 | 19 | 17 | 16 | 11 | 10 | 7 | 7 | 6 | 6 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.199 | I |  |  | MS4 | 94 | 73 | 67 | 55 | 52 | 48 | 40 | 35 | 29 | 25 | 18 | 16 | 13 | 11 | 9 | 7 | 5 | 5 | 3 | 2 | 2 | 2 | 2 | 1
G3.200 | I |  |  | MS5 | 120 | 113 | 104 | 78 | 71 | 68 | 62 | 56 | 39 | 32 | 28 | 25 | 18 | 14 | 11 | 9 | 6 | 5 | 5 | 3 | 2 | 2 | 2 | 1
SR21 Total |  | 4: Confirmed on Committed List | Non Named (Programmes and Projects within programmes | [23 empty] | Pre Committed List Named | [23 empty] | Confirmed in Committed List + Minimum expectation
|  | 4: 2021-22; 8: 2022-23; 12: 2023-24; 16: 2024-25; 20: 2025-26; 24: 2026-27 | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27 |  |  |  | 2021-22 |  |  |  | 2022-23 |  |  |  | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26 |  |  |  | 2026-27
Line Ref | Field type | Management Approach Reference(s) | Type | Gate | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
G3.201 | I |  | Baseline | Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 348 | 503 | 615 | 675 | 720 | 764 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 20 | 52 | 107 | 163 | 192 | 221 | 243 | 289 | 303 | 306 | 306 | 306 | 316 | 317 | 317 | 317 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 172 | 400 | 610 | 778 | 867 | 941 | 1007 | 1059 | 1073 | 1076 | 1076 | 1076 | 1086 | 1087 | 1087 | 1087 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090
G3.202 | I |  |  | Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 44 | 64 | 70 | 76 | 95 | 100 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 7 | 19 | 46 | 75 | 89 | 102 | 123 | 171 | 210 | 252 | 280 | 316 | 338 | 351 | 358 | 373 | 398 | 399 | 404 | 425 | 426 | 427 | 427 | 427 | 25 | 63 | 110 | 145 | 165 | 197 | 223 | 290 | 329 | 371 | 399 | 435 | 457 | 470 | 477 | 492 | 517 | 518 | 523 | 544 | 545 | 546 | 546 | 546
G3.203 | I |  |  | Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 114 | 169 | 200 | 249 | 295 | 315 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 4 | 18 | 37 | 51 | 57 | 70 | 97 | 121 | 177 | 233 | 266 | 315 | 366 | 391 | 405 | 414 | 435 | 451 | 463 | 492 | 495 | 495 | 495 | 497 | 74 | 132 | 206 | 251 | 306 | 365 | 412 | 461 | 517 | 573 | 606 | 655 | 706 | 731 | 745 | 754 | 775 | 791 | 803 | 832 | 835 | 835 | 835 | 837
G3.204 | I |  |  | Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 122 | 155 | 200 | 263 | 332 | 370 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 1 | 1 | 3 | 4 | 5 | 7 | 12 | 18 | 73 | 121 | 169 | 217 | 262 | 298 | 329 | 368 | 404 | 429 | 456 | 471 | 484 | 491 | 497 | 508 | 78 | 123 | 158 | 204 | 268 | 339 | 382 | 445 | 500 | 548 | 596 | 644 | 689 | 725 | 756 | 795 | 831 | 856 | 883 | 898 | 911 | 918 | 924 | 935
G3.205 | I |  |  | Gate 90 - Delivery Approval | 6 | 21 | 33 | 54 | 69 | 80 | 108 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 1026 | 1987 | 2932 | 4333 | 4588 | 5482 | 6939 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 99 | 157 | 205 | 255 | 284 | 308 | 343 | 368 | 394 | 434 | 452 | 467 | 478 | 487 | 493 | 1032 | 2008 | 2965 | 4387 | 4657 | 5562 | 7047 | 8582 | 8627 | 8681 | 8739 | 8787 | 8837 | 8866 | 8890 | 8925 | 8950 | 8976 | 9016 | 9034 | 9049 | 9060 | 9069 | 9075
G3.206 | I |  |  | SOS - Start on Site | 16 | 28 | 44 | 53 | 69 | 88 | 107 | 136 | 150 | 159 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 1000 | 1926 | 2924 | 4379 | 4718 | 5690 | 7171 | 8664 | 8753 | 8777 | 8782 | 8783 | 8786 | 8788 | 8788 | 8789 | 8789 | 8790 | 8791 | 8791 | 8791 | 8791 | 8791 | 8792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 1954 | 2968 | 4432 | 4787 | 5778 | 7278 | 8800 | 8903 | 8936 | 8945 | 8946 | 8949 | 8951 | 8951 | 8952 | 8952 | 8953 | 8954 | 8954 | 8954 | 8954 | 8954 | 8955
G3.207 | I |  |  | G100 - Project Acceptance | 52 | 111 | 147 | 181 | 207 | 230 | 247 | 260 | 272 | 291 | 310 | 330 | 349 | 364 | 378 | 383 | 384 | 387 | 387 | 391 | 392 | 392 | 392 | 392 | 1557 | 2554 | 3499 | 4462 | 5887 | 6222 | 7212 | 8699 | 10209 | 10300 | 10397 | 10457 | 10486 | 10504 | 10515 | 10521 | 10528 | 10535 | 10539 | 10543 | 10545 | 10547 | 10552 | 10594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609 | 2665 | 3646 | 4643 | 6094 | 6452 | 7459 | 8959 | 10481 | 10591 | 10707 | 10787 | 10835 | 10868 | 10893 | 10904 | 10912 | 10922 | 10926 | 10934 | 10937 | 10939 | 10944 | 10986
G3.208 | I |  |  | G110 - Financial Closure | 5 | 5 | 37 | 79 | 129 | 170 | 209 | 235 | 260 | 280 | 293 | 309 | 328 | 348 | 366 | 383 | 399 | 412 | 417 | 418 | 421 | 421 | 425 | 426 | 1489 | 2471 | 3410 | 4313 | 5725 | 6020 | 7017 | 8518 | 10028 | 10176 | 10326 | 10430 | 10516 | 10557 | 10586 | 10601 | 10611 | 10615 | 10623 | 10629 | 10635 | 10637 | 10640 | 10672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494 | 2476 | 3447 | 4392 | 5854 | 6190 | 7226 | 8753 | 10288 | 10456 | 10619 | 10739 | 10844 | 10905 | 10952 | 10984 | 11010 | 11027 | 11040 | 11047 | 11056 | 11058 | 11065 | 11098
G3.209 | I |  | Forecast Actual | Gate 30 - Project Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 348 | 503 | 615 | 675 | 720 | 764 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 770 | 20 | 52 | 107 | 163 | 192 | 221 | 243 | 289 | 303 | 306 | 306 | 306 | 316 | 317 | 317 | 317 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 172 | 400 | 610 | 778 | 867 | 941 | 1007 | 1059 | 1073 | 1076 | 1076 | 1076 | 1086 | 1087 | 1087 | 1087 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090 | 1090
G3.210 | I |  |  | Gate 50 - Options Confirmed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 44 | 64 | 70 | 76 | 95 | 100 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 119 | 7 | 19 | 46 | 75 | 89 | 102 | 123 | 171 | 210 | 252 | 280 | 316 | 338 | 351 | 358 | 373 | 398 | 399 | 404 | 425 | 426 | 427 | 427 | 427 | 25 | 63 | 110 | 145 | 165 | 197 | 223 | 290 | 329 | 371 | 399 | 435 | 457 | 470 | 477 | 492 | 517 | 518 | 523 | 544 | 545 | 546 | 546 | 546
G3.211 | I |  |  | Gate 70 - Option Selection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 114 | 169 | 200 | 249 | 295 | 315 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 340 | 4 | 18 | 37 | 51 | 57 | 70 | 97 | 121 | 177 | 233 | 266 | 315 | 366 | 391 | 405 | 414 | 435 | 451 | 463 | 492 | 495 | 495 | 495 | 497 | 74 | 132 | 206 | 251 | 306 | 365 | 412 | 461 | 517 | 573 | 606 | 655 | 706 | 731 | 745 | 754 | 775 | 791 | 803 | 832 | 835 | 835 | 835 | 837
G3.212 | I |  |  | Gate 80 - Project Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 122 | 155 | 200 | 263 | 332 | 370 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 427 | 1 | 1 | 3 | 4 | 5 | 7 | 12 | 18 | 73 | 121 | 169 | 217 | 262 | 298 | 329 | 368 | 404 | 429 | 456 | 471 | 484 | 491 | 497 | 508 | 78 | 123 | 158 | 204 | 268 | 339 | 382 | 445 | 500 | 548 | 596 | 644 | 689 | 725 | 756 | 795 | 831 | 856 | 883 | 898 | 911 | 918 | 924 | 935
G3.213 | I |  |  | Gate 90 - Delivery Approval | 6 | 21 | 33 | 54 | 69 | 80 | 108 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 1026 | 1987 | 2932 | 4333 | 4588 | 5482 | 6939 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 8439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 99 | 157 | 205 | 255 | 284 | 308 | 343 | 368 | 394 | 434 | 452 | 467 | 478 | 487 | 493 | 1032 | 2008 | 2965 | 4387 | 4657 | 5562 | 7047 | 8582 | 8627 | 8681 | 8739 | 8787 | 8837 | 8866 | 8890 | 8925 | 8950 | 8976 | 9016 | 9034 | 9049 | 9060 | 9069 | 9075
G3.214 | I |  |  | SOS - Start on Site | 16 | 28 | 43 | 61 | 74 | 92 | 111 | 144 | 152 | 159 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 1021 | 1923 | 2883 | 4331 | 4601 | 5537 | 7005 | 8541 | 8625 | 8684 | 8708 | 8714 | 8733 | 8737 | 8738 | 8738 | 8752 | 8753 | 8757 | 8757 | 8757 | 8757 | 8758 | 8758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 69 | 99 | 155 | 213 | 254 | 283 | 308 | 342 | 365 | 398 | 435 | 453 | 467 | 478 | 488 | 1037 | 1951 | 2926 | 4392 | 4675 | 5629 | 7116 | 8685 | 8800 | 8912 | 8970 | 9032 | 9109 | 9154 | 9184 | 9209 | 9257 | 9281 | 9318 | 9355 | 9373 | 9387 | 9399 | 9409
G3.215 | I |  |  | G100 - Project Acceptance | 42 | 79 | 108 | 146 | 156 | 172 | 195 | 233 | 258 | 286 | 316 | 334 | 354 | 370 | 377 | 380 | 385 | 385 | 389 | 390 | 390 | 391 | 391 | 391 | 636 | 1548 | 2443 | 3015 | 4161 | 4789 | 5669 | 6889 | 9797 | 9961 | 10201 | 10296 | 10396 | 10452 | 10477 | 10490 | 10511 | 10524 | 10542 | 10545 | 10548 | 10551 | 10556 | 10598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 9 | 18 | 29 | 57 | 83 | 111 | 156 | 185 | 214 | 249 | 274 | 309 | 336 | 375 | 678 | 1627 | 2551 | 3161 | 4317 | 4961 | 5864 | 7122 | 10056 | 10249 | 10526 | 10648 | 10779 | 10879 | 10937 | 10981 | 11052 | 11094 | 11145 | 11184 | 11212 | 11251 | 11283 | 11364
G3.216 | I |  |  | G110 - Financial Closure | 4 | 17 | 51 | 124 | 139 | 155 | 177 | 231 | 238 | 275 | 303 | 330 | 361 | 376 | 389 | 401 | 410 | 415 | 419 | 421 | 424 | 424 | 424 | 425 | 605 | 1435 | 2313 | 2867 | 3980 | 4604 | 5496 | 6700 | 9567 | 9720 | 9947 | 10119 | 10281 | 10389 | 10481 | 10535 | 10564 | 10585 | 10595 | 10616 | 10626 | 10630 | 10633 | 10669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 16 | 29 | 47 | 66 | 95 | 125 | 168 | 189 | 226 | 260 | 291 | 322 | 609 | 1452 | 2364 | 2991 | 4119 | 4759 | 5673 | 6931 | 9806 | 9996 | 10252 | 10455 | 10658 | 10794 | 10917 | 11002 | 11069 | 11125 | 11182 | 11226 | 11276 | 11314 | 11348 | 11416
G3.217 | I |  |  | Needs from Gate 30 onwards put on hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3.218 | I |  |  | Needs from Gate 30 onwards that do not require an intervention | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: …………………………………………….. |  | 2: Date:
Checked by: ……………………………………………..
Authorised by: |  | 2: Date:

## G4a
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G4a: Summary IPOD by Ministerial Objective
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Line Ref | Ministerial Objective | Type | Gate | Pre 21-22 | 2021-22-Q1 | 2021-22-Q2 | 2021-22-Q3 | 2021-22-Q4 | 2022-23-Q1 | 2022-23-Q2 | 2022-23-Q3 | 2022-23-Q4 | 2023-24-Q1 | 2023-24-Q2 | 2023-24-Q3 | 2023-24-Q4 | 2024-25-Q1 | 2024-25-Q2 | 2024-25-Q3 | 2024-25-Q4 | 2025-26-Q1 | 2025-26-Q2 | 2025-26-Q3 | 2025-26-Q4 | 2026-27-Q1 | 2026-27-Q2 | 2026-27-Q3 | 2026-27-Q4 | Post 2026-27
G4a.01 | Standards of Service | Committed List Baseline | SOS - Start On Site | 0 | 13 | 23 | 38 | 45 | 56 | 71 | 86 | 104 | 116 | 121 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
G4a.02 |  |  | G100 - Acceptance | 0 | 47 | 89 | 119 | 144 | 164 | 182 | 197 | 204 | 211 | 227 | 238 | 255 | 269 | 275 | 288 | 292 | 293 | 294 | 294 | 297 | 298 | 298 | 298 | 298 | 298
G4a.03 |  |  | G110 - Financial Closure | 0 | 4 | 4 | 32 | 68 | 103 | 138 | 170 | 191 | 211 | 226 | 232 | 243 | 257 | 270 | 283 | 297 | 304 | 316 | 320 | 321 | 322 | 322 | 325 | 326 | 326
G4a.04 |  |  | Total | 0 | 64 | 116 | 189 | 257 | 323 | 391 | 453 | 499 | 538 | 574 | 594 | 622 | 650 | 669 | 695 | 713 | 721 | 734 | 738 | 742 | 744 | 744 | 747 | 748 | 748
G4a.05 |  | Forecast Actual | SOS - Start On Site | 8 | 13 | 23 | 36 | 49 | 58 | 73 | 86 | 111 | 118 | 121 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
G4a.06 |  |  | G100 - Acceptance | 13 | 38 | 71 | 94 | 121 | 128 | 143 | 161 | 189 | 206 | 225 | 246 | 259 | 271 | 283 | 286 | 289 | 292 | 292 | 296 | 297 | 297 | 298 | 298 | 298 | 298
G4a.07 |  |  | G110 - Financial Closure | 0 | 4 | 14 | 45 | 101 | 114 | 128 | 146 | 192 | 195 | 220 | 244 | 261 | 281 | 289 | 297 | 307 | 313 | 318 | 320 | 322 | 325 | 325 | 325 | 326 | 326
G4a.08 |  |  | Total | 21 | 55 | 108 | 175 | 271 | 300 | 344 | 393 | 492 | 519 | 566 | 614 | 644 | 676 | 696 | 707 | 720 | 729 | 734 | 740 | 743 | 746 | 747 | 747 | 748 | 748
G4a.09 | Asset Maintenance | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.10 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.11 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.12 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.13 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.14 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.15 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.16 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.17 | Supporting Sustainable Economic Growth | Committed List Baseline | SOS - Start On Site | 0 | 2 | 4 | 5 | 6 | 7 | 8 | 11 | 13 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G4a.18 |  |  | G100 - Acceptance | 0 | 4 | 8 | 12 | 21 | 24 | 28 | 28 | 30 | 32 | 35 | 36 | 38 | 41 | 46 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G4a.19 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 2 | 6 | 8 | 12 | 19 | 23 | 27 | 28 | 30 | 32 | 36 | 38 | 40 | 43 | 48 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G4a.20 |  |  | Total | 0 | 6 | 12 | 19 | 33 | 39 | 48 | 58 | 66 | 73 | 79 | 83 | 87 | 94 | 101 | 104 | 108 | 113 | 114 | 115 | 115 | 115 | 115 | 115 | 115 | 115
G4a.21 |  | Forecast Actual | SOS - Start On Site | 0 | 2 | 3 | 5 | 7 | 9 | 11 | 13 | 14 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
G4a.22 |  |  | G100 - Acceptance | 2 | 3 | 5 | 8 | 15 | 16 | 17 | 19 | 24 | 29 | 31 | 33 | 36 | 41 | 45 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
G4a.23 |  |  | G110 - Financial Closure | 0 | 0 | 1 | 3 | 10 | 10 | 12 | 15 | 20 | 23 | 30 | 31 | 33 | 38 | 42 | 46 | 47 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
G4a.24 |  |  | Total | 2 | 5 | 9 | 16 | 32 | 35 | 40 | 47 | 58 | 66 | 77 | 81 | 86 | 96 | 104 | 111 | 112 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115
G4a.25 | Long Term Water Sector Vision | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.26 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.27 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.28 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4a.29 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.30 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.31 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4a.32 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4a.33 | Drinking Water | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 2 | 5 | 7 | 8 | 13 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G4a.34 |  |  | G100 - Acceptance | 0 | 0 | 1 | 2 | 2 | 4 | 5 | 7 | 11 | 14 | 14 | 16 | 17 | 18 | 22 | 22 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 24
G4a.35 |  |  | G110 - Financial Closure | 0 | 1 | 1 | 1 | 2 | 3 | 4 | 4 | 4 | 5 | 9 | 14 | 16 | 16 | 18 | 20 | 20 | 24 | 24 | 24 | 24 | 25 | 25 | 26 | 26 | 26
G4a.36 |  |  | Total | 0 | 2 | 3 | 4 | 6 | 12 | 16 | 19 | 28 | 33 | 38 | 45 | 48 | 49 | 55 | 57 | 57 | 61 | 62 | 62 | 63 | 64 | 64 | 65 | 65 | 65
G4a.37 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 2 | 2 | 4 | 6 | 7 | 9 | 13 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G4a.38 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 7 | 11 | 16 | 18 | 21 | 21 | 21 | 21 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24
G4a.39 |  |  | G110 - Financial Closure | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 6 | 8 | 13 | 19 | 22 | 23 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 25 | 26
G4a.40 |  |  | Total | 0 | 1 | 4 | 4 | 8 | 10 | 11 | 13 | 21 | 25 | 32 | 39 | 46 | 55 | 58 | 59 | 59 | 61 | 61 | 63 | 63 | 63 | 63 | 63 | 63 | 65
G4a.41 | Environment | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.42 |  |  | G100 - Acceptance | 0 | 1 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G4a.43 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 2 | 3 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15
G4a.44 |  |  | Total | 0 | 1 | 8 | 11 | 12 | 21 | 22 | 22 | 24 | 24 | 25 | 27 | 27 | 27 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31
G4a.45 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.46 |  |  | G100 - Acceptance | 1 | 1 | 3 | 3 | 5 | 6 | 6 | 9 | 10 | 10 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
G4a.47 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 6 | 7 | 7 | 8 | 11 | 11 | 12 | 12 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G4a.48 |  |  | Total | 1 | 1 | 3 | 4 | 12 | 14 | 14 | 18 | 23 | 23 | 26 | 27 | 29 | 29 | 29 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
G4a.49 | Flooding and Surface Water Management | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.50 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.51 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.52 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.53 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.54 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.55 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.56 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.57 | Security & Resilience | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.58 |  |  | G100 - Acceptance | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G4a.59 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G4a.60 |  |  | Total | 0 | 0 | 5 | 5 | 5 | 10 | 11 | 11 | 13 | 13 | 13 | 15 | 16 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G4a.61 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.62 |  |  | G100 - Acceptance | 0 | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 6 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G4a.63 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
G4a.64 |  |  | Total | 0 | 0 | 0 | 3 | 8 | 10 | 10 | 11 | 13 | 14 | 17 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
G4a.65 | Climate Change, Adaptation and Mitigation | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.66 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.67 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.68 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.69 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.70 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.71 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4a.72 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
G4a.73 | Private Finance Initiative Funded Projects | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.74 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.75 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.76 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.77 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.78 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.79 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.80 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.81 | Circular Economy | Committed List Baseline | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.82 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.83 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.84 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.85 |  | Forecast Actual | SOS - Start On Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.86 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.87 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4a.88 |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: |  | 2: Date:

## G4b
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G4b: Summary IPOD by Portfolio
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Line Ref | Portfolio | Type | Gate | Pre 21-22 | 2021-22-Q1 | 2021-22-Q2 | 2021-22-Q3 | 2021-22-Q4 | 2022-23-Q1 | 2022-23-Q2 | 2022-23-Q3 | 2022-23-Q4 | 2023-24-Q1 | 2023-24-Q2 | 2023-24-Q3 | 2023-24-Q4 | 2024-25-Q1 | 2024-25-Q2 | 2024-25-Q3 | 2024-25-Q4 | 2025-26-Q1 | 2025-26-Q2 | 2025-26-Q3 | 2025-26-Q4 | 2026-27-Q1 | 2026-27-Q2 | 2026-27-Q3 | 2026-27-Q4 | Post 2026-27
G4b.01 | CE&FS | Committed List Baseline | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4b.02 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.03 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.04 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4b.05 |  | Forecast Actual | SOS - Start On Site | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G4b.06 |  |  | G100 - Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.07 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G4b.08 |  |  | Total | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
G4b.09 | Water | Committed List Baseline | SOS - Start On Site | 0 | 11 | 15 | 25 | 31 | 43 | 55 | 64 | 77 | 88 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94
G4b.10 |  |  | G100 - Acceptance | 0 | 27 | 48 | 64 | 80 | 93 | 104 | 115 | 124 | 132 | 143 | 153 | 167 | 178 | 189 | 196 | 198 | 198 | 200 | 200 | 204 | 205 | 205 | 205 | 205 | 205
G4b.11 |  |  | G110 - Financial Closure | 0 | 5 | 5 | 28 | 47 | 64 | 81 | 102 | 115 | 127 | 141 | 151 | 162 | 169 | 181 | 195 | 205 | 216 | 223 | 225 | 225 | 227 | 227 | 231 | 232 | 232
G4b.12 |  |  | Total | 0 | 43 | 68 | 117 | 158 | 200 | 240 | 281 | 316 | 347 | 377 | 398 | 423 | 441 | 464 | 485 | 497 | 508 | 517 | 519 | 523 | 526 | 526 | 530 | 531 | 531
G4b.13 |  | Forecast Actual | SOS - Start On Site | 7 | 11 | 16 | 26 | 36 | 45 | 56 | 66 | 81 | 88 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94
G4b.14 |  |  | G100 - Acceptance | 5 | 16 | 36 | 53 | 70 | 72 | 82 | 90 | 109 | 122 | 138 | 157 | 165 | 181 | 190 | 191 | 194 | 199 | 199 | 202 | 203 | 203 | 204 | 204 | 204 | 205
G4b.15 |  |  | G110 - Financial Closure | 0 | 2 | 12 | 29 | 68 | 75 | 80 | 96 | 118 | 123 | 138 | 149 | 168 | 189 | 198 | 205 | 213 | 218 | 223 | 226 | 227 | 230 | 230 | 230 | 231 | 232
G4b.16 |  |  | Total | 12 | 29 | 64 | 108 | 174 | 192 | 218 | 252 | 308 | 333 | 369 | 400 | 427 | 464 | 482 | 490 | 501 | 511 | 516 | 522 | 524 | 527 | 528 | 528 | 529 | 531
G4b.17 | Wastewater | Committed List Baseline | SOS - Start On Site | 0 | 4 | 11 | 16 | 18 | 21 | 25 | 33 | 43 | 46 | 50 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G4b.18 |  |  | G100 - Acceptance | 0 | 21 | 51 | 71 | 88 | 101 | 112 | 117 | 121 | 124 | 130 | 135 | 138 | 144 | 148 | 155 | 158 | 159 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
G4b.19 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 8 | 27 | 53 | 76 | 93 | 106 | 117 | 123 | 126 | 129 | 136 | 141 | 144 | 150 | 155 | 161 | 164 | 165 | 166 | 166 | 166 | 166 | 166
G4b.20 |  |  | Total | 0 | 25 | 62 | 95 | 133 | 175 | 213 | 243 | 270 | 287 | 303 | 314 | 320 | 333 | 342 | 352 | 361 | 367 | 374 | 377 | 378 | 379 | 379 | 379 | 379 | 379
G4b.21 |  | Forecast Actual | SOS - Start On Site | 0 | 3 | 9 | 13 | 20 | 23 | 29 | 36 | 47 | 48 | 50 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
G4b.22 |  |  | G100 - Acceptance | 11 | 25 | 41 | 48 | 65 | 71 | 77 | 91 | 108 | 117 | 124 | 132 | 142 | 146 | 153 | 159 | 159 | 159 | 159 | 160 | 160 | 160 | 160 | 160 | 160 | 160
G4b.23 |  |  | G110 - Financial Closure | 0 | 0 | 3 | 18 | 46 | 52 | 61 | 67 | 97 | 99 | 115 | 127 | 134 | 144 | 150 | 156 | 160 | 164 | 164 | 165 | 166 | 166 | 166 | 166 | 166 | 166
G4b.24 |  |  | Total | 11 | 28 | 53 | 79 | 131 | 146 | 167 | 194 | 252 | 264 | 289 | 312 | 329 | 343 | 356 | 368 | 372 | 376 | 376 | 378 | 379 | 379 | 379 | 379 | 379 | 379
G4b.25 | Support Services | Committed List Baseline | SOS - Start On Site | 0 | 1 | 2 | 3 | 4 | 5 | 8 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G4b.26 |  |  | G100 - Acceptance | 0 | 4 | 12 | 12 | 13 | 13 | 14 | 15 | 15 | 16 | 18 | 22 | 25 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G4b.27 |  |  | G110 - Financial Closure | 0 | 0 | 0 | 1 | 5 | 12 | 13 | 14 | 14 | 16 | 16 | 16 | 18 | 23 | 26 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G4b.28 |  |  | Total | 0 | 5 | 14 | 16 | 22 | 30 | 35 | 39 | 45 | 48 | 50 | 54 | 59 | 66 | 69 | 70 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71
G4b.29 |  | Forecast Actual | SOS - Start On Site | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
G4b.30 |  |  | G100 - Acceptance | 0 | 1 | 2 | 7 | 11 | 13 | 13 | 14 | 16 | 19 | 24 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
G4b.31 |  |  | G110 - Financial Closure | 0 | 2 | 2 | 4 | 10 | 12 | 14 | 14 | 16 | 16 | 22 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
G4b.32 |  |  | Total | 1 | 5 | 7 | 15 | 26 | 31 | 34 | 37 | 48 | 51 | 62 | 70 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71
G4b.33 | Total | Committed List Baseline | SOS - Start On Site | 0 | 17 | 29 | 45 | 54 | 70 | 89 | 108 | 137 | 151 | 160 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164
G4b.34 |  |  | G100 - Acceptance | 0 | 52 | 111 | 147 | 181 | 207 | 230 | 247 | 260 | 272 | 291 | 310 | 330 | 349 | 364 | 378 | 383 | 384 | 387 | 387 | 391 | 392 | 392 | 392 | 392 | 393
G4b.35 |  |  | G110 - Financial Closure | 0 | 5 | 5 | 37 | 79 | 129 | 170 | 209 | 235 | 260 | 280 | 293 | 309 | 328 | 348 | 366 | 383 | 399 | 412 | 417 | 418 | 421 | 421 | 425 | 426 | 427
G4b.36 |  |  | Total | 0 | 74 | 145 | 229 | 314 | 406 | 489 | 564 | 632 | 683 | 731 | 767 | 803 | 841 | 876 | 908 | 930 | 947 | 963 | 968 | 973 | 977 | 977 | 981 | 982 | 984
G4b.37 |  | Forecast Actual | SOS - Start On Site | 8 | 17 | 29 | 44 | 62 | 75 | 93 | 112 | 145 | 153 | 160 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164 | 164
G4b.38 |  |  | G100 - Acceptance | 16 | 42 | 79 | 108 | 146 | 156 | 172 | 195 | 233 | 258 | 286 | 316 | 334 | 354 | 370 | 377 | 380 | 385 | 385 | 389 | 390 | 390 | 391 | 391 | 391 | 393
G4b.39 |  |  | G110 - Financial Closure | 0 | 4 | 17 | 51 | 124 | 139 | 155 | 177 | 231 | 238 | 275 | 303 | 330 | 361 | 376 | 389 | 401 | 410 | 415 | 419 | 421 | 424 | 424 | 424 | 425 | 427
G4b.40 |  |  | Total | 24 | 63 | 125 | 203 | 332 | 370 | 420 | 484 | 609 | 649 | 721 | 783 | 828 | 879 | 910 | 930 | 945 | 959 | 964 | 972 | 975 | 978 | 979 | 979 | 980 | 984
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: |  | 2: Date:

## G4c
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G4c: Detail IPOD
GATE ID | PROJECT ID | DESCRIPTION | PORTFOLIO | GATE | GATE NAME | BASELINE DATE | FORECAST DATE | BASELINE MONTH | FORECAST MONTH | BASELINE QUARTER | FORECAST QUARTER
SOS403716 | 403716 | SR15 ES - Sanday Sludge Storage Area and Drying Beds | Wastewater | SOS | Start on Site | 2022-07-11 | 2022-07-11 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
SOS500046 | 500046 | Improvement to Supply-Demand Balance - Stornoway WRZ | Water | SOS | Start on Site | 2023-05-11 | 2021-12-21 | 2023_24_P02 | 2021_22_P09 | 2023_24_Q1 | 2021_22_Q3
SOS404026 | 404026 | SR15 ES - Main Street Newtonmore | Wastewater | SOS | Start on Site | 2021-08-09 | 2022-03-31 | 2021_22_P05 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
SOS403995 | 403995 | SR15 ES - Londornoch WTW | Water | SOS | Start on Site | 2022-03-15 | 2022-03-15 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS403923 | 403923 | SR15 ES - E1618 - Rose Street Annan 14 33 and 35 | Wastewater | SOS | Start on Site | 2021-04-06 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS403967 | 403967 | Winchburgh WwTW - Growth | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-07-29 | 2021_22_P05 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS403782 | 403782 | Kennethmont WwTW Growth | Wastewater | SOS | Start on Site | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
SOS500229 | 500229 | East Linton WwTW - Growth | Wastewater | SOS | Start on Site | 2021-07-30 | 2022-03-31 | 2021_22_P04 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
SOS500576 | 500576 | Orphir Village WwTW - Enforcement Mitigations | Wastewater | SOS | Start on Site | 2023-03-31 | 2023-03-31 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS404132 | 404132 | Picketlaw WTW - Main Out | Water | SOS | Start on Site | 2023-05-23 | 2023-03-06 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
SOS500654 | 500654 | SE246 - Burnswark View Eaglesfield | Wastewater | SOS | Start on Site | 2021-05-10 | 2021-09-30 | 2021_22_P02 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
SOS500681 | 500681 | SW843 Wellgate Lanark | Wastewater | SOS | Start on Site | 2021-08-03 | 2021-09-27 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
SOS500661 | 500661 | E1010 Craigleith Road Edinburgh | Wastewater | SOS | Start on Site | 2021-08-09 | 2021-08-20 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS500682 | 500682 | SW857 - Townhead Street Stonehouse | Wastewater | SOS | Start on Site | 2021-09-20 | 2021-09-20 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
SOS500892 | 500892 | Cowsrieve Service Reservoir | Water | SOS | Start on Site | 2021-06-02 | 2021-04-26 | 2021_22_P03 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
SOS500755 | 500755 | North Coast SCADA Replacement | Water | SOS | Start on Site | 2021-09-01 | 2021-08-02 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS500724 | 500724 | Udny Green WwTW - Growth | Wastewater | SOS | Start on Site | 2023-02-03 | 2023-02-20 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS500729 | 500729 | Boughden Braes Lesmahagow Sewer Replacement | Wastewater | SOS | Start on Site | 2023-09-25 | 2023-03-28 | 2023_24_P06 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
SOS501017 | 501017 | SW1015 - Shieldaig Road, Glasgow | Wastewater | SOS | Start on Site | 2022-08-22 | 2022-08-22 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
SOS500731 | 500731 | Newmachar WwTW - Growth | Wastewater | SOS | Start on Site | 2022-12-05 | 2022-05-31 | 2022_23_P09 | 2022_23_P02 | 2022_23_Q3 | 2022_23_Q1
SOS500893 | 500893 | Craigmaddie and Milngavie VT Works | Water | SOS | Start on Site | 2022-09-26 | 2022-10-17 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
SOS501512 | 501512 | INSH WWTW 1996 NH809016 | Wastewater | SOS | Start on Site | 2022-10-11 | 2022-12-05 | 2022_23_P07 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
SOS501379 | 501379 | WTW000640 - MARCHBANK WTW NT165645 | Water | SOS | Start on Site | 2021-04-01 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS501670 | 501670 | DAER WOA - Stablewood Pipe Bridge - H&S upgrade | Water | SOS | Start on Site | 2023-07-03 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS501731 | 501731 | Kerse TWS Refurb | Water | SOS | Start on Site | 2022-09-01 | 2022-06-30 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
SOS501703 | 501703 | Station Rd - Nairn Rd Ardersier - replace sewer | Wastewater | SOS | Start on Site | 2023-02-14 | 2023-02-06 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS502243 | 502243 | Mannofield WTW -Improvements to Treatment Process | Water | SOS | Start on Site | 2022-09-01 | 2022-08-15 | 2022_23_P06 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
SOS502332 | 502332 | Drumnadrochit WwTW - Growth | Wastewater | SOS | Start on Site | 2022-10-06 | 2022-10-19 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
SOS502282 | 502282 | Oykel Bridge - Radon | Water | SOS | Start on Site | 2022-09-12 | 2022-06-06 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
SOS502220 | 502220 | IR18 Allowance - Edgehead Septic Tank | Wastewater | SOS | Start on Site | 2023-07-17 | 2023-07-17 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS502425 | 502425 | SW599 - Laighlands Road Bothwell | Wastewater | SOS | Start on Site | 2023-12-04 | 2023-11-17 | 2023_24_P09 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3
SOS502375 | 502375 | W574 1-21 Clarkston Road, Glasgow | Wastewater | SOS | Start on Site | 2022-09-22 | 2022-06-06 | 2022_23_P06 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
SOS502212 | 502212 | IR18 Allowance - Newton Septic Tank | Wastewater | SOS | Start on Site | 2022-04-04 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS502342 | 502342 | MCC SR15- Hamilton WWTW MCC Replacement | Wastewater | SOS | Start on Site | 2021-07-05 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS502358 | 502358 | Black Esk and Winterhope WOA - Gretna Water Supply | Water | SOS | Start on Site | 2022-08-29 | 2022-09-30 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS502383 | 502383 | IR18 Allowance - Fife - Abstraction Improvement | Water | SOS | Start on Site | 2021-04-14 | 2021-03-08 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS502369 | 502369 | Beasdale WTW UV Alterations | Water | SOS | Start on Site | 2023-09-04 | 2023-09-04 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
SOS502895 | 502895 | SW1392 - Third Avenue Glasgow | Wastewater | SOS | Start on Site | 2021-11-18 | 2021-11-18 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS502652 | 502652 | IR18 Allowance - Barra WTW | Water | SOS | Start on Site | 2022-02-21 | 2022-02-21 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
SOS502827 | 502827 | Tarves WwTW - Growth | Wastewater | SOS | Start on Site | 2021-05-18 | 2021-05-31 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
SOS502746 | 502746 | WATER OF LEITH UIDs BATCH 7 Longstone CSOs | Wastewater | SOS | Start on Site | 2023-06-19 | 2023-03-13 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
SOS502955 | 502955 | EFOS - A8 East Hamilton Street Greenock | Wastewater | SOS | Start on Site | 2023-07-10 | 2023-01-09 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
SOS502563 | 502563 | IR18 Allowance - Dye Water Fish Pass | Water | SOS | Start on Site | 2021-07-20 | 2021-07-05 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
SOS502958 | 502958 | Aboyne WwTW - Capital Maintenance | Wastewater | SOS | Start on Site | 2021-10-18 | 2021-10-18 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS502853 | 502853 | Chemical Dosing Programme - Phase 1 - Glendevon WTW | Water | SOS | Start on Site | 2021-10-22 | 2021-10-22 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS503050 | 503050 | Wishaw TM Water Quality | Water | SOS | Start on Site | 2021-08-04 | 2021-08-30 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS502857 | 502857 | Chemical Dosing Programme - Phase 1 - Turriff WTW | Water | SOS | Start on Site | 2022-05-19 | 2022-05-19 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS503092 | 503092 | Legbrannock DSR | Water | SOS | Start on Site | 2023-07-03 | 2023-07-03 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS503234 | 503234 | Allt Sanna WFPM | Water | SOS | Start on Site | 2021-06-21 | 2021-06-01 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS503162 | 503162 | Auchneel WTW - Lime to Caustic | Water | SOS | Start on Site | 2021-10-05 | 2021-12-14 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
SOS503336 | 503336 | Water Quality Improvement-Wick East DMA | Water | SOS | Start on Site | 2021-08-02 | 2021-08-04 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS503230 | 503230 | Main Street Kirkconnel Pipe Bridge | Wastewater | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS503480 | 503480 | Kettleton Impounding Reservoir | Water | SOS | Start on Site | 2023-07-10 | 2023-07-10 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS503408 | 503408 | Blairlinnans PSC TM Monitoring | Water | SOS | Start on Site | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
SOS503412 | 503412 | Dalmacoulter WSZ Trunk Main Cleaning | Water | SOS | Start on Site | 2021-04-21 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503413 | 503413 | Garbethill WSZ Trunk Main Cleaning | Water | SOS | Start on Site | 2021-04-21 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503421 | 503421 | Stornoway WTW - Interim THM and Cryptosporidium measures | Water | SOS | Start on Site | 2022-04-18 | 2021-09-13 | 2022_23_P01 | 2021_22_P06 | 2022_23_Q1 | 2021_22_Q2
SOS503441 | 503441 | Oldmeldrum STW - Surface Aerator Replacement & Interim Oxymem Install | Wastewater | SOS | Start on Site | 2022-02-28 | 2022-03-28 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS503571 | 503571 | E1287 - Claredon Place Dunblane | Wastewater | SOS | Start on Site | 2021-06-10 | 2021-06-10 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS503594 | 503594 | E1050 Marchmont Road Warrender Park Road Edinburgh Recycled | Wastewater | SOS | Start on Site | 2022-11-22 | 2022-08-30 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
SOS503628 | 503628 | SR21ES Herricks WTW upgrade | Water | SOS | Start on Site | 2022-11-14 | 2022-11-21 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
SOS503638 | 503638 | SR21 Carstairs Junction Overland Sewer | Wastewater | SOS | Start on Site | 2023-03-02 | 2023-03-27 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS503613 | 503613 | SR21 ES Loch Calder WOA - Roster Occumster Mains Rehab | Water | SOS | Start on Site | 2023-01-09 | 2023-01-09 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS503678 | 503678 | SR21 ES Camps | Water | SOS | Start on Site | 2022-03-11 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS503680 | 503680 | Dunside Upper and Lower Risk Reduction | Water | SOS | Start on Site | 2023-06-27 | 2023-06-27 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
SOS503686 | 503686 | SR21 ES Munnoch Breach | Water | SOS | Start on Site | 2022-04-04 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS503714 | 503714 | SR21 ES North Third | Water | SOS | Start on Site | 2022-12-06 | 2023-02-16 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
SOS503716 | 503716 | SR21 ES Mill Glen Breach | Water | SOS | Start on Site | 2021-06-14 | 2021-05-11 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
SOS503730 | 503730 | Stonebyres DMA Mains Rehabilitation | Water | SOS | Start on Site | 2022-11-16 | 2022-02-14 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4
SOS503731 | 503731 | Elsrickle DMA Mains Rehabilitation | Water | SOS | Start on Site | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS503732 | 503732 | Portree - Braes DMA Mains Rehabilitation | Water | SOS | Start on Site | 2022-12-12 | 2022-12-21 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
SOS503761 | 503761 | SR21 Bonnycraig WTW Growth and Quality | Water | SOS | Start on Site | 2021-05-25 | 2021-06-22 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS504465 | 504465 | Forehill WTW - Ferric Storage and delivery area | Water | SOS | Start on Site | 2023-06-02 | 2023-05-19 | 2023_24_P03 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
SOS504995 | 504995 | Loch Calder WTW - Treated Water Pumps | Water | SOS | Start on Site | 2022-09-05 | 2022-08-22 | 2022_23_P06 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
SOS505053 | 505053 | EFOS - Sauchie Road Crieff - 0248 | Wastewater | SOS | Start on Site | 2022-05-23 | 2022-05-23 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS505447 | 505447 | RCI Bigton DMA Maywick Road | Water | SOS | Start on Site | 2021-12-01 | 2021-11-29 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS505504 | 505504 | RCI High Dykes DMA (Auchincarroch Rd) | Water | SOS | Start on Site | 2021-11-29 | 2022-08-01 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2
SOS505687 | 505687 | Rosewell WwTW - Interim Growth Solution SAF | Wastewater | SOS | Start on Site | 2023-02-15 | 2022-10-12 | 2022_23_P11 | 2022_23_P07 | 2022_23_Q4 | 2022_23_Q3
SOS505693 | 505693 | RCI West Ballochy DMA (Hillside) | Water | SOS | Start on Site | 2021-11-08 | 2021-11-22 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS505641 | 505641 | Lochwinnoch WwTW - Inlet Screw Pumps Refurbishment - 500k | Wastewater | SOS | Start on Site | 2022-01-06 | 2022-01-06 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS505927 | 505927 | RCI Hilliclay DMA (Stainland) | Water | SOS | Start on Site | 2022-12-19 | 2022-12-14 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
SOS505949 | 505949 | Skellyton WwTW SR10 Outstanding CM | Wastewater | SOS | Start on Site | 2023-02-15 | 2022-11-14 | 2022_23_P11 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
SOS506029 | 506029 | RCI Roskhill DMA and Dunvegan DMA Roag | Water | SOS | Start on Site | 2022-08-31 | 2022-08-22 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
SOS506032 | 506032 | RCI Broadford DMA and Breakish DMA Broadford | Water | SOS | Start on Site | 2022-09-30 | 2022-09-05 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS506149 | 506149 | RCI Tankerness and Foubister DMA Tankerness | Water | SOS | Start on Site | 2022-05-23 | 2022-06-27 | 2022_23_P02 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS506151 | 506151 | RCI West Line DMA Oust WSZ | Water | SOS | Start on Site | 2023-03-06 | 2023-03-05 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS506234 | 506234 | RCI Luing DMA Cullipool | Water | SOS | Start on Site | 2021-10-26 | 2021-10-26 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS506232 | 506232 | RCI Kinlochleven DMA | Water | SOS | Start on Site | 2021-10-11 | 2021-10-11 | 2021_22_P07 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
SOS506228 | 506228 | RCI Bowmore DMA (Torra Mains) | Water | SOS | Start on Site | 2021-10-11 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS506231 | 506231 | RCI Eathie DMA (Muirhead Farm and Eathie Mains) | Water | SOS | Start on Site | 2023-01-16 | 2023-01-09 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS506275 | 506275 | RCI Tore and Drumderfit DMA (Tore to Kessock) | Water | SOS | Start on Site | 2022-06-27 | 2022-06-27 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS506271 | 506271 | RCI Bragar DMA (West Lewis WOA) | Water | SOS | Start on Site | 2022-11-01 | 2022-11-28 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
SOS506422 | 506422 | Business Management System | Support Services | SOS | Start on Site | 2022-09-26 | 2022-10-01 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
SOS506608 | 506608 | E-W-NI-140520-Craighead WTW - Upgrade Mn removal - Covid 19 - 66 | Water | SOS | Start on Site | 2022-06-10 | 2022-06-20 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS506618 | 506618 | RCI Kinlochbervie DMA (Kinlochbervie WOA) | Water | SOS | Start on Site | 2022-07-12 | 2022-07-26 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
SOS506684 | 506684 | Repair at Glenhove DSR 2 | Water | SOS | Start on Site | 2021-04-05 | 2021-03-23 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS506779 | 506779 | Stoneybridge WTW - Essential Capital Maintenance | Water | SOS | Start on Site | 2021-10-11 | 2021-11-01 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS507057 | 507057 | RCI Catterthun DMA Craigton of Monikie | Water | SOS | Start on Site | 2022-05-30 | 2022-05-23 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS507186 | 507186 | RCI Craigie DMA Plewlands | Water | SOS | Start on Site | 2022-01-10 | 2022-01-24 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS507189 | 507189 | RCI Rossie DMA Ethie PMA | Water | SOS | Start on Site | 2022-03-30 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
SOS507493 | 507493 | RCI SR21 ES Mains of Moyness - Non DMA Phase 2 | Water | SOS | Start on Site | 2022-09-12 | 2022-09-26 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS507808 | 507808 | Croy WwTW - Growth | Wastewater | SOS | Start on Site | 2023-11-06 | 2023-11-06 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3
SOS507933 | 507933 | Catrineholm WwTW- Emergency Project to Maintain CAR Licence Compliance | Wastewater | SOS | Start on Site | 2021-10-22 | 2021-11-19 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS508109 | 508109 | Microsoft Teams | Support Services | SOS | Start on Site | 2021-04-19 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
SOS508601 | 508601 | SR15 Milnbe Weir Eel Pass PPD | Wastewater | SOS | Start on Site | 2021-11-02 | 2022-01-10 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
SOS508752 | 508752 | E-WW-NI-150920-PERTH CITY WWTW-IFAS | Wastewater | SOS | Start on Site | 2022-11-04 | 2022-08-31 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
SOS509283 | 509283 | Simple Repair at Peterhead Newfield DSR | Water | SOS | Start on Site | 2021-04-12 | 2021-02-15 | 2021_22_P01 | 2020_21_P11 | 2021_22_Q1 | 2020_21_Q4
SOS510392 | 510392 | Oban, Stevenson Street SPS - Replace Screw Pumps | Wastewater | SOS | Start on Site | 2022-10-25 | 2022-10-24 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
SOS510727 | 510727 | Infrastructure Tactical Project | Support Services | SOS | Start on Site | 2021-12-13 | 2021-11-09 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS510931 | 510931 | Dores DMA - Mains Rehab | Water | SOS | Start on Site | 2022-09-12 | 2022-09-12 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS511334 | 511334 | RCI Clachan DMA Longrigg | Water | SOS | Start on Site | 2022-10-10 | 2022-10-19 | 2022_23_P07 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
SOS511344 | 511344 | Field Service Transformation Project | Support Services | SOS | Start on Site | 2022-08-24 | 2021-04-30 | 2022_23_P05 | 2021_22_P01 | 2022_23_Q2 | 2021_22_Q1
SOS511495 | 511495 | SR21 Core WTW pilots - Chlorine Dioxide | Water | SOS | Start on Site | 2023-02-20 | 2023-02-13 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS511500 | 511500 | SR21 Core WTW pilots - Ozone GAC | Water | SOS | Start on Site | 2023-01-11 | 2022-12-12 | 2022_23_P10 | 2022_23_P09 | 2022_23_Q4 | 2022_23_Q3
SOS511704 | 511704 | RCI Comrie and Bogside DMA Righead Farm | Water | SOS | Start on Site | 2022-11-28 | 2022-11-28 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
SOS512469 | 512469 | SR21 Core WTW Pilots - Filter Columns | Water | SOS | Start on Site | 2023-01-16 | 2023-01-19 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS512600 | 512600 | ICF - NIA0157 Glencorse WOA - Danderhall and Gilmerton DMAs - Solution 01 | Water | SOS | Start on Site | 2022-04-04 | 2022-04-04 | 2022_23_P01 | 2022_23_P01 | 2022_23_Q1 | 2022_23_Q1
SOS512639 | 512639 | Server and Storage Project | Support Services | SOS | Start on Site | 2022-08-08 | 2022-09-01 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS512749 | 512749 | RCI Benbecula DMA Ceann a Bunteag | Water | SOS | Start on Site | 2022-05-25 | 2022-07-29 | 2022_23_P02 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2
SOS512711 | 512711 | WQ Mains Rehabilitation Ph1 Ma2b Patna DMA | Water | SOS | Start on Site | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS512815 | 512815 | RCI Garelochhead Shandon DMA Faslane Diversion | Water | SOS | Start on Site | 2023-05-18 | 2023-05-18 | 2023_24_P02 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
SOS512940 | 512940 | RCI Bixter Tresta and Sandsound DMA Effirth | Water | SOS | Start on Site | 2023-01-09 | 2023-01-30 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS512997 | 512997 | ICF - Nairn Water Main Upgrade - Galantray Element | Water | SOS | Start on Site | 2023-08-17 | 2023-07-17 | 2023_24_P05 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS513208 | 513208 | SR21 Carron Valley WTW - Air Curtain | Water | SOS | Start on Site | 2023-03-21 | 2023-01-12 | 2022_23_P12 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS513312 | 513312 | Hydro Nation Chair | CE&FS | SOS | Start on Site | 2021-06-22 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
SOS513433 | 513433 | SR21 Glenfarg WTW - Air Curtain | Water | SOS | Start on Site | 2023-05-18 | 2023-05-18 | 2023_24_P02 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
SOS513461 | 513461 | Inverness Laboratory Extension | Support Services | SOS | Start on Site | 2022-03-21 | 2022-01-26 | 2021_22_P12 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
SOS513826 | 513826 | RCI Newfield PS To Broadmuir TM DMA Hatton Hotspot | Water | SOS | Start on Site | 2022-11-07 | 2022-10-23 | 2022_23_P08 | 2022_23_P07 | 2022_23_Q3 | 2022_23_Q3
SOS513832 | 513832 | Non-Complex Service Delivery (NCSD) Phase 3 | Support Services | SOS | Start on Site | 2021-08-17 | 2021-08-23 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
SOS513923 | 513923 | Black Isle Trunk Main - Valve Replacement | Water | SOS | Start on Site | 2021-11-15 | 2021-11-25 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
SOS514041 | 514041 | C-WW-NI-Management of Wastewater Temporary Process Units - Aberuthven STW | Wastewater | SOS | Start on Site | 2023-04-10 | 2023-04-30 | 2023_24_P01 | 2023_24_P01 | 2023_24_Q1 | 2023_24_Q1
SOS514047 | 514047 | RCI Stornoway Point DMA Bayble | Water | SOS | Start on Site | 2023-01-09 | 2022-11-30 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
SOS514080 | 514080 | RCI Dolphinton Line DMA | Water | SOS | Start on Site | 2023-04-24 | 2023-03-20 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
SOS514217 | 514217 | E-WW-NI-140721-Inverurie Old STW Redundant Assets Demo | Wastewater | SOS | Start on Site | 2022-11-01 | 2022-11-07 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
SOS514441 | 514441 | Digital Securing Operational Assets | Support Services | SOS | Start on Site | 2023-02-02 | 2023-02-02 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS514448 | 514448 | EFOS - Main Street Bridge of Weir - 281-1 | Wastewater | SOS | Start on Site | 2023-11-22 | 2023-11-22 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3
SOS514598 | 514598 | Networks Refresh Project | Support Services | SOS | Start on Site | 2022-12-28 | 2023-01-01 | 2022_23_P09 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4
SOS514631 | 514631 | E-WWNI-050821-Kirkcaldy STW-Renew media in 1st stage biopur (BAFF) process | Wastewater | SOS | Start on Site | 2022-09-16 | 2022-09-16 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
SOS515139 | 515139 | Dirty Dam - Silt removal | Water | SOS | Start on Site | 2023-03-31 | 2023-03-29 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS515505 | 515505 | SR21 Eela WTW Interim Measures | Water | SOS | Start on Site | 2022-04-11 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
SOS515607 | 515607 | C-WW-NI-MCC Replacement – Pitmedden STW | Wastewater | SOS | Start on Site | 2023-06-05 | 2023-03-20 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
SOS515625 | 515625 | rDWD Implementation - Juniper House | Support Services | SOS | Start on Site | 2022-12-19 | 2022-12-13 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
SOS516045 | 516045 | TWS Tiree WTW CWBT Replacement | Water | SOS | Start on Site | 2023-04-10 | 2023-03-31 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
SOS516085 | 516085 | Milngavie WTW - replace hypo bulk tank 2 | Water | SOS | Start on Site | 2023-06-16 | 2023-06-16 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
SOS516502 | 516502 | SR21 Black Esk WTW - Manganese Monitors | Water | SOS | Start on Site | 2022-06-23 | 2022-06-23 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
SOS516659 | 516659 | Greater Glasgow Bioresource Treatment Project | Wastewater | SOS | Start on Site | 2023-01-31 | 2022-12-21 | 2022_23_P10 | 2022_23_P09 | 2022_23_Q4 | 2022_23_Q3
SOS517533 | 517533 | SR21 Islay Flow Gauging | Water | SOS | Start on Site | 2022-07-11 | 2022-07-11 | 2022_23_P04 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
SOS518244 | 518244 | Shieldhall WWTW - PST Maintenance Bays - Replacement | Wastewater | SOS | Start on Site | 2023-02-06 | 2023-02-20 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS518444 | 518444 | Orkney Sludge Trial Enabling Works | Water | SOS | Start on Site | 2023-01-19 | 2023-01-19 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS518591 | 518591 | Cults Pitfodels TWP - Replace MCC | Water | SOS | Start on Site | 2023-10-06 | 2023-10-06 | 2023_24_P07 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3
SOS518579 | 518579 | Shieldhall WWTW - cleaning of Inlet Delta Storm Bypass Culvert and Velocity Channels at Pre-Sed Bldng | Wastewater | SOS | Start on Site | 2022-11-01 | 2022-09-26 | 2022_23_P08 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2
SOS520228 | 520228 | NCSD Need4621 Loch Turret investigation overpumping drought periods | Water | SOS | Start on Site | 2023-03-17 | 2023-03-14 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS520229 | 520229 | Non Complex Service Delivery (NCSD) Phase 3 Implementation | Support Services | SOS | Start on Site | 2022-06-10 | 2022-05-30 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
SOS520459 | 520459 | Apex Applications Replacement | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-01 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS520500 | 520500 | E-WW-NI-070422-Banchory STW Chemical Dosing | Wastewater | SOS | Start on Site | 2023-07-10 | 2023-07-10 | 2023_24_P04 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
SOS520606 | 520606 | RCI Colmonell DMA | Water | SOS | Start on Site | 2023-01-09 | 2023-01-25 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS520761 | 520761 | Field Connectivity Project | Support Services | SOS | Start on Site | 2023-01-23 | 2023-01-01 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS522707 | 522707 | Redcraigs DSR - Rationalisation | Water | SOS | Start on Site | 2023-06-05 | 2023-06-05 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
SOS523508 | 523508 | Powfoot SEP - Refurbish Reed Beds | Wastewater | SOS | Start on Site | 2023-02-13 | 2023-02-06 | 2022_23_P11 | 2022_23_P11 | 2022_23_Q4 | 2022_23_Q4
SOS524913 | 524913 | SW Reporting Redefined | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-01 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS524914 | 524914 | Open Data | Support Services | SOS | Start on Site | 2023-03-13 | 2023-03-22 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS525189 | 525189 | Saltcoats Stormflow WWPS Rising Main Replacement - Emergency Works | Wastewater | SOS | Start on Site | 2023-03-31 | 2023-03-31 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
SOS527220 | 527220 | SIP Yr 3 OKR Delivery | Support Services | SOS | Start on Site | 2023-01-23 | 2023-01-31 | 2022_23_P10 | 2022_23_P10 | 2022_23_Q4 | 2022_23_Q4
SOS528868 | 528868 | WQ Carron Valley WOA Discolouration Management Plan Delivery | Water | SOS | Start on Site | 2023-06-12 | 2023-06-12 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
G100046172 | 046172 | Distribution Water Quality Rehab - Kirbister Orkney RSZ | Water | G100 | Gate 100 | 2021-09-01 | 2021-10-05 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3
G100400324 | 400324 | NRSWA C3 Service Relocate Edinburgh Tram Lines Mains Diversion | Water | G100 | Gate 100 | 2023-04-14 | 2023-02-01 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G100401795 | 401795 | S157 UID Seedhill No1 CSO West of 6 Seedhill at Mill Street Paisley | Wastewater | G100 | Gate 100 | 2021-07-06 | 2021-06-28 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100401705 | 401705 | S087 - UID - Scotwood Overflow North East of Lay-by Busby Road | Wastewater | G100 | Gate 100 | 2021-10-24 | 2023-11-24 | 2021_22_P07 | 2023_24_P08 | 2021_22_Q3 | 2023_24_Q3
G100401687 | 401687 | S048 - UID - Farme Estate PS EO Downiebrae Road Shieldhall No.40 | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100401668 | 401668 | S043 - UID - Cambuslang Road Richmond Laundry - South East of Railway Rutherglen | Wastewater | G100 | Gate 100 | 2021-09-20 | 2023-09-01 | 2021_22_P06 | 2023_24_P06 | 2021_22_Q2 | 2023_24_Q2
G100401685 | 401685 | S046 - UID - Downiebrae Road Farme Estate Shieldhall No 39 | Wastewater | G100 | Gate 100 | 2021-09-20 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100402197 | 402197 | Sewer Flooding Burnbank Street Airdrie | Wastewater | G100 | Gate 100 | 2021-05-11 | 2021-04-30 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100403238 | 403238 | SR15 ES - E016 Field off North Park Avenue CSO | Wastewater | G100 | Gate 100 | 2021-08-16 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403104 | 403104 | QS3b AR - P012 UID 317 Northwoodside Road Glasgow | Wastewater | G100 | Gate 100 | 2021-09-01 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100403090 | 403090 | QS3b AR - Kaim WTW | Water | G100 | Gate 100 | 2021-06-30 | 2021-05-31 | 2021_22_P03 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100403100 | 403100 | QS3b AR - P008 UID At West Bank of Footbridge BGs Addison Road | Wastewater | G100 | Gate 100 | 2021-08-21 | 2021-09-24 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403103 | 403103 | QS3b AR - P011 UID Queen Margaret Road Bridge CSO at Botanical Gardens | Wastewater | G100 | Gate 100 | 2021-09-26 | 2021-03-31 | 2021_22_P06 | 2020_21_P12 | 2021_22_Q2 | 2020_21_Q4
G100403098 | 403098 | QS3b AR - P006 UID Near the Junction of Kelvindale Road and Balfour Street | Wastewater | G100 | Gate 100 | 2021-12-01 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100403101 | 403101 | QS3b AR - P009 UID North of Playground off Garriochmill Road | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100403102 | 403102 | QS3b AR - P010 UID Botanic Gardens Nr Junc of Garrioch Drive Garrioch Rd and Shakespeare St | Wastewater | G100 | Gate 100 | 2021-08-24 | 2021-09-21 | 2021_22_P05 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100402949 | 402949 | SR15 ES - LRC3 Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall Development | Wastewater | G100 | Gate 100 | 2022-10-21 | 2022-07-29 | 2022_23_P07 | 2022_23_P04 | 2022_23_Q3 | 2022_23_Q2
G100403321 | 403321 | SR15 ES - Craigneuk Avenue Airdrie Internal and External Flooding | Wastewater | G100 | Gate 100 | 2022-08-27 | 2023-01-31 | 2022_23_P05 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100403106 | 403106 | QS3b AR - P014 UID Westbank Quadrant at Eldon Street Bridge CSO NS273667 | Wastewater | G100 | Gate 100 | 2023-01-31 | 2023-09-15 | 2022_23_P10 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G100403658 | 403658 | Darnley Mains Development - Trunk Mains Diversion | Water | G100 | Gate 100 | 2022-09-30 | 2023-02-23 | 2022_23_P06 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4
G100403716 | 403716 | SR15 ES - Sanday Sludge Storage Area and Drying Beds | Wastewater | G100 | Gate 100 | 2023-02-22 | 2022-11-23 | 2022_23_P11 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G100500046 | 500046 | Improvement to Supply-Demand Balance - Stornoway WRZ | Water | G100 | Gate 100 | 2024-08-18 | 2022-03-10 | 2024_25_P05 | 2021_22_P12 | 2024_25_Q2 | 2021_22_Q4
G100403127 | 403127 | SR15 ES - Loch Ness Regional WTW Scheme | Water | G100 | Gate 100 | 2022-01-31 | 2023-03-30 | 2021_22_P10 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4
G100403532 | 403532 | SR15 ES - Kyle of Lochalsh WTW - Water Resource Strategic Study | Water | G100 | Gate 100 | 2021-10-01 | 2022-01-21 | 2021_22_P07 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100500060 | 500060 | FRMA Improvements | Water | G100 | Gate 100 | 2021-05-12 | 2021-04-01 | 2021_22_P02 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100403934 | 403934 | Blairythan Terrace Foveran ST Growth | Wastewater | G100 | Gate 100 | 2022-07-04 | 2023-01-18 | 2022_23_P04 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100404026 | 404026 | SR15 ES - Main Street Newtonmore | Wastewater | G100 | Gate 100 | 2022-06-20 | 2024-08-16 | 2022_23_P03 | 2024_25_P05 | 2022_23_Q1 | 2024_25_Q2
G100403902 | 403902 | Ellon WwTW - Growth | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-08-29 | 2021_22_P08 | 2022_23_P05 | 2021_22_Q3 | 2022_23_Q2
G100403995 | 403995 | SR15 ES - Londornoch WTW | Water | G100 | Gate 100 | 2024-10-17 | 2026-02-12 | 2024_25_P07 | 2025_26_P11 | 2024_25_Q3 | 2025_26_Q4
G100403991 | 403991 | SR15 ES - Newmore WTW - WQ and Essential Related CM Upgrade | Water | G100 | Gate 100 | 2023-01-30 | 2023-10-23 | 2022_23_P10 | 2023_24_P07 | 2022_23_Q4 | 2023_24_Q3
G100403994 | 403994 | SR15 ES - Uig WTW - SR15 WQ | Water | G100 | Gate 100 | 2022-02-25 | 2023-04-28 | 2021_22_P11 | 2023_24_P01 | 2021_22_Q4 | 2023_24_Q1
G100500017 | 500017 | W473 - Conon Avenue | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100403923 | 403923 | SR15 ES - E1618 - Rose Street Annan 14 33 and 35 | Wastewater | G100 | Gate 100 | 2022-06-30 | 2023-02-22 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4
G100403967 | 403967 | Winchburgh WwTW - Growth | Wastewater | G100 | Gate 100 | 2024-09-09 | 2024-07-30 | 2024_25_P06 | 2024_25_P04 | 2024_25_Q2 | 2024_25_Q2
G100403939 | 403939 | Stewarton WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-05-05 | 2023-05-02 | 2022_23_P02 | 2023_24_P02 | 2022_23_Q1 | 2023_24_Q1
G100403781 | 403781 | Aberchirder WwTW Growth | Wastewater | G100 | Gate 100 | 2021-09-16 | 2021-07-20 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100403782 | 403782 | Kennethmont WwTW Growth | Wastewater | G100 | Gate 100 | 2023-05-01 | 2024-01-25 | 2023_24_P02 | 2023_24_P10 | 2023_24_Q1 | 2023_24_Q4
G100404093 | 404093 | SR15 ES - Greenock WTW - SCADA Replacement | Water | G100 | Gate 100 | 2023-08-23 | 2024-01-03 | 2023_24_P05 | 2023_24_P10 | 2023_24_Q2 | 2023_24_Q4
G100403943 | 403943 | Canonbie WwTW - Upgrade Growth (Transfer from 403465) | Wastewater | G100 | Gate 100 | 2021-11-18 | 2023-03-29 | 2021_22_P08 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4
G100500047 | 500047 | Roberton WTW | Water | G100 | Gate 100 | 2022-10-07 | 2022-11-25 | 2022_23_P07 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G100404003 | 404003 | SR15 ES - PSCD Bradan Trunk Main - Close Proximity Diversions | Water | G100 | Gate 100 | 2021-04-01 | 2021-11-19 | 2021_22_P01 | 2021_22_P08 | 2021_22_Q1 | 2021_22_Q3
G100404134 | 404134 | Tomatin WTW - Cartridge Filters and UV | Water | G100 | Gate 100 | 2021-06-17 | 2021-10-01 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G100404135 | 404135 | Dalwhinnie WTW - TTU | Water | G100 | Gate 100 | 2023-01-27 | 2024-06-07 | 2022_23_P10 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1
G100500052 | 500052 | Carstairs Village WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-07-30 | 2023-06-05 | 2022_23_P04 | 2023_24_P03 | 2022_23_Q2 | 2023_24_Q1
G100500040 | 500040 | Bradan RSZ Cleaning Programme | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-30 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100403986 | 403986 | SR15 ES - Carron Valley WTW Scada Replacement | Water | G100 | Gate 100 | 2023-04-14 | 2023-03-28 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100500218 | 500218 | Inverness - DW5 Interventions | Water | G100 | Gate 100 | 2022-02-15 | 2021-12-21 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100500068 | 500068 | Newtown St Boswells WwTW - Growth | Wastewater | G100 | Gate 100 | 2021-06-23 | 2021-06-29 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100404069 | 404069 | Aviemore WwTW - Growth | Wastewater | G100 | Gate 100 | 2021-04-30 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500235 | 500235 | Hatton of Cruden WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-06-03 | 2022-11-28 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G100500207 | 500207 | Muirdykes- DW5 Interventions | Water | G100 | Gate 100 | 2021-06-01 | 2021-10-21 | 2021_22_P03 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G100500246 | 500246 | Ringford WTW | Water | G100 | Gate 100 | 2021-10-22 | 2023-05-22 | 2021_22_P07 | 2023_24_P02 | 2021_22_Q3 | 2023_24_Q1
G100500229 | 500229 | East Linton WwTW - Growth | Wastewater | G100 | Gate 100 | 2023-07-28 | 2024-11-13 | 2023_24_P04 | 2024_25_P08 | 2023_24_Q2 | 2024_25_Q3
G100404007 | 404007 | SR15 ES - Laighpark Paisley WWTW NS485655 | Wastewater | G100 | Gate 100 | 2022-02-18 | 2021-09-30 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2
G100500573 | 500573 | Tullich WOA - Oban North and South TWS Refurbishment | Water | G100 | Gate 100 | 2022-06-28 | 2022-08-30 | 2022_23_P03 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G100500575 | 500575 | Muirdykes WTW CM | Water | G100 | Gate 100 | 2022-08-22 | 2022-12-01 | 2022_23_P05 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3
G100500576 | 500576 | Orphir Village WwTW - Enforcement Mitigations | Wastewater | G100 | Gate 100 | 2024-06-17 | 2024-02-02 | 2024_25_P03 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G100500665 | 500665 | E1282 Carronflats Road Grangemouth | Wastewater | G100 | Gate 100 | 2022-01-16 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G100404132 | 404132 | Picketlaw WTW - Main Out | Water | G100 | Gate 100 | 2026-02-15 | 2025-05-20 | 2025_26_P11 | 2025_26_P02 | 2025_26_Q4 | 2025_26_Q1
G100500302 | 500302 | W462 - Coalburn Road Coalburn | Wastewater | G100 | Gate 100 | 2022-06-30 | 2023-05-15 | 2022_23_P03 | 2023_24_P02 | 2022_23_Q1 | 2023_24_Q1
G100500523 | 500523 | Ayrshire Strategic Resilience | Water | G100 | Gate 100 | 2023-09-20 | 2024-09-09 | 2023_24_P06 | 2024_25_P06 | 2023_24_Q2 | 2024_25_Q2
G100500509 | 500509 | South Edinburgh Service Resilience | Water | G100 | Gate 100 | 2021-08-24 | 2024-05-24 | 2021_22_P05 | 2024_25_P02 | 2021_22_Q2 | 2024_25_Q1
G100500299 | 500299 | E117 Brown Street Armadale | Wastewater | G100 | Gate 100 | 2021-10-20 | 2021-08-31 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2
G100500245 | 500245 | Galashiels Manse Street WTW | Water | G100 | Gate 100 | 2022-08-17 | 2023-11-08 | 2022_23_P05 | 2023_24_P08 | 2022_23_Q2 | 2023_24_Q3
G100500947 | 500947 | OD Dumfries Office Marchmount and Lincluden Depots | Support Services | G100 | Gate 100 | 2021-06-16 | 2022-03-03 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100500233 | 500233 | Burrelton WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-01-14 | 2023-06-22 | 2021_22_P10 | 2023_24_P03 | 2021_22_Q4 | 2023_24_Q1
G100500654 | 500654 | SE246 - Burnswark View Eaglesfield | Wastewater | G100 | Gate 100 | 2022-01-29 | 2023-01-31 | 2021_22_P10 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4
G100500579 | 500579 | Kinneil Kerse WwTW - Capital Maintenance | Wastewater | G100 | Gate 100 | 2022-03-31 | 2023-03-17 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4
G100500742 | 500742 | Loch Calder WTW Disinfection Replacement | Water | G100 | Gate 100 | 2021-04-30 | 2021-07-14 | 2021_22_P01 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100501001 | 501001 | SR15 TE CM Staney Hill North - Q Sandy Loch WTW | Water | G100 | Gate 100 | 2023-02-16 | 2025-04-15 | 2022_23_P11 | 2025_26_P01 | 2022_23_Q4 | 2025_26_Q1
G100500652 | 500652 | SE847 Church Street Harbour Road Eyemouth | Wastewater | G100 | Gate 100 | 2021-11-09 | 2022-03-17 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100500655 | 500655 | Barmore Road Tarbert | Wastewater | G100 | Gate 100 | 2022-03-28 | 2021-10-29 | 2021_22_P12 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3
G100500784 | 500784 | Springfield WwTW | Wastewater | G100 | Gate 100 | 2021-04-23 | 2021-06-15 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100500687 | 500687 | Whitecraigs Court Giffnock | Wastewater | G100 | Gate 100 | 2021-09-24 | 2021-07-29 | 2021_22_P06 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100404082 | 404082 | Loch Eck Caustic and Hypo Dosing Upgrade | Water | G100 | Gate 100 | 2021-09-10 | 2021-04-26 | 2021_22_P06 | 2021_22_P01 | 2021_22_Q2 | 2021_22_Q1
G100500709 | 500709 | Bradan WTW CM | Water | G100 | Gate 100 | 2021-10-11 | 2022-12-23 | 2021_22_P07 | 2022_23_P09 | 2021_22_Q3 | 2022_23_Q3
G100500496 | 500496 | Lockerbie WWTW | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-26 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500681 | 500681 | SW843 Wellgate Lanark | Wastewater | G100 | Gate 100 | 2022-09-14 | 2023-08-11 | 2022_23_P06 | 2023_24_P05 | 2022_23_Q2 | 2023_24_Q2
G100500661 | 500661 | E1010 Craigleith Road Edinburgh | Wastewater | G100 | Gate 100 | 2022-09-22 | 2023-01-31 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G100500662 | 500662 | W646 - Brandon Gardens Prestwick | Wastewater | G100 | Gate 100 | 2021-11-24 | 2022-01-26 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100500771 | 500771 | Westhill Service Reservoir | Water | G100 | Gate 100 | 2021-06-14 | 2021-12-21 | 2021_22_P03 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G100500682 | 500682 | SW857 - Townhead Street Stonehouse | Wastewater | G100 | Gate 100 | 2022-09-07 | 2023-02-28 | 2022_23_P06 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4
G100500892 | 500892 | Cowsrieve Service Reservoir | Water | G100 | Gate 100 | 2022-06-27 | 2023-08-01 | 2022_23_P03 | 2023_24_P05 | 2022_23_Q1 | 2023_24_Q2
G100500755 | 500755 | North Coast SCADA Replacement | Water | G100 | Gate 100 | 2023-11-13 | 2024-05-09 | 2023_24_P08 | 2024_25_P02 | 2023_24_Q3 | 2024_25_Q1
G100501216 | 501216 | Lintrathen WTW - QUALITY Disinfection | Water | G100 | Gate 100 | 2021-11-18 | 2022-03-22 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100500707 | 500707 | Longforgan Station Road WWPS 1995 NO316293 SR15 Capital Maintenance | Wastewater | G100 | Gate 100 | 2021-07-14 | 2021-06-14 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100500580 | 500580 | Forres WWTW 1973 NJ038595 - SR15 Capital Maintenance | Wastewater | G100 | Gate 100 | 2022-10-30 | 2023-08-25 | 2022_23_P07 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2
G100500958 | 500958 | Sandy Loch WTW Additional RGF - CM | Water | G100 | Gate 100 | 2021-07-08 | 2022-01-13 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100500694 | 500694 | Bo ness WWTW NT022813 | Wastewater | G100 | Gate 100 | 2021-11-22 | 2022-09-30 | 2021_22_P08 | 2022_23_P06 | 2021_22_Q3 | 2022_23_Q2
G100500695 | 500695 | St Andrews WwTW and St Andrews STC SR15-CM | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500723 | 500723 | Alford WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-01-26 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G100500724 | 500724 | Udny Green WwTW - Growth | Wastewater | G100 | Gate 100 | 2025-01-07 | 2024-10-24 | 2024_25_P10 | 2024_25_P07 | 2024_25_Q4 | 2024_25_Q3
G100501019 | 501019 | E1460 - Yetholm Park Dunfermline | Wastewater | G100 | Gate 100 | 2021-05-29 | 2021-03-12 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100500729 | 500729 | Boughden Braes Lesmahagow Sewer Replacement | Wastewater | G100 | Gate 100 | 2024-11-10 | 2024-04-19 | 2024_25_P08 | 2024_25_P01 | 2024_25_Q3 | 2024_25_Q1
G100500918 | 500918 | Glendye - Belts of Collonach & Woodlands TM Rehabilitation | Water | G100 | Gate 100 | 2022-05-31 | 2022-07-22 | 2022_23_P02 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2
G100501151 | 501151 | Cargenbridge SPS | Wastewater | G100 | Gate 100 | 2021-05-25 | 2021-06-28 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501040 | 501040 | North Ronaldsay WTW Quality | Water | G100 | Gate 100 | 2021-05-31 | 2021-06-30 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501200 | 501200 | Whitehall DSR CM | Water | G100 | Gate 100 | 2022-04-25 | 2022-08-31 | 2022_23_P01 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G100501070 | 501070 | Kirkmichael WTW - CM | Water | G100 | Gate 100 | 2021-10-22 | 2027-04-01 | 2021_22_P07 | 2027_28_P01 | 2021_22_Q3 | 2027_28_Q1
G100501017 | 501017 | SW1015 - Shieldaig Road, Glasgow | Wastewater | G100 | Gate 100 | 2023-11-02 | 2023-10-27 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3
G100500896 | 500896 | Craighead WTW - CM | Water | G100 | Gate 100 | 2022-11-07 | 2023-06-26 | 2022_23_P08 | 2023_24_P03 | 2022_23_Q3 | 2023_24_Q1
G100501390 | 501390 | WTW000627 - ROSEBERY WTW 1940 NT305570 | Water | G100 | Gate 100 | 2022-11-10 | 2023-11-24 | 2022_23_P08 | 2023_24_P08 | 2022_23_Q3 | 2023_24_Q3
G100501290 | 501290 | Ardersier WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-07-30 | 2022-10-31 | 2022_23_P04 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G100501153 | 501153 | Kirkconnel STW | Wastewater | G100 | Gate 100 | 2021-09-28 | 2022-10-31 | 2021_22_P06 | 2022_23_P07 | 2021_22_Q2 | 2022_23_Q3
G100501217 | 501217 | Glenlatterach WTW Manganese Removal | Water | G100 | Gate 100 | 2021-08-31 | 2023-04-03 | 2021_22_P05 | 2023_24_P01 | 2021_22_Q2 | 2023_24_Q1
G100501091 | 501091 | Eela Water WTW QUALITY | Water | G100 | Gate 100 | 2022-01-12 | 2021-08-23 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G100500731 | 500731 | Newmachar WwTW - Growth | Wastewater | G100 | Gate 100 | 2024-09-10 | 2024-11-04 | 2024_25_P06 | 2024_25_P08 | 2024_25_Q2 | 2024_25_Q3
G100501219 | 501219 | Daer WTW - Improving WQ in Network (OMG5) | Water | G100 | Gate 100 | 2021-07-01 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100501146 | 501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Water | G100 | Gate 100 | 2021-04-30 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100500893 | 500893 | Craigmaddie and Milngavie VT Works | Water | G100 | Gate 100 | 2023-12-21 | 2023-09-07 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100501159 | 501159 | Alloa STW | Wastewater | G100 | Gate 100 | 2023-06-20 | 2025-10-09 | 2023_24_P03 | 2025_26_P07 | 2023_24_Q1 | 2025_26_Q3
G100501168 | 501168 | Ochiltree STW | Wastewater | G100 | Gate 100 | 2022-05-30 | 2022-05-31 | 2022_23_P02 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G100501169 | 501169 | Meadowhead STW | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-05-10 | 2021_22_P01 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100501144 | 501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Water | G100 | Gate 100 | 2022-01-21 | 2022-02-21 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G100501233 | 501233 | Herricks WTW - QUALITY | Water | G100 | Gate 100 | 2021-07-30 | 2021-05-17 | 2021_22_P04 | 2021_22_P02 | 2021_22_Q2 | 2021_22_Q1
G100501599 | 501599 | Southpark Avenue Barrhead Repair Sewer | Wastewater | G100 | Gate 100 | 2021-06-30 | 2023-03-09 | 2021_22_P03 | 2022_23_P12 | 2021_22_Q1 | 2022_23_Q4
G100501352 | 501352 | Battery Park WWPS | Wastewater | G100 | Gate 100 | 2021-12-09 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100501158 | 501158 | Ardoch STW | Wastewater | G100 | Gate 100 | 2021-06-03 | 2022-03-01 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100501021 | 501021 | Banchory WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-03-31 | 2023-06-09 | 2021_22_P12 | 2023_24_P03 | 2021_22_Q4 | 2023_24_Q1
G100501518 | 501518 | STEVENSTON POINT WWTW NS275404 | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-12-20 | 2021_22_P06 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100501232 | 501232 | Whitehillocks WTW - Quality and CM | Water | G100 | Gate 100 | 2022-02-02 | 2023-12-18 | 2021_22_P11 | 2023_24_P09 | 2021_22_Q4 | 2023_24_Q3
G100501165 | 501165 | Rothesay STW | Wastewater | G100 | Gate 100 | 2021-06-16 | 2021-03-30 | 2021_22_P03 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501218 | 501218 | Badentinan WTW - Quality | Water | G100 | Gate 100 | 2021-08-27 | 2021-11-17 | 2021_22_P05 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100501156 | 501156 | Tillicoultry STW | Wastewater | G100 | Gate 100 | 2021-10-11 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100501402 | 501402 | DALMACOULTER DSR NS767679 | Water | G100 | Gate 100 | 2021-05-07 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501512 | 501512 | INSH WWTW 1996 NH809016 | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-03-20 | 2024_25_P01 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4
G100501720 | 501720 | Cambuslang SPS 2 RM - Replace Rising Main | Wastewater | G100 | Gate 100 | 2021-08-30 | 2021-06-28 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100501632 | 501632 | CMA Market Releases | Support Services | G100 | Gate 100 | 2021-05-07 | 2021-06-02 | 2021_22_P02 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501635 | 501635 | Happendon - Camps TM Douglas Water Crossing | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-21 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501393 | 501393 | WTW000712 - HOWDEN WTW NT456275 | Water | G100 | Gate 100 | 2022-05-30 | 2023-07-24 | 2022_23_P02 | 2023_24_P04 | 2022_23_Q1 | 2023_24_Q2
G100501579 | 501579 | DALDERSE WWTW 1966 NS903822 | Wastewater | G100 | Gate 100 | 2022-12-30 | 2023-09-04 | 2022_23_P09 | 2023_24_P06 | 2022_23_Q3 | 2023_24_Q2
G100501379 | 501379 | WTW000640 - MARCHBANK WTW NT165645 | Water | G100 | Gate 100 | 2022-09-29 | 2023-09-01 | 2022_23_P06 | 2023_24_P06 | 2022_23_Q2 | 2023_24_Q2
G100501670 | 501670 | DAER WOA - Stablewood Pipe Bridge - H&S upgrade | Water | G100 | Gate 100 | 2024-09-08 | 2024-06-10 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G100501666 | 501666 | Hungry Snout | Water | G100 | Gate 100 | 2021-06-25 | 2022-07-15 | 2021_22_P03 | 2022_23_P04 | 2021_22_Q1 | 2022_23_Q2
G100501243 | 501243 | Invercannie WTW Pre-Treatment CWT and CM | Water | G100 | Gate 100 | 2023-02-01 | 2023-09-19 | 2022_23_P11 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G100501259 | 501259 | Backies WOA Brora Dalchalm and Victoria Road Mains Rehab | Water | G100 | Gate 100 | 2021-06-15 | 2021-07-19 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100501388 | 501388 | WTW000626 - PATESHILL WTW NS983595 | Water | G100 | Gate 100 | 2022-01-31 | 2023-04-28 | 2021_22_P10 | 2023_24_P01 | 2021_22_Q4 | 2023_24_Q1
G100501488 | 501488 | STRAN LARG ROAD WWPS No 1 NX048623 | Wastewater | G100 | Gate 100 | 2022-03-30 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100501499 | 501499 | PATNA WWTW NS414124 | Wastewater | G100 | Gate 100 | 2022-02-21 | 2022-08-31 | 2021_22_P11 | 2022_23_P05 | 2021_22_Q4 | 2022_23_Q2
G100501500 | 501500 | Earlston WwTW | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501592 | 501592 | EARLSTON WWTW 1959 NT573382 | Wastewater | G100 | Gate 100 | 2021-05-30 | 2021-05-20 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100501593 | 501593 | LUGAR WWPS NS585207 | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-04-01 | 2021_22_P01 | 2021_22_P01 | 2021_22_Q1 | 2021_22_Q1
G100501600 | 501600 | Glendevon WTW - Quality (Reduce high Production risks in DWSP) | Water | G100 | Gate 100 | 2021-07-12 | 2021-09-24 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100501639 | 501639 | Telemetry Application Consolidation | Support Services | G100 | Gate 100 | 2021-06-15 | 2021-09-06 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
G100501683 | 501683 | Shieldhall WWTW Grade 5 HC Sewer Ph1 | Wastewater | G100 | Gate 100 | 2021-11-30 | 2023-06-19 | 2021_22_P08 | 2023_24_P03 | 2021_22_Q3 | 2023_24_Q1
G100501731 | 501731 | Kerse TWS Refurb | Water | G100 | Gate 100 | 2024-08-01 | 2024-01-16 | 2024_25_P05 | 2023_24_P10 | 2024_25_Q2 | 2023_24_Q4
G100501436 | 501436 | 500788 - Alexandria WTW | Water | G100 | Gate 100 | 2021-04-28 | 2021-06-18 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501829 | 501829 | Daldowie WWTW Grade 5 HC Sewer | Wastewater | G100 | Gate 100 | 2021-12-11 | 2022-05-31 | 2021_22_P09 | 2022_23_P02 | 2021_22_Q3 | 2022_23_Q1
G100501703 | 501703 | Station Rd - Nairn Rd Ardersier - replace sewer | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-01-26 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4
G100501418 | 501418 | 500122 - Ness WTW | Water | G100 | Gate 100 | 2021-12-03 | 2023-04-03 | 2021_22_P09 | 2023_24_P01 | 2021_22_Q3 | 2023_24_Q1
G100501421 | 501421 | 500793 - Carrick Castle WTW | Water | G100 | Gate 100 | 2021-04-01 | 2021-06-11 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100501554 | 501554 | Carfin Incident - MD interventions | Water | G100 | Gate 100 | 2022-11-10 | 2023-01-31 | 2022_23_P08 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4
G100501739 | 501739 | Meadowhead WwTW HCS | Wastewater | G100 | Gate 100 | 2021-07-22 | 2022-11-25 | 2021_22_P04 | 2022_23_P08 | 2021_22_Q2 | 2022_23_Q3
G100501898 | 501898 | Cost Investment Intelligence Project for EES and SWISS Strategic Refresh Upgrade | Support Services | G100 | Gate 100 | 2021-09-29 | 2022-05-31 | 2021_22_P06 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1
G100502243 | 502243 | Mannofield WTW -Improvements to Treatment Process | Water | G100 | Gate 100 | 2024-12-01 | 2025-03-27 | 2024_25_P09 | 2024_25_P12 | 2024_25_Q3 | 2024_25_Q4
G100502231 | 502231 | South WWTW MCC Replacements Phase 1 | Wastewater | G100 | Gate 100 | 2021-04-02 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100501818 | 501818 | LIMS Refresh | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-30 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100502246 | 502246 | Rosebery WTW Lime to Caustic | Water | G100 | Gate 100 | 2021-07-12 | 2021-12-20 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100502267 | 502267 | HV Asset Replacement Phase 1 - Laighpark WwTW | Wastewater | G100 | Gate 100 | 2021-04-22 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502268 | 502268 | HV Asset Replacement Phase 1 - Shieldhall WwTW | Wastewater | G100 | Gate 100 | 2022-04-14 | 2023-03-23 | 2022_23_P01 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4
G100502132 | 502132 | Burncrooks WTW Quality THM Compliance | Water | G100 | Gate 100 | 2023-01-20 | 2024-02-12 | 2022_23_P10 | 2023_24_P11 | 2022_23_Q4 | 2023_24_Q4
G100502269 | 502269 | HV Asset Replacement Phase 1 - Stevenston Point WwTW | Wastewater | G100 | Gate 100 | 2021-04-12 | 2021-03-22 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502332 | 502332 | Drumnadrochit WwTW - Growth | Wastewater | G100 | Gate 100 | 2023-10-23 | 2023-07-21 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100502281 | 502281 | Savalbeg WTW Sludge Lagoon Upgrade | Wastewater | G100 | Gate 100 | 2021-11-19 | 2022-04-25 | 2021_22_P08 | 2022_23_P01 | 2021_22_Q3 | 2022_23_Q1
G100502280 | 502280 | Londornoch WTW Sludge Lagoon Upgrade | Wastewater | G100 | Gate 100 | 2022-03-07 | 2023-03-28 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4
G100502282 | 502282 | Oykel Bridge - Radon | Water | G100 | Gate 100 | 2023-09-14 | 2023-05-08 | 2023_24_P06 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100502220 | 502220 | IR18 Allowance - Edgehead Septic Tank | Wastewater | G100 | Gate 100 | 2025-08-17 | 2024-11-15 | 2025_26_P05 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3
G100502329 | 502329 | Loch Thom MIOS Drawdown & Freebaoard Enhancement | Water | G100 | Gate 100 | 2021-08-09 | 2021-08-24 | 2021_22_P05 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100502425 | 502425 | SW599 - Laighlands Road Bothwell | Wastewater | G100 | Gate 100 | 2024-08-14 | 2023-11-17 | 2024_25_P05 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3
G100502375 | 502375 | W574 1-21 Clarkston Road, Glasgow | Wastewater | G100 | Gate 100 | 2023-07-18 | 2022-12-06 | 2023_24_P04 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3
G100502212 | 502212 | IR18 Allowance - Newton Septic Tank | Wastewater | G100 | Gate 100 | 2023-10-24 | 2023-03-30 | 2023_24_P07 | 2022_23_P12 | 2023_24_Q3 | 2022_23_Q4
G100502342 | 502342 | MCC SR15- Hamilton WWTW MCC Replacement | Wastewater | G100 | Gate 100 | 2022-07-07 | 2022-11-25 | 2022_23_P04 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3
G100502584 | 502584 | Carbarns WwTW - Inlet Screen Replacement | Wastewater | G100 | Gate 100 | 2021-04-01 | 2021-03-24 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502578 | 502578 | Johnstone Black Cart Aerial Sewer | Wastewater | G100 | Gate 100 | 2022-04-27 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100502358 | 502358 | Black Esk and Winterhope WOA - Gretna Water Supply | Water | G100 | Gate 100 | 2024-06-06 | 2024-09-13 | 2024_25_P03 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2
G100502383 | 502383 | IR18 Allowance - Fife - Abstraction Improvement | Water | G100 | Gate 100 | 2021-12-20 | 2022-01-31 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100502412 | 502412 | Bradan WTW Water Quality | Water | G100 | Gate 100 | 2021-06-25 | 2021-08-03 | 2021_22_P03 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2
G100502380 | 502380 | IR18 Allowance - Forth Valley - Abstraction Improvement | Water | G100 | Gate 100 | 2021-04-01 | 2021-08-17 | 2021_22_P01 | 2021_22_P05 | 2021_22_Q1 | 2021_22_Q2
G100502382 | 502382 | IR18 Allowance - East Berwickshire - Abstraction Improvement | Water | G100 | Gate 100 | 2021-10-29 | 2022-03-24 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100502369 | 502369 | Beasdale WTW UV Alterations | Water | G100 | Gate 100 | 2024-08-15 | 2024-05-17 | 2024_25_P05 | 2024_25_P02 | 2024_25_Q2 | 2024_25_Q1
G100502895 | 502895 | SW1392 - Third Avenue Glasgow | Wastewater | G100 | Gate 100 | 2022-09-18 | 2022-11-29 | 2022_23_P06 | 2022_23_P08 | 2022_23_Q2 | 2022_23_Q3
G100502896 | 502896 | Barcraigs Drawdown Capacity Enhancement (MIoS) | Water | G100 | Gate 100 | 2021-10-12 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100502648 | 502648 | IR18 Allowance - Ardrishaig WTW | Water | G100 | Gate 100 | 2022-06-01 | 2023-09-13 | 2022_23_P03 | 2023_24_P06 | 2022_23_Q1 | 2023_24_Q2
G100502741 | 502741 | WATER OF LEITH UIDs BATCH 2 Currie Old Mill Off Lanark Road CSO and Juniper Green | Wastewater | G100 | Gate 100 | 2021-07-22 | 2021-06-02 | 2021_22_P04 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100502742 | 502742 | WATER OF LEITH UIDs BATCH 3 Juniper Green Off Lanark Road CSO | Wastewater | G100 | Gate 100 | 2021-10-14 | 2021-08-24 | 2021_22_P07 | 2021_22_P05 | 2021_22_Q3 | 2021_22_Q2
G100502747 | 502747 | WATER OF LEITH UIDs BATCH 8 Kingsknowe R 0 29 Dovecot Grove CSO | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502765 | 502765 | WATER OF LEITH UIDs - BATCH 9.2 - Currie GDN 2A Lanark Road West CSO | Wastewater | G100 | Gate 100 | 2021-10-26 | 2021-09-21 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G100502651 | 502651 | Afton WTW_Ayrshire_THM Research and Investigation | Water | G100 | Gate 100 | 2022-07-19 | 2023-12-22 | 2022_23_P04 | 2023_24_P09 | 2022_23_Q2 | 2023_24_Q3
G100502652 | 502652 | IR18 Allowance - Barra WTW | Water | G100 | Gate 100 | 2023-01-19 | 2023-03-28 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G100502827 | 502827 | Tarves WwTW - Growth | Wastewater | G100 | Gate 100 | 2022-01-13 | 2022-03-30 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100502780 | 502780 | Erskine WwTW Coarse Screens Replacement CM | Wastewater | G100 | Gate 100 | 2021-06-11 | 2021-06-28 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100502772 | 502772 | Daer WRZ SR Residual Chorine Monitors | Water | G100 | Gate 100 | 2021-05-11 | 2021-03-31 | 2021_22_P02 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100502392 | 502392 | Barrhead South SDO | Water | G100 | Gate 100 | 2022-03-01 | 2022-03-22 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100502743 | 502743 | WATER OF LEITH UIDs BATCH 4 Balerno Bridge Road CSOs | Wastewater | G100 | Gate 100 | 2022-06-13 | 2022-11-04 | 2022_23_P03 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G100502746 | 502746 | WATER OF LEITH UIDs BATCH 7 Longstone CSOs | Wastewater | G100 | Gate 100 | 2025-04-22 | 2024-04-08 | 2025_26_P01 | 2024_25_P01 | 2025_26_Q1 | 2024_25_Q1
G100502947 | 502947 | IR18 CAS Compliance Improvements - WWTW North, Complex | Wastewater | G100 | Gate 100 | 2021-07-26 | 2021-09-29 | 2021_22_P04 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502740 | 502740 | WATER OF LEITH UIDs BATCH 1 South Gyle Gogarloch SPS EO | Wastewater | G100 | Gate 100 | 2021-08-27 | 2021-06-02 | 2021_22_P05 | 2021_22_P03 | 2021_22_Q2 | 2021_22_Q1
G100502783 | 502783 | Balmore Pipebridge Repairs | Water | G100 | Gate 100 | 2022-06-23 | 2024-04-04 | 2022_23_P03 | 2024_25_P01 | 2022_23_Q1 | 2024_25_Q1
G100502955 | 502955 | EFOS - A8 East Hamilton Street Greenock | Wastewater | G100 | Gate 100 | 2025-01-12 | 2024-01-05 | 2024_25_P10 | 2023_24_P10 | 2024_25_Q4 | 2023_24_Q4
G100502563 | 502563 | IR18 Allowance - Dye Water Fish Pass | Water | G100 | Gate 100 | 2022-01-18 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100502748 | 502748 | WATER OF LEITH UIDs BATCH 9.1 Currie Kinleith Ind Est CSO | Wastewater | G100 | Gate 100 | 2022-07-24 | 2022-01-27 | 2022_23_P04 | 2021_22_P10 | 2022_23_Q2 | 2021_22_Q4
G100502749 | 502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Wastewater | G100 | Gate 100 | 2022-05-10 | 2022-11-29 | 2022_23_P02 | 2022_23_P08 | 2022_23_Q1 | 2022_23_Q3
G100502605 | 502605 | Carron Valley RSZ Cleaning - Mains Conditioning | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100502808 | 502808 | NRSWA Construction Water A9 Dualling Luncarty to Birnam | Water | G100 | Gate 100 | 2021-11-02 | 2021-12-01 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100502958 | 502958 | Aboyne WwTW - Capital Maintenance | Wastewater | G100 | Gate 100 | 2023-01-03 | 2023-03-03 | 2022_23_P10 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G100502600 | 502600 | Back Tolsta- Main out form North Lochs | Water | G100 | Gate 100 | 2022-01-10 | 2022-10-21 | 2021_22_P10 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3
G100502934 | 502934 | Flemington Road Glenrothes Sewer Rehab | Wastewater | G100 | Gate 100 | 2021-10-03 | 2021-11-22 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100502944 | 502944 | IR18 CAS Compliance Improvements - Networks East & North, Complex | Wastewater | G100 | Gate 100 | 2021-09-06 | 2023-10-06 | 2021_22_P06 | 2023_24_P07 | 2021_22_Q2 | 2023_24_Q3
G100502649 | 502649 | Dhu Loch_Argyll and Bute_THM Research and Investigation | Water | G100 | Gate 100 | 2023-01-30 | 2023-09-25 | 2022_23_P10 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G100502650 | 502650 | IR18 Allowance - Tarbert WTW | Water | G100 | Gate 100 | 2022-06-16 | 2023-06-23 | 2022_23_P03 | 2023_24_P03 | 2022_23_Q1 | 2023_24_Q1
G100502866 | 502866 | NRSWA Construction Sewer Greenhills Road Widening East Kilbride | Wastewater | G100 | Gate 100 | 2022-01-14 | 2022-02-17 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G100502867 | 502867 | NRSWA Construction Water Greenhills Road Widening East Kilbride | Water | G100 | Gate 100 | 2022-01-14 | 2021-12-08 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G100502853 | 502853 | Chemical Dosing Programme - Phase 1 - Glendevon WTW | Water | G100 | Gate 100 | 2022-10-26 | 2022-08-24 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G100502945 | 502945 | IR18 CAS Compliance Improvements - Networks South & West, Complex | Wastewater | G100 | Gate 100 | 2021-09-29 | 2022-12-21 | 2021_22_P06 | 2022_23_P09 | 2021_22_Q2 | 2022_23_Q3
G100502946 | 502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Wastewater | G100 | Gate 100 | 2021-12-03 | 2022-12-21 | 2021_22_P09 | 2022_23_P09 | 2021_22_Q3 | 2022_23_Q3
G100502949 | 502949 | Dunfermline Wellwood Waste Water Infrastructure | Wastewater | G100 | Gate 100 | 2022-03-01 | 2024-02-16 | 2021_22_P12 | 2023_24_P11 | 2021_22_Q4 | 2023_24_Q4
G100503119 | 503119 | IR18 Network Segregation Treatment | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-11-25 | 2021_22_P04 | 2021_22_P08 | 2021_22_Q2 | 2021_22_Q3
G100503050 | 503050 | Wishaw TM Water Quality | Water | G100 | Gate 100 | 2022-08-25 | 2023-03-29 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G100503072 | 503072 | Turriff WTW - Essential CM | Water | G100 | Gate 100 | 2022-09-30 | 2022-09-29 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100502857 | 502857 | Chemical Dosing Programme - Phase 1 - Turriff WTW | Water | G100 | Gate 100 | 2023-06-20 | 2023-07-17 | 2023_24_P03 | 2023_24_P04 | 2023_24_Q1 | 2023_24_Q2
G100502943 | 502943 | IR18 CAS Compliance Improvements - WWTW, Non Complex | Wastewater | G100 | Gate 100 | 2021-09-06 | 2022-05-31 | 2021_22_P06 | 2022_23_P02 | 2021_22_Q2 | 2022_23_Q1
G100502940 | 502940 | Fair Isle WTW - Quality | Water | G100 | Gate 100 | 2021-10-04 | 2023-03-22 | 2021_22_P07 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4
G100503194 | 503194 | Amlaird RSZ - DW5 Interventions | Water | G100 | Gate 100 | 2021-04-27 | 2021-06-30 | 2021_22_P01 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100503256 | 503256 | Water Quality Improvement - Greenock Phase 2 - Conditioning | Water | G100 | Gate 100 | 2021-06-29 | 2021-07-29 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G100503257 | 503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | Water | G100 | Gate 100 | 2021-04-30 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503045 | 503045 | Winchburgh WwTW - Growth Intermediate Solution Support | Wastewater | G100 | Gate 100 | 2021-07-02 | 2021-08-26 | 2021_22_P04 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100503195 | 503195 | IR18 Water Quality Improvement - Camps RSZ | Water | G100 | Gate 100 | 2022-08-30 | 2021-09-30 | 2022_23_P05 | 2021_22_P06 | 2022_23_Q2 | 2021_22_Q2
G100503197 | 503197 | IR18 Water Quality Improvement - Pateshill RSZ | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503198 | 503198 | IR18 Water Quality Improvement - Rawburn RSZ | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503199 | 503199 | IR18 Water Quality Improvement - Roberton RSZ | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503200 | 503200 | IR18 Water Quality Improvement - Spynie RSZ | Water | G100 | Gate 100 | 2021-06-17 | 2021-09-03 | 2021_22_P03 | 2021_22_P06 | 2021_22_Q1 | 2021_22_Q2
G100503177 | 503177 | IR18 External Flooding Clarkston | Wastewater | G100 | Gate 100 | 2021-11-17 | 2021-10-26 | 2021_22_P08 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
G100503120 | 503120 | IR18 Network Segregation Datacentre | Support Services | G100 | Gate 100 | 2021-07-28 | 2021-12-22 | 2021_22_P04 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100503229 | 503229 | Dalmuir Wastewater Strategy Review | Wastewater | G100 | Gate 100 | 2021-12-10 | 2021-12-20 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100503092 | 503092 | Legbrannock DSR | Water | G100 | Gate 100 | 2024-03-14 | 2023-12-15 | 2023_24_P12 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3
G100503234 | 503234 | Allt Sanna WFPM | Water | G100 | Gate 100 | 2021-12-20 | 2021-12-06 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G100503235 | 503235 | Galashiels Manse Street Infra | Water | G100 | Gate 100 | 2022-11-30 | 2023-08-07 | 2022_23_P08 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2
G100503249 | 503249 | IR18 Investigate Future Changes in the Occurrance of Algal Blooms | Water | G100 | Gate 100 | 2021-04-21 | 2022-03-10 | 2021_22_P01 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G100503162 | 503162 | Auchneel WTW - Lime to Caustic | Water | G100 | Gate 100 | 2022-08-09 | 2023-11-20 | 2022_23_P05 | 2023_24_P08 | 2022_23_Q2 | 2023_24_Q3
G100503393 | 503393 | Ayr Shore Road SPS - Emergency Repairs to Transfer Pumps and Wet Well Guide Rails | Wastewater | G100 | Gate 100 | 2021-11-03 | 2022-01-17 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G100503121 | 503121 | IR18 Legacy Infrastructure | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-01-20 | 2021_22_P04 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100503336 | 503336 | Water Quality Improvement-Wick East DMA | Water | G100 | Gate 100 | 2022-11-01 | 2023-12-18 | 2022_23_P08 | 2023_24_P09 | 2022_23_Q3 | 2023_24_Q3
G100503094 | 503094 | IR18 - 59034 - Legacy sludge requirement at Operational Sites | Water | G100 | Gate 100 | 2021-04-01 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503291 | 503291 | IR18 Security Operations Tools | Support Services | G100 | Gate 100 | 2021-07-28 | 2022-04-05 | 2021_22_P04 | 2022_23_P01 | 2021_22_Q2 | 2022_23_Q1
G100503230 | 503230 | Main Street Kirkconnel Pipe Bridge | Wastewater | G100 | Gate 100 | 2023-06-20 | 2023-03-30 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100503110 | 503110 | IR18 Tighnabruaich Lead Comms Investigation and Replacement | Water | G100 | Gate 100 | 2023-05-27 | 2023-03-30 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100503480 | 503480 | Kettleton Impounding Reservoir | Water | G100 | Gate 100 | 2024-08-14 | 2024-05-16 | 2024_25_P05 | 2024_25_P02 | 2024_25_Q2 | 2024_25_Q1
G100503239 | 503239 | Sharphill_Saltcoats | Water | G100 | Gate 100 | 2021-09-01 | 2022-03-25 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100503250 | 503250 | Carron Valley RSZ Cleaning – Flushing | Water | G100 | Gate 100 | 2021-07-30 | 2021-07-29 | 2021_22_P04 | 2021_22_P04 | 2021_22_Q2 | 2021_22_Q2
G100503236 | 503236 | IR18- Investigation of Long Term DOC increases in Drinking Water Catchments | Water | G100 | Gate 100 | 2021-04-06 | 2021-03-31 | 2021_22_P01 | 2020_21_P12 | 2021_22_Q1 | 2020_21_Q4
G100503269 | 503269 | Dalmarnock WWTW Improvements | Wastewater | G100 | Gate 100 | 2022-05-18 | 2022-08-29 | 2022_23_P02 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G100503362 | 503362 | Infra-Kingdom Park | Wastewater | G100 | Gate 100 | 2021-09-01 | 2024-08-27 | 2021_22_P06 | 2024_25_P05 | 2021_22_Q2 | 2024_25_Q2
G100503408 | 503408 | Blairlinnans PSC TM Monitoring | Water | G100 | Gate 100 | 2022-11-30 | 2022-08-26 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G100503412 | 503412 | Dalmacoulter WSZ Trunk Main Cleaning | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503413 | 503413 | Garbethill WSZ Trunk Main Cleaning | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-21 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503415 | 503415 | Bothwell Sewer - Replacement of approximatly 130m of 600mm | Wastewater | G100 | Gate 100 | 2022-04-22 | 2023-01-18 | 2022_23_P01 | 2022_23_P10 | 2022_23_Q1 | 2022_23_Q4
G100503418 | 503418 | Mauldslie Access Road & Bridge Repairs | Wastewater | G100 | Gate 100 | 2021-09-30 | 2021-10-12 | 2021_22_P06 | 2021_22_P07 | 2021_22_Q2 | 2021_22_Q3
G100503421 | 503421 | Stornoway WTW - Interim THM and Cryptosporidium measures | Water | G100 | Gate 100 | 2023-04-05 | 2023-05-25 | 2023_24_P01 | 2023_24_P02 | 2023_24_Q1 | 2023_24_Q1
G100503434 | 503434 | IR18 Daer CWT | Water | G100 | Gate 100 | 2022-03-31 | 2022-10-31 | 2021_22_P12 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3
G100503441 | 503441 | Oldmeldrum STW - Surface Aerator Replacement & Interim Oxymem Install | Wastewater | G100 | Gate 100 | 2023-08-20 | 2023-05-22 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100503562 | 503562 | Torra WTW Growth - TTU Installation | Water | G100 | Gate 100 | 2021-09-10 | 2022-01-31 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100503564 | 503564 | Brechin WwTW - Bio Filter Media Filter | Wastewater | G100 | Gate 100 | 2022-02-03 | 2022-06-30 | 2021_22_P11 | 2022_23_P03 | 2021_22_Q4 | 2022_23_Q1
G100503571 | 503571 | E1287 - Claredon Place Dunblane | Wastewater | G100 | Gate 100 | 2022-03-31 | 2022-11-25 | 2021_22_P12 | 2022_23_P08 | 2021_22_Q4 | 2022_23_Q3
G100503587 | 503587 | Argyll SCADA - Ardrishaig | Water | G100 | Gate 100 | 2021-10-30 | 2022-06-30 | 2021_22_P07 | 2022_23_P03 | 2021_22_Q3 | 2022_23_Q1
G100503594 | 503594 | E1050 Marchmont Road Warrender Park Road Edinburgh Recycled | Wastewater | G100 | Gate 100 | 2024-10-06 | 2024-07-22 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100503595 | 503595 | Yarrowfues WTW main-out 2019 | Water | G100 | Gate 100 | 2022-03-29 | 2023-06-21 | 2021_22_P12 | 2023_24_P03 | 2021_22_Q4 | 2023_24_Q1
G100503628 | 503628 | SR21ES Herricks WTW upgrade | Water | G100 | Gate 100 | 2026-02-19 | 2025-06-18 | 2025_26_P11 | 2025_26_P03 | 2025_26_Q4 | 2025_26_Q1
G100503630 | 503630 | OMG06 Shortfall Project | Water | G100 | Gate 100 | 2021-09-30 | 2021-09-30 | 2021_22_P06 | 2021_22_P06 | 2021_22_Q2 | 2021_22_Q2
G100503631 | 503631 | Bradan WOA- WQ High Priority Customer Interventions | Water | G100 | Gate 100 | 2022-01-27 | 2022-03-24 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100503638 | 503638 | SR21 Carstairs Junction Overland Sewer | Wastewater | G100 | Gate 100 | 2024-03-21 | 2024-01-22 | 2023_24_P12 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G100503632 | 503632 | Bradan WQ Improvement Pennyburn Road DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2022-07-05 | 2022-08-31 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G100503613 | 503613 | SR21 ES Loch Calder WOA - Roster Occumster Mains Rehab | Water | G100 | Gate 100 | 2026-04-09 | 2024-12-09 | 2026_27_P01 | 2024_25_P09 | 2026_27_Q1 | 2024_25_Q3
G100503617 | 503617 | Tullich WOA Oban 12 Main Refurbishment -CWA- | Water | G100 | Gate 100 | 2022-03-17 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100503543 | 503543 | Drongan WwTW Bathing Water Improvement | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-03-30 | 2021_22_P06 | 2021_22_P12 | 2021_22_Q2 | 2021_22_Q4
G100503545 | 503545 | Mauchline WwTW Bathing Water Improvement | Wastewater | G100 | Gate 100 | 2021-09-21 | 2022-02-16 | 2021_22_P06 | 2021_22_P11 | 2021_22_Q2 | 2021_22_Q4
G100503546 | 503546 | Belleisle Golf Course CSO Bathing Water Improvement | Wastewater | G100 | Gate 100 | 2021-09-21 | 2021-08-24 | 2021_22_P06 | 2021_22_P05 | 2021_22_Q2 | 2021_22_Q2
G100503678 | 503678 | SR21 ES Camps | Water | G100 | Gate 100 | 2024-01-16 | 2026-09-11 | 2023_24_P10 | 2026_27_P06 | 2023_24_Q4 | 2026_27_Q2
G100503680 | 503680 | Dunside Upper and Lower Risk Reduction | Water | G100 | Gate 100 | 2026-03-19 | 2025-12-19 | 2025_26_P12 | 2025_26_P09 | 2025_26_Q4 | 2025_26_Q3
G100503733 | 503733 | Aird a Mhachair - Benbecula DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2022-05-31 | 2022-03-14 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100503686 | 503686 | SR21 ES Munnoch Breach | Water | G100 | Gate 100 | 2023-08-31 | 2022-12-19 | 2023_24_P05 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3
G100503714 | 503714 | SR21 ES North Third | Water | G100 | Gate 100 | 2024-03-17 | 2024-03-21 | 2023_24_P12 | 2023_24_P12 | 2023_24_Q4 | 2023_24_Q4
G100503716 | 503716 | SR21 ES Mill Glen Breach | Water | G100 | Gate 100 | 2022-04-30 | 2021-12-02 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G100503730 | 503730 | Stonebyres DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2023-10-26 | 2022-12-20 | 2023_24_P07 | 2022_23_P09 | 2023_24_Q3 | 2022_23_Q3
G100503731 | 503731 | Elsrickle DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2022-08-23 | 2022-09-22 | 2022_23_P05 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100503732 | 503732 | Portree - Braes DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2024-06-20 | 2024-03-22 | 2024_25_P03 | 2023_24_P12 | 2024_25_Q1 | 2023_24_Q4
G100503726 | 503726 | Neilston and Uplawmoor Rd - Neilston High DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2021-10-06 | 2021-11-29 | 2021_22_P07 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100503727 | 503727 | SR21 ES Alyth Loyal - Cothelhill DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2022-02-15 | 2022-01-31 | 2021_22_P11 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G100503728 | 503728 | SR21 ES Edzell Rural DMA Mains Rehabilitation | Water | G100 | Gate 100 | 2021-06-30 | 2021-06-09 | 2021_22_P03 | 2021_22_P03 | 2021_22_Q1 | 2021_22_Q1
G100503701 | 503701 | Dalmarnock WwTW STW000222 - Asset Cleaning Project & Control of Odours | Wastewater | G100 | Gate 100 | 2021-05-14 | 2021-05-28 | 2021_22_P02 | 2021_22_P02 | 2021_22_Q1 | 2021_22_Q1
G100503761 | 503761 | SR21 Bonnycraig WTW Growth and Quality | Water | G100 | Gate 100 | 2023-06-19 | 2023-03-27 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G100503860 | 503860 | EFOS Crow Wood Terrace Chryston W1000 | Wastewater | G100 | Gate 100 | 2022-07-28 | 2022-09-01 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G100504434 | 504434 | Bradan WTW - Top and Bottom Generator Install | Water | G100 | Gate 100 | 2021-11-18 | 2021-11-29 | 2021_22_P08 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G100504465 | 504465 | Forehill WTW - Ferric Storage and delivery area | Water | G100 | Gate 100 | 2024-04-17 | 2024-07-19 | 2024_25_P01 | 2024_25_P04 | 2024_25_Q1 | 2024_25_Q2
G100505032 | 505032 | ICF - Grandholm, Aberdeen - Water Main Installation. | Water | G100 | Gate 100 | 2021-12-10 | 2022-03-18 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G100504995 | 504995 | Loch Calder WTW - Treated Water Pumps | Water | G100 | Gate 100 | 2024-10-24 | 2024-07-26 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100505053 | 505053 | EFOS - Sauchie Road Crieff - 0248 | Wastewater | G100 | Gate 100 | 2023-08-02 | 2023-05-12 | 2023_24_P05 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100505384 | 505384 | NRSWA Edinburgh Trams York Place to Newhaven | Water | G100 | Gate 100 | 2024-01-19 | 2023-12-15 | 2023_24_P10 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3
G100505447 | 505447 | RCI Bigton DMA Maywick Road | Water | G100 | Gate 100 | 2023-06-11 | 2023-02-28 | 2023_24_P03 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G100505504 | 505504 | RCI High Dykes DMA (Auchincarroch Rd) | Water | G100 | Gate 100 | 2022-12-05 | 2023-03-31 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G100505687 | 505687 | Rosewell WwTW - Interim Growth Solution SAF | Wastewater | G100 | Gate 100 | 2024-02-28 | 2023-11-21 | 2023_24_P11 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3
G100505693 | 505693 | RCI West Ballochy DMA (Hillside) | Water | G100 | Gate 100 | 2024-02-26 | 2023-08-08 | 2023_24_P11 | 2023_24_P05 | 2023_24_Q4 | 2023_24_Q2
G100505641 | 505641 | Lochwinnoch WwTW - Inlet Screw Pumps Refurbishment - 500k | Wastewater | G100 | Gate 100 | 2022-12-14 | 2023-03-17 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G100505927 | 505927 | RCI Hilliclay DMA (Stainland) | Water | G100 | Gate 100 | 2024-04-08 | 2024-01-09 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4
G100505949 | 505949 | Skellyton WwTW SR10 Outstanding CM | Wastewater | G100 | Gate 100 | 2025-03-20 | 2024-12-20 | 2024_25_P12 | 2024_25_P09 | 2024_25_Q4 | 2024_25_Q3
G100506029 | 506029 | RCI Roskhill DMA and Dunvegan DMA Roag | Water | G100 | Gate 100 | 2024-06-19 | 2024-04-30 | 2024_25_P03 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1
G100506032 | 506032 | RCI Broadford DMA and Breakish DMA Broadford | Water | G100 | Gate 100 | 2024-07-29 | 2024-04-30 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G100506149 | 506149 | RCI Tankerness and Foubister DMA Tankerness | Water | G100 | Gate 100 | 2024-03-17 | 2024-04-30 | 2023_24_P12 | 2024_25_P01 | 2023_24_Q4 | 2024_25_Q1
G100506151 | 506151 | RCI West Line DMA Oust WSZ | Water | G100 | Gate 100 | 2024-11-24 | 2025-11-25 | 2024_25_P08 | 2025_26_P08 | 2024_25_Q3 | 2025_26_Q3
G100506234 | 506234 | RCI Luing DMA Cullipool | Water | G100 | Gate 100 | 2023-07-02 | 2022-09-29 | 2023_24_P04 | 2022_23_P06 | 2023_24_Q2 | 2022_23_Q2
G100506232 | 506232 | RCI Kinlochleven DMA | Water | G100 | Gate 100 | 2023-07-02 | 2023-03-28 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G100506228 | 506228 | RCI Bowmore DMA (Torra Mains) | Water | G100 | Gate 100 | 2023-07-02 | 2023-05-26 | 2023_24_P04 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G100506231 | 506231 | RCI Eathie DMA (Muirhead Farm and Eathie Mains) | Water | G100 | Gate 100 | 2024-09-15 | 2024-06-17 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G100506275 | 506275 | RCI Tore and Drumderfit DMA (Tore to Kessock) | Water | G100 | Gate 100 | 2024-01-21 | 2023-12-04 | 2023_24_P10 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3
G100506271 | 506271 | RCI Bragar DMA (West Lewis WOA) | Water | G100 | Gate 100 | 2024-09-04 | 2024-08-16 | 2024_25_P06 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2
G100506422 | 506422 | Business Management System | Support Services | G100 | Gate 100 | 2023-10-19 | 2023-06-30 | 2023_24_P07 | 2023_24_P03 | 2023_24_Q3 | 2023_24_Q1
G100506608 | 506608 | E-W-NI-140520-Craighead WTW - Upgrade Mn removal - Covid 19 - 66 | Water | G100 | Gate 100 | 2023-04-26 | 2023-02-27 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G100506618 | 506618 | RCI Kinlochbervie DMA (Kinlochbervie WOA) | Water | G100 | Gate 100 | 2024-02-21 | 2023-09-11 | 2023_24_P11 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G100506684 | 506684 | Repair at Glenhove DSR 2 | Water | G100 | Gate 100 | 2023-03-24 | 2022-11-04 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G100506779 | 506779 | Stoneybridge WTW - Essential Capital Maintenance | Water | G100 | Gate 100 | 2024-01-18 | 2023-10-20 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100506864 | 506864 | ICF - Forres Strategic Water upgrade | Water | G100 | Gate 100 | 2023-03-01 | 2024-06-21 | 2022_23_P12 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1
G100506865 | 506865 | ICF - Forres Strategic Wastewater upgrade | Wastewater | G100 | Gate 100 | 2023-03-01 | 2024-06-21 | 2022_23_P12 | 2024_25_P03 | 2022_23_Q4 | 2024_25_Q1
G100506896 | 506896 | Windows 10 Upgrade | Support Services | G100 | Gate 100 | 2021-09-30 | 2022-01-18 | 2021_22_P06 | 2021_22_P10 | 2021_22_Q2 | 2021_22_Q4
G100507057 | 507057 | RCI Catterthun DMA Craigton of Monikie | Water | G100 | Gate 100 | 2023-12-17 | 2023-09-18 | 2023_24_P09 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100507186 | 507186 | RCI Craigie DMA Plewlands | Water | G100 | Gate 100 | 2023-07-16 | 2023-02-28 | 2023_24_P04 | 2022_23_P11 | 2023_24_Q2 | 2022_23_Q4
G100507189 | 507189 | RCI Rossie DMA Ethie PMA | Water | G100 | Gate 100 | 2023-12-18 | 2023-06-30 | 2023_24_P09 | 2023_24_P03 | 2023_24_Q3 | 2023_24_Q1
G100507173 | 507173 | Oracle ULA Exit | Support Services | G100 | Gate 100 | 2021-08-02 | 2021-12-21 | 2021_22_P05 | 2021_22_P09 | 2021_22_Q2 | 2021_22_Q3
G100507455 | 507455 | ICF - Ellon - Bridge of Don Aberdeen Development Corridor - Balmedie to Blackdog Section Water | Water | G100 | Gate 100 | 2024-04-30 | 2024-04-30 | 2024_25_P01 | 2024_25_P01 | 2024_25_Q1 | 2024_25_Q1
G100507493 | 507493 | RCI SR21 ES Mains of Moyness - Non DMA Phase 2 | Water | G100 | Gate 100 | 2024-04-16 | 2023-10-20 | 2024_25_P01 | 2023_24_P07 | 2024_25_Q1 | 2023_24_Q3
G100507813 | 507813 | Simple Repair at Aberdeen Kirkhill DSR | Water | G100 | Gate 100 | 2022-04-25 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G100507860 | 507860 | Simple Repair at Rochomie DSR | Water | G100 | Gate 100 | 2022-05-15 | 2021-12-15 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G100507808 | 507808 | Croy WwTW - Growth | Wastewater | G100 | Gate 100 | 2024-12-05 | 2024-09-06 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2
G100507933 | 507933 | Catrineholm WwTW- Emergency Project to Maintain CAR Licence Compliance | Wastewater | G100 | Gate 100 | 2022-11-16 | 2022-12-22 | 2022_23_P08 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
G100508109 | 508109 | Microsoft Teams | Support Services | G100 | Gate 100 | 2021-05-14 | 2021-12-07 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G100508601 | 508601 | SR15 Milnbe Weir Eel Pass PPD | Wastewater | G100 | Gate 100 | 2022-06-12 | 2022-06-01 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G100508752 | 508752 | E-WW-NI-150920-PERTH CITY WWTW-IFAS | Wastewater | G100 | Gate 100 | 2024-05-08 | 2024-02-08 | 2024_25_P02 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G100509283 | 509283 | Simple Repair at Peterhead Newfield DSR | Water | G100 | Gate 100 | 2022-06-04 | 2022-06-29 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G100510392 | 510392 | Oban, Stevenson Street SPS - Replace Screw Pumps | Wastewater | G100 | Gate 100 | 2023-09-01 | 2023-06-02 | 2023_24_P06 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1
G100510727 | 510727 | Infrastructure Tactical Project | Support Services | G100 | Gate 100 | 2022-11-04 | 2023-05-15 | 2022_23_P08 | 2023_24_P02 | 2022_23_Q3 | 2023_24_Q1
G100510931 | 510931 | Dores DMA - Mains Rehab | Water | G100 | Gate 100 | 2023-11-16 | 2023-05-19 | 2023_24_P08 | 2023_24_P02 | 2023_24_Q3 | 2023_24_Q1
G100511334 | 511334 | RCI Clachan DMA Longrigg | Water | G100 | Gate 100 | 2024-01-15 | 2023-07-07 | 2023_24_P10 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2
G100511344 | 511344 | Field Service Transformation Project | Support Services | G100 | Gate 100 | 2024-04-17 | 2022-10-25 | 2024_25_P01 | 2022_23_P07 | 2024_25_Q1 | 2022_23_Q3
G100511495 | 511495 | SR21 Core WTW pilots - Chlorine Dioxide | Water | G100 | Gate 100 | 2024-07-21 | 2024-04-22 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G100511500 | 511500 | SR21 Core WTW pilots - Ozone GAC | Water | G100 | Gate 100 | 2023-12-26 | 2023-12-18 | 2023_24_P09 | 2023_24_P09 | 2023_24_Q3 | 2023_24_Q3
G100511704 | 511704 | RCI Comrie and Bogside DMA Righead Farm | Water | G100 | Gate 100 | 2024-01-04 | 2024-01-09 | 2023_24_P10 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G100512469 | 512469 | SR21 Core WTW Pilots - Filter Columns | Water | G100 | Gate 100 | 2023-10-26 | 2023-09-28 | 2023_24_P07 | 2023_24_P06 | 2023_24_Q3 | 2023_24_Q2
G100512600 | 512600 | ICF - NIA0157 Glencorse WOA - Danderhall and Gilmerton DMAs - Solution 01 | Water | G100 | Gate 100 | 2023-08-24 | 2023-03-24 | 2023_24_P05 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G100512639 | 512639 | Server and Storage Project | Support Services | G100 | Gate 100 | 2024-01-28 | 2023-10-13 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100512749 | 512749 | RCI Benbecula DMA Ceann a Bunteag | Water | G100 | Gate 100 | 2023-11-30 | 2023-03-23 | 2023_24_P08 | 2022_23_P12 | 2023_24_Q3 | 2022_23_Q4
G100512711 | 512711 | WQ Mains Rehabilitation Ph1 Ma2b Patna DMA | Water | G100 | Gate 100 | 2023-09-10 | 2023-03-31 | 2023_24_P06 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G100512815 | 512815 | RCI Garelochhead Shandon DMA Faslane Diversion | Water | G100 | Gate 100 | 2024-10-13 | 2024-07-18 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100512940 | 512940 | RCI Bixter Tresta and Sandsound DMA Effirth | Water | G100 | Gate 100 | 2024-06-23 | 2024-09-19 | 2024_25_P03 | 2024_25_P06 | 2024_25_Q1 | 2024_25_Q2
G100512997 | 512997 | ICF - Nairn Water Main Upgrade - Galantray Element | Water | G100 | Gate 100 | 2024-08-04 | 2024-04-03 | 2024_25_P05 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G100513208 | 513208 | SR21 Carron Valley WTW - Air Curtain | Water | G100 | Gate 100 | 2024-04-04 | 2023-12-29 | 2024_25_P01 | 2023_24_P09 | 2024_25_Q1 | 2023_24_Q3
G100513312 | 513312 | Hydro Nation Chair | CE&FS | G100 | Gate 100 | 2027-09-16 | 2027-06-18 | 2027_28_P06 | 2027_28_P03 | 2027_28_Q2 | 2027_28_Q1
G100513433 | 513433 | SR21 Glenfarg WTW - Air Curtain | Water | G100 | Gate 100 | 2024-02-28 | 2023-11-30 | 2023_24_P11 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3
G100513461 | 513461 | Inverness Laboratory Extension | Support Services | G100 | Gate 100 | 2022-08-21 | 2023-03-08 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G100513826 | 513826 | RCI Newfield PS To Broadmuir TM DMA Hatton Hotspot | Water | G100 | Gate 100 | 2024-05-15 | 2024-02-15 | 2024_25_P02 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G100513832 | 513832 | Non-Complex Service Delivery (NCSD) Phase 3 | Support Services | G100 | Gate 100 | 2022-03-31 | 2022-03-28 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G100513923 | 513923 | Black Isle Trunk Main - Valve Replacement | Water | G100 | Gate 100 | 2023-07-02 | 2025-01-10 | 2023_24_P04 | 2024_25_P10 | 2023_24_Q2 | 2024_25_Q4
G100514041 | 514041 | C-WW-NI-Management of Wastewater Temporary Process Units - Aberuthven STW | Wastewater | G100 | Gate 100 | 2024-12-12 | 2024-09-13 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2
G100514047 | 514047 | RCI Stornoway Point DMA Bayble | Water | G100 | Gate 100 | 2025-01-12 | 2025-01-28 | 2024_25_P10 | 2024_25_P10 | 2024_25_Q4 | 2024_25_Q4
G100514080 | 514080 | RCI Dolphinton Line DMA | Water | G100 | Gate 100 | 2024-11-27 | 2024-08-29 | 2024_25_P08 | 2024_25_P05 | 2024_25_Q3 | 2024_25_Q2
G100514217 | 514217 | E-WW-NI-140721-Inverurie Old STW Redundant Assets Demo | Wastewater | G100 | Gate 100 | 2023-07-18 | 2023-03-31 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G100514441 | 514441 | Digital Securing Operational Assets | Support Services | G100 | Gate 100 | 2024-05-09 | 2023-12-11 | 2024_25_P02 | 2023_24_P09 | 2024_25_Q1 | 2023_24_Q3
G100514448 | 514448 | EFOS - Main Street Bridge of Weir - 281-1 | Wastewater | G100 | Gate 100 | 2024-11-04 | 2023-11-06 | 2024_25_P08 | 2023_24_P08 | 2024_25_Q3 | 2023_24_Q3
G100514598 | 514598 | Networks Refresh Project | Support Services | G100 | Gate 100 | 2024-01-22 | 2023-08-25 | 2023_24_P10 | 2023_24_P05 | 2023_24_Q4 | 2023_24_Q2
G100514631 | 514631 | E-WWNI-050821-Kirkcaldy STW-Renew media in 1st stage biopur (BAFF) process | Wastewater | G100 | Gate 100 | 2023-11-08 | 2023-10-20 | 2023_24_P08 | 2023_24_P07 | 2023_24_Q3 | 2023_24_Q3
G100515139 | 515139 | Dirty Dam - Silt removal | Water | G100 | Gate 100 | 2024-03-07 | 2023-12-08 | 2023_24_P12 | 2023_24_P09 | 2023_24_Q4 | 2023_24_Q3
G100515505 | 515505 | SR21 Eela WTW Interim Measures | Water | G100 | Gate 100 | 2022-10-19 | 2023-10-06 | 2022_23_P07 | 2023_24_P07 | 2022_23_Q3 | 2023_24_Q3
G100515607 | 515607 | C-WW-NI-MCC Replacement – Pitmedden STW | Wastewater | G100 | Gate 100 | 2024-10-06 | 2024-07-19 | 2024_25_P07 | 2024_25_P04 | 2024_25_Q3 | 2024_25_Q2
G100515625 | 515625 | rDWD Implementation - Juniper House | Support Services | G100 | Gate 100 | 2023-05-03 | 2023-02-28 | 2023_24_P02 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G100516045 | 516045 | TWS Tiree WTW CWBT Replacement | Water | G100 | Gate 100 | 2024-10-17 | 2023-11-22 | 2024_25_P07 | 2023_24_P08 | 2024_25_Q3 | 2023_24_Q3
G100516085 | 516085 | Milngavie WTW - replace hypo bulk tank 2 | Water | G100 | Gate 100 | 2025-03-12 | 2024-09-13 | 2024_25_P12 | 2024_25_P06 | 2024_25_Q4 | 2024_25_Q2
G100516502 | 516502 | SR21 Black Esk WTW - Manganese Monitors | Water | G100 | Gate 100 | 2022-12-28 | 2023-02-27 | 2022_23_P09 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
G100516659 | 516659 | Greater Glasgow Bioresource Treatment Project | Wastewater | G100 | Gate 100 | 2023-10-10 | 2023-07-12 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100517533 | 517533 | SR21 Islay Flow Gauging | Water | G100 | Gate 100 | 2025-09-16 | 2025-06-18 | 2025_26_P06 | 2025_26_P03 | 2025_26_Q2 | 2025_26_Q1
G100518244 | 518244 | Shieldhall WWTW - PST Maintenance Bays - Replacement | Wastewater | G100 | Gate 100 | 2024-12-30 | 2024-10-01 | 2024_25_P09 | 2024_25_P07 | 2024_25_Q3 | 2024_25_Q3
G100518444 | 518444 | Orkney Sludge Trial Enabling Works | Water | G100 | Gate 100 | 2023-10-18 | 2023-08-18 | 2023_24_P07 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2
G100518591 | 518591 | Cults Pitfodels TWP - Replace MCC | Water | G100 | Gate 100 | 2025-07-10 | 2025-04-11 | 2025_26_P04 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1
G100518579 | 518579 | Shieldhall WWTW - cleaning of Inlet Delta Storm Bypass Culvert and Velocity Channels at Pre-Sed Bldng | Wastewater | G100 | Gate 100 | 2024-01-26 | 2023-10-27 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100520228 | 520228 | NCSD Need4621 Loch Turret investigation overpumping drought periods | Water | G100 | Gate 100 | 2024-07-31 | 2024-04-29 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G100520229 | 520229 | Non Complex Service Delivery (NCSD) Phase 3 Implementation | Support Services | G100 | Gate 100 | 2023-08-24 | 2023-07-21 | 2023_24_P05 | 2023_24_P04 | 2023_24_Q2 | 2023_24_Q2
G100520459 | 520459 | Apex Applications Replacement | Support Services | G100 | Gate 100 | 2023-12-28 | 2023-07-31 | 2023_24_P09 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100520500 | 520500 | E-WW-NI-070422-Banchory STW Chemical Dosing | Wastewater | G100 | Gate 100 | 2024-09-19 | 2024-06-21 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G100520606 | 520606 | RCI Colmonell DMA | Water | G100 | Gate 100 | 2024-06-26 | 2023-09-06 | 2024_25_P03 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G100520761 | 520761 | Field Connectivity Project | Support Services | G100 | Gate 100 | 2024-03-25 | 2023-10-27 | 2023_24_P12 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G100522707 | 522707 | Redcraigs DSR - Rationalisation | Water | G100 | Gate 100 | 2024-02-04 | 2023-11-06 | 2023_24_P11 | 2023_24_P08 | 2023_24_Q4 | 2023_24_Q3
G100523508 | 523508 | Powfoot SEP - Refurbish Reed Beds | Wastewater | G100 | Gate 100 | 2024-04-25 | 2024-01-26 | 2024_25_P01 | 2023_24_P10 | 2024_25_Q1 | 2023_24_Q4
G100524913 | 524913 | SW Reporting Redefined | Support Services | G100 | Gate 100 | 2023-10-29 | 2023-07-31 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100524914 | 524914 | Open Data | Support Services | G100 | Gate 100 | 2023-10-29 | 2023-07-31 | 2023_24_P07 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G100525189 | 525189 | Saltcoats Stormflow WWPS Rising Main Replacement - Emergency Works | Wastewater | G100 | Gate 100 | 2024-05-06 | 2024-02-06 | 2024_25_P02 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G100527220 | 527220 | SIP Yr 3 OKR Delivery | Support Services | G100 | Gate 100 | 2023-07-27 | 2023-06-28 | 2023_24_P04 | 2023_24_P03 | 2023_24_Q2 | 2023_24_Q1
G100528868 | 528868 | WQ Carron Valley WOA Discolouration Management Plan Delivery | Water | G100 | Gate 100 | 2026-03-12 | 2025-12-12 | 2025_26_P12 | 2025_26_P09 | 2025_26_Q4 | 2025_26_Q3
G110046172 | 046172 | Distribution Water Quality Rehab - Kirbister Orkney RSZ | Water | G110 | Gate 110 | 2022-06-02 | 2022-10-26 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G110400324 | 400324 | NRSWA C3 Service Relocate Edinburgh Tram Lines Mains Diversion | Water | G110 | Gate 110 | 2024-01-13 | 2023-08-09 | 2023_24_P10 | 2023_24_P05 | 2023_24_Q4 | 2023_24_Q2
G110401795 | 401795 | S157 UID Seedhill No1 CSO West of 6 Seedhill at Mill Street Paisley | Wastewater | G110 | Gate 110 | 2022-04-06 | 2022-02-15 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110401705 | 401705 | S087 - UID - Scotwood Overflow North East of Lay-by Busby Road | Wastewater | G110 | Gate 110 | 2022-07-25 | 2024-03-20 | 2022_23_P04 | 2023_24_P12 | 2022_23_Q2 | 2023_24_Q4
G110401687 | 401687 | S048 - UID - Farme Estate PS EO Downiebrae Road Shieldhall No.40 | Wastewater | G110 | Gate 110 | 2022-06-22 | 2023-02-24 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4
G110401668 | 401668 | S043 - UID - Cambuslang Road Richmond Laundry - South East of Railway Rutherglen | Wastewater | G110 | Gate 110 | 2022-06-21 | 2024-01-24 | 2022_23_P03 | 2023_24_P10 | 2022_23_Q1 | 2023_24_Q4
G110401685 | 401685 | S046 - UID - Downiebrae Road Farme Estate Shieldhall No 39 | Wastewater | G110 | Gate 110 | 2022-06-21 | 2023-02-24 | 2022_23_P03 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4
G110402197 | 402197 | Sewer Flooding Burnbank Street Airdrie | Wastewater | G110 | Gate 110 | 2022-02-09 | 2022-02-01 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110403097 | 403097 | QS3b AR - P005 UID Off Garriochmill Road CSO North Kelvin | Wastewater | G110 | Gate 110 | 2021-11-26 | 2021-12-09 | 2021_22_P08 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110403238 | 403238 | SR15 ES - E016 Field off North Park Avenue CSO | Wastewater | G110 | Gate 110 | 2022-05-17 | 2023-02-27 | 2022_23_P02 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4
G110403104 | 403104 | QS3b AR - P012 UID 317 Northwoodside Road Glasgow | Wastewater | G110 | Gate 110 | 2022-06-02 | 2022-06-23 | 2022_23_P03 | 2022_23_P03 | 2022_23_Q1 | 2022_23_Q1
G110403090 | 403090 | QS3b AR - Kaim WTW | Water | G110 | Gate 110 | 2022-03-31 | 2022-10-24 | 2021_22_P12 | 2022_23_P07 | 2021_22_Q4 | 2022_23_Q3
G110403100 | 403100 | QS3b AR - P008 UID At West Bank of Footbridge BGs Addison Road | Wastewater | G110 | Gate 110 | 2022-05-22 | 2022-03-30 | 2022_23_P02 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110403103 | 403103 | QS3b AR - P011 UID Queen Margaret Road Bridge CSO at Botanical Gardens | Wastewater | G110 | Gate 110 | 2022-06-27 | 2021-08-25 | 2022_23_P03 | 2021_22_P05 | 2022_23_Q1 | 2021_22_Q2
G110403098 | 403098 | QS3b AR - P006 UID Near the Junction of Kelvindale Road and Balfour Street | Wastewater | G110 | Gate 110 | 2022-09-01 | 2023-01-31 | 2022_23_P06 | 2022_23_P10 | 2022_23_Q2 | 2022_23_Q4
G110403101 | 403101 | QS3b AR - P009 UID North of Playground off Garriochmill Road | Wastewater | G110 | Gate 110 | 2022-05-25 | 2023-02-27 | 2022_23_P02 | 2022_23_P11 | 2022_23_Q1 | 2022_23_Q4
G110403102 | 403102 | QS3b AR - P010 UID Botanic Gardens Nr Junc of Garrioch Drive Garrioch Rd and Shakespeare St | Wastewater | G110 | Gate 110 | 2022-05-25 | 2023-04-03 | 2022_23_P02 | 2023_24_P01 | 2022_23_Q1 | 2023_24_Q1
G110403146 | 403146 | SR15 ES - Amlaird WTW and Corsehouse WTW Strategic Main Out and Decommission | Water | G110 | Gate 110 | 2021-06-16 | 2021-07-01 | 2021_22_P03 | 2021_22_P04 | 2021_22_Q1 | 2021_22_Q2
G110402949 | 402949 | SR15 ES - LRC3 Daldowie WWTW to Dalmarnock WWTW FE Transfer and Outfall Development | Wastewater | G110 | Gate 110 | 2023-07-22 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110403321 | 403321 | SR15 ES - Craigneuk Avenue Airdrie Internal and External Flooding | Wastewater | G110 | Gate 110 | 2023-05-28 | 2023-03-24 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110403106 | 403106 | QS3b AR - P014 UID Westbank Quadrant at Eldon Street Bridge CSO NS273667 | Wastewater | G110 | Gate 110 | 2023-11-01 | 2023-11-29 | 2023_24_P08 | 2023_24_P08 | 2023_24_Q3 | 2023_24_Q3
G110403658 | 403658 | Darnley Mains Development - Trunk Mains Diversion | Water | G110 | Gate 110 | 2023-07-01 | 2023-05-03 | 2023_24_P04 | 2023_24_P02 | 2023_24_Q2 | 2023_24_Q1
G110403917 | 403917 | SR15 ES - Savalbeg WTW - WQ and Essential CM Upgrade | Water | G110 | Gate 110 | 2022-06-29 | 2022-03-31 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110403716 | 403716 | SR15 ES - Sanday Sludge Storage Area and Drying Beds | Wastewater | G110 | Gate 110 | 2023-11-19 | 2023-07-26 | 2023_24_P08 | 2023_24_P04 | 2023_24_Q3 | 2023_24_Q2
G110403605 | 403605 | SR15 ES Clunas WTW and Treatment Trial - Legacy Sludge | Water | G110 | Gate 110 | 2021-11-29 | 2022-01-27 | 2021_22_P08 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G110500046 | 500046 | Improvement to Supply-Demand Balance - Stornoway WRZ | Water | G110 | Gate 110 | 2025-05-15 | 2023-03-30 | 2025_26_P02 | 2022_23_P12 | 2025_26_Q1 | 2022_23_Q4
G110403127 | 403127 | SR15 ES - Loch Ness Regional WTW Scheme | Water | G110 | Gate 110 | 2023-05-17 | 2023-08-23 | 2023_24_P02 | 2023_24_P05 | 2023_24_Q1 | 2023_24_Q2
G110403532 | 403532 | SR15 ES - Kyle of Lochalsh WTW - Water Resource Strategic Study | Water | G110 | Gate 110 | 2022-07-02 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110500060 | 500060 | FRMA Improvements | Water | G110 | Gate 110 | 2022-02-23 | 2021-11-26 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110403934 | 403934 | Blairythan Terrace Foveran ST Growth | Wastewater | G110 | Gate 110 | 2023-04-04 | 2023-03-24 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110404026 | 404026 | SR15 ES - Main Street Newtonmore | Wastewater | G110 | Gate 110 | 2023-04-22 | 2024-12-11 | 2023_24_P01 | 2024_25_P09 | 2023_24_Q1 | 2024_25_Q3
G110403902 | 403902 | Ellon WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-08-23 | 2023-03-30 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G110403995 | 403995 | SR15 ES - Londornoch WTW | Water | G110 | Gate 110 | 2025-07-14 | 2026-06-24 | 2025_26_P04 | 2026_27_P03 | 2025_26_Q2 | 2026_27_Q1
G110403991 | 403991 | SR15 ES - Newmore WTW - WQ and Essential Related CM Upgrade | Water | G110 | Gate 110 | 2023-10-31 | 2024-02-07 | 2023_24_P07 | 2023_24_P11 | 2023_24_Q3 | 2023_24_Q4
G110403994 | 403994 | SR15 ES - Uig WTW - SR15 WQ | Water | G110 | Gate 110 | 2022-11-26 | 2023-10-04 | 2022_23_P08 | 2023_24_P07 | 2022_23_Q3 | 2023_24_Q3
G110500017 | 500017 | W473 - Conon Avenue | Wastewater | G110 | Gate 110 | 2022-11-22 | 2022-08-30 | 2022_23_P08 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110403923 | 403923 | SR15 ES - E1618 - Rose Street Annan 14 33 and 35 | Wastewater | G110 | Gate 110 | 2023-03-31 | 2023-03-27 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110403967 | 403967 | Winchburgh WwTW - Growth | Wastewater | G110 | Gate 110 | 2025-06-06 | 2024-12-16 | 2025_26_P03 | 2024_25_P09 | 2025_26_Q1 | 2024_25_Q3
G110403939 | 403939 | Stewarton WwTW - Growth | Wastewater | G110 | Gate 110 | 2023-02-03 | 2023-08-09 | 2022_23_P11 | 2023_24_P05 | 2022_23_Q4 | 2023_24_Q2
G110403781 | 403781 | Aberchirder WwTW Growth | Wastewater | G110 | Gate 110 | 2022-06-17 | 2022-01-18 | 2022_23_P03 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4
G110403782 | 403782 | Kennethmont WwTW Growth | Wastewater | G110 | Gate 110 | 2024-01-26 | 2024-07-10 | 2023_24_P10 | 2024_25_P04 | 2023_24_Q4 | 2024_25_Q2
G110404093 | 404093 | SR15 ES - Greenock WTW - SCADA Replacement | Water | G110 | Gate 110 | 2024-05-23 | 2024-05-29 | 2024_25_P02 | 2024_25_P02 | 2024_25_Q1 | 2024_25_Q1
G110403943 | 403943 | Canonbie WwTW - Upgrade Growth (Transfer from 403465) | Wastewater | G110 | Gate 110 | 2022-08-19 | 2023-07-26 | 2022_23_P05 | 2023_24_P04 | 2022_23_Q2 | 2023_24_Q2
G110403968 | 403968 | Haddington WwTW - Growth | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-28 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500047 | 500047 | Roberton WTW | Water | G110 | Gate 110 | 2023-07-08 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110404003 | 404003 | SR15 ES - PSCD Bradan Trunk Main - Close Proximity Diversions | Water | G110 | Gate 110 | 2021-12-31 | 2022-04-29 | 2021_22_P09 | 2022_23_P01 | 2021_22_Q3 | 2022_23_Q1
G110404134 | 404134 | Tomatin WTW - Cartridge Filters and UV | Water | G110 | Gate 110 | 2022-03-18 | 2022-03-31 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110404135 | 404135 | Dalwhinnie WTW - TTU | Water | G110 | Gate 110 | 2023-10-28 | 2024-10-02 | 2023_24_P07 | 2024_25_P07 | 2023_24_Q3 | 2024_25_Q3
G110500052 | 500052 | Carstairs Village WwTW - Growth | Wastewater | G110 | Gate 110 | 2023-04-30 | 2023-09-06 | 2023_24_P01 | 2023_24_P06 | 2023_24_Q1 | 2023_24_Q2
G110500040 | 500040 | Bradan RSZ Cleaning Programme | Water | G110 | Gate 110 | 2022-01-29 | 2021-12-16 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110403986 | 403986 | SR15 ES - Carron Valley WTW Scada Replacement | Water | G110 | Gate 110 | 2024-01-13 | 2023-07-12 | 2023_24_P10 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2
G110500218 | 500218 | Inverness - DW5 Interventions | Water | G110 | Gate 110 | 2022-11-16 | 2022-04-01 | 2022_23_P08 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1
G110500068 | 500068 | Newtown St Boswells WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-03-24 | 2021-12-21 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110404069 | 404069 | Aviemore WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-01-29 | 2021-11-09 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110500030 | 500030 | Eela WTW to Sullom Voe | Water | G110 | Gate 110 | 2021-12-30 | 2022-03-10 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500235 | 500235 | Hatton of Cruden WwTW - Growth | Wastewater | G110 | Gate 110 | 2023-03-04 | 2023-03-24 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110500211 | 500211 | Picketlaw- DW5 Interventions | Water | G110 | Gate 110 | 2021-10-20 | 2022-03-31 | 2021_22_P07 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500154 | 500154 | Leven Valley DOA (DOA002460) Environmental Study | Wastewater | G110 | Gate 110 | 2021-10-29 | 2021-09-24 | 2021_22_P07 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110500206 | 500206 | Marchbank B - DW5 Interventions | Water | G110 | Gate 110 | 2021-05-05 | 2021-12-16 | 2021_22_P02 | 2021_22_P09 | 2021_22_Q1 | 2021_22_Q3
G110500207 | 500207 | Muirdykes- DW5 Interventions | Water | G110 | Gate 110 | 2022-09-21 | 2023-03-31 | 2022_23_P06 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G110500190 | 500190 | Climate Change Model for WRZ | Water | G110 | Gate 110 | 2021-12-07 | 2022-03-24 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500241 | 500241 | Fairmilehead C - DW5 Interventions | Water | G110 | Gate 110 | 2021-10-26 | 2021-12-21 | 2021_22_P07 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110500246 | 500246 | Ringford WTW | Water | G110 | Gate 110 | 2022-07-23 | 2023-11-01 | 2022_23_P04 | 2023_24_P08 | 2022_23_Q2 | 2023_24_Q3
G110500229 | 500229 | East Linton WwTW - Growth | Wastewater | G110 | Gate 110 | 2024-04-27 | 2025-04-15 | 2024_25_P01 | 2025_26_P01 | 2024_25_Q1 | 2025_26_Q1
G110404007 | 404007 | SR15 ES - Laighpark Paisley WWTW NS485655 | Wastewater | G110 | Gate 110 | 2022-11-19 | 2022-02-08 | 2022_23_P08 | 2021_22_P11 | 2022_23_Q3 | 2021_22_Q4
G110500573 | 500573 | Tullich WOA - Oban North and South TWS Refurbishment | Water | G110 | Gate 110 | 2023-03-29 | 2023-03-21 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110500575 | 500575 | Muirdykes WTW CM | Water | G110 | Gate 110 | 2023-05-23 | 2023-03-22 | 2023_24_P02 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110500576 | 500576 | Orphir Village WwTW - Enforcement Mitigations | Wastewater | G110 | Gate 110 | 2025-03-14 | 2024-08-02 | 2024_25_P12 | 2024_25_P05 | 2024_25_Q4 | 2024_25_Q2
G110500665 | 500665 | E1282 Carronflats Road Grangemouth | Wastewater | G110 | Gate 110 | 2022-10-17 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110404132 | 404132 | Picketlaw WTW - Main Out | Water | G110 | Gate 110 | 2026-11-12 | 2025-10-15 | 2026_27_P08 | 2025_26_P07 | 2026_27_Q3 | 2025_26_Q3
G110500244 | 500244 | Bonnycraig WTW | Water | G110 | Gate 110 | 2021-11-19 | 2021-07-30 | 2021_22_P08 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2
G110500302 | 500302 | W462 - Coalburn Road Coalburn | Wastewater | G110 | Gate 110 | 2023-03-31 | 2023-09-06 | 2022_23_P12 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G110500523 | 500523 | Ayrshire Strategic Resilience | Water | G110 | Gate 110 | 2024-06-20 | 2025-03-19 | 2024_25_P03 | 2024_25_P12 | 2024_25_Q1 | 2024_25_Q4
G110500509 | 500509 | South Edinburgh Service Resilience | Water | G110 | Gate 110 | 2022-05-25 | 2024-11-13 | 2022_23_P02 | 2024_25_P08 | 2022_23_Q1 | 2024_25_Q3
G110500299 | 500299 | E117 Brown Street Armadale | Wastewater | G110 | Gate 110 | 2022-07-21 | 2022-02-11 | 2022_23_P04 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4
G110500245 | 500245 | Galashiels Manse Street WTW | Water | G110 | Gate 110 | 2023-05-18 | 2024-05-16 | 2023_24_P02 | 2024_25_P02 | 2023_24_Q1 | 2024_25_Q1
G110500947 | 500947 | OD Dumfries Office Marchmount and Lincluden Depots | Support Services | G110 | Gate 110 | 2022-03-17 | 2022-07-27 | 2021_22_P12 | 2022_23_P04 | 2021_22_Q4 | 2022_23_Q2
G110500233 | 500233 | Burrelton WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-10-15 | 2023-09-06 | 2022_23_P07 | 2023_24_P06 | 2022_23_Q3 | 2023_24_Q2
G110500654 | 500654 | SE246 - Burnswark View Eaglesfield | Wastewater | G110 | Gate 110 | 2022-10-30 | 2023-03-26 | 2022_23_P07 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G110500579 | 500579 | Kinneil Kerse WwTW - Capital Maintenance | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-11-01 | 2022_23_P09 | 2023_24_P08 | 2022_23_Q3 | 2023_24_Q3
G110500742 | 500742 | Loch Calder WTW Disinfection Replacement | Water | G110 | Gate 110 | 2022-01-29 | 2022-11-18 | 2021_22_P10 | 2022_23_P08 | 2021_22_Q4 | 2022_23_Q3
G110501001 | 501001 | SR15 TE CM Staney Hill North - Q Sandy Loch WTW | Water | G110 | Gate 110 | 2023-11-17 | 2025-09-17 | 2023_24_P08 | 2025_26_P06 | 2023_24_Q3 | 2025_26_Q2
G110500652 | 500652 | SE847 Church Street Harbour Road Eyemouth | Wastewater | G110 | Gate 110 | 2022-08-10 | 2022-12-16 | 2022_23_P05 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3
G110500655 | 500655 | Barmore Road Tarbert | Wastewater | G110 | Gate 110 | 2022-12-27 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110500784 | 500784 | Springfield WwTW | Wastewater | G110 | Gate 110 | 2022-01-22 | 2021-11-24 | 2021_22_P10 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110500687 | 500687 | Whitecraigs Court Giffnock | Wastewater | G110 | Gate 110 | 2022-06-25 | 2022-03-30 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110404082 | 404082 | Loch Eck Caustic and Hypo Dosing Upgrade | Water | G110 | Gate 110 | 2022-06-11 | 2021-11-10 | 2022_23_P03 | 2021_22_P08 | 2022_23_Q1 | 2021_22_Q3
G110500843 | 500843 | Critical Reservoirs 500843 | Water | G110 | Gate 110 | 2021-12-30 | 2021-11-19 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110500709 | 500709 | Bradan WTW CM | Water | G110 | Gate 110 | 2022-07-12 | 2023-03-23 | 2022_23_P04 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G110500496 | 500496 | Lockerbie WWTW | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-30 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110500681 | 500681 | SW843 Wellgate Lanark | Wastewater | G110 | Gate 110 | 2023-06-14 | 2023-12-13 | 2023_24_P03 | 2023_24_P09 | 2023_24_Q1 | 2023_24_Q3
G110500661 | 500661 | E1010 Craigleith Road Edinburgh | Wastewater | G110 | Gate 110 | 2023-06-19 | 2023-03-27 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110500662 | 500662 | W646 - Brandon Gardens Prestwick | Wastewater | G110 | Gate 110 | 2022-08-25 | 2022-05-30 | 2022_23_P05 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G110500771 | 500771 | Westhill Service Reservoir | Water | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110500682 | 500682 | SW857 - Townhead Street Stonehouse | Wastewater | G110 | Gate 110 | 2023-06-04 | 2023-03-29 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110500892 | 500892 | Cowsrieve Service Reservoir | Water | G110 | Gate 110 | 2023-03-28 | 2024-01-10 | 2022_23_P12 | 2023_24_P10 | 2022_23_Q4 | 2023_24_Q4
G110500755 | 500755 | North Coast SCADA Replacement | Water | G110 | Gate 110 | 2024-08-23 | 2024-08-21 | 2024_25_P05 | 2024_25_P05 | 2024_25_Q2 | 2024_25_Q2
G110501216 | 501216 | Lintrathen WTW - QUALITY Disinfection | Water | G110 | Gate 110 | 2022-08-19 | 2022-10-26 | 2022_23_P05 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110500707 | 500707 | Longforgan Station Road WWPS 1995 NO316293 SR15 Capital Maintenance | Wastewater | G110 | Gate 110 | 2022-04-14 | 2021-12-22 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110500580 | 500580 | Forres WWTW 1973 NJ038595 - SR15 Capital Maintenance | Wastewater | G110 | Gate 110 | 2023-07-31 | 2023-11-29 | 2023_24_P04 | 2023_24_P08 | 2023_24_Q2 | 2023_24_Q3
G110500958 | 500958 | Sandy Loch WTW Additional RGF - CM | Water | G110 | Gate 110 | 2022-04-08 | 2022-03-29 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110500694 | 500694 | Bo ness WWTW NT022813 | Wastewater | G110 | Gate 110 | 2022-08-23 | 2023-03-15 | 2022_23_P05 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G110500695 | 500695 | St Andrews WwTW and St Andrews STC SR15-CM | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-10-22 | 2021_22_P10 | 2021_22_P07 | 2021_22_Q4 | 2021_22_Q3
G110500723 | 500723 | Alford WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-10-15 | 2022-08-31 | 2022_23_P07 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110500724 | 500724 | Udny Green WwTW - Growth | Wastewater | G110 | Gate 110 | 2025-10-04 | 2025-04-16 | 2025_26_P07 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1
G110501019 | 501019 | E1460 - Yetholm Park Dunfermline | Wastewater | G110 | Gate 110 | 2022-02-27 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110500729 | 500729 | Boughden Braes Lesmahagow Sewer Replacement | Wastewater | G110 | Gate 110 | 2025-08-07 | 2024-08-21 | 2025_26_P05 | 2024_25_P05 | 2025_26_Q2 | 2024_25_Q2
G110500918 | 500918 | Glendye - Belts of Collonach & Woodlands TM Rehabilitation | Water | G110 | Gate 110 | 2023-03-01 | 2022-11-08 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110501151 | 501151 | Cargenbridge SPS | Wastewater | G110 | Gate 110 | 2022-02-23 | 2021-12-22 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110501040 | 501040 | North Ronaldsay WTW Quality | Water | G110 | Gate 110 | 2022-03-01 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501200 | 501200 | Whitehall DSR CM | Water | G110 | Gate 110 | 2023-01-24 | 2022-11-30 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110501070 | 501070 | Kirkmichael WTW - CM | Water | G110 | Gate 110 | 2022-07-23 | 2027-07-21 | 2022_23_P04 | 2027_28_P04 | 2022_23_Q2 | 2027_28_Q2
G110501017 | 501017 | SW1015 - Shieldaig Road, Glasgow | Wastewater | G110 | Gate 110 | 2024-07-29 | 2024-01-24 | 2024_25_P04 | 2023_24_P10 | 2024_25_Q2 | 2023_24_Q4
G110500896 | 500896 | Craighead WTW - CM | Water | G110 | Gate 110 | 2023-08-08 | 2023-09-26 | 2023_24_P05 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
G110501390 | 501390 | WTW000627 - ROSEBERY WTW 1940 NT305570 | Water | G110 | Gate 110 | 2023-08-11 | 2024-03-05 | 2023_24_P05 | 2023_24_P12 | 2023_24_Q2 | 2023_24_Q4
G110501290 | 501290 | Ardersier WwTW - Growth | Wastewater | G110 | Gate 110 | 2023-04-30 | 2023-03-31 | 2023_24_P01 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110501153 | 501153 | Kirkconnel STW | Wastewater | G110 | Gate 110 | 2022-06-29 | 2023-03-29 | 2022_23_P03 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4
G110501217 | 501217 | Glenlatterach WTW Manganese Removal | Water | G110 | Gate 110 | 2022-06-01 | 2023-07-12 | 2022_23_P03 | 2023_24_P04 | 2022_23_Q1 | 2023_24_Q2
G110501091 | 501091 | Eela Water WTW QUALITY | Water | G110 | Gate 110 | 2022-10-13 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110501092 | 501092 | Stronsay WTW | Water | G110 | Gate 110 | 2021-11-18 | 2022-03-31 | 2021_22_P08 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500731 | 500731 | Newmachar WwTW - Growth | Wastewater | G110 | Gate 110 | 2025-06-07 | 2025-04-03 | 2025_26_P03 | 2025_26_P01 | 2025_26_Q1 | 2025_26_Q1
G110501219 | 501219 | Daer WTW - Improving WQ in Network (OMG5) | Water | G110 | Gate 110 | 2022-04-01 | 2022-01-20 | 2022_23_P01 | 2021_22_P10 | 2022_23_Q1 | 2021_22_Q4
G110501146 | 501146 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 5 | Water | G110 | Gate 110 | 2022-01-29 | 2021-07-30 | 2021_22_P10 | 2021_22_P04 | 2021_22_Q4 | 2021_22_Q2
G110501152 | 501152 | Haddington STW | Wastewater | G110 | Gate 110 | 2021-12-30 | 2022-03-16 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110500893 | 500893 | Craigmaddie and Milngavie VT Works | Water | G110 | Gate 110 | 2024-09-16 | 2025-04-16 | 2024_25_P06 | 2025_26_P01 | 2024_25_Q2 | 2025_26_Q1
G110500899 | 500899 | Drought Resilience Improved Hydrological Information Hydrology Modelling and CAR Licences | Water | G110 | Gate 110 | 2021-12-17 | 2022-03-29 | 2021_22_P09 | 2021_22_P12 | 2021_22_Q3 | 2021_22_Q4
G110501159 | 501159 | Alloa STW | Wastewater | G110 | Gate 110 | 2024-03-20 | 2026-03-18 | 2023_24_P12 | 2025_26_P12 | 2023_24_Q4 | 2025_26_Q4
G110501227 | 501227 | Lintrathen WTW - QUALITY (Reduction of risks identified in Drinking Water Safety Plan - Transmission | Water | G110 | Gate 110 | 2022-05-18 | 2021-06-29 | 2022_23_P02 | 2021_22_P03 | 2022_23_Q1 | 2021_22_Q1
G110501574 | 501574 | Greenock WTW | Water | G110 | Gate 110 | 2021-06-16 | 2022-03-24 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G110501168 | 501168 | Ochiltree STW | Wastewater | G110 | Gate 110 | 2023-02-28 | 2023-03-29 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110501169 | 501169 | Meadowhead STW | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-11-15 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110501144 | 501144 | Improving Reliability of WQ in Network - Emerging SR Risks - PHASE 3 | Water | G110 | Gate 110 | 2022-10-22 | 2022-04-28 | 2022_23_P07 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1
G110501203 | 501203 | Lomond Hills WTW - CM | Water | G110 | Gate 110 | 2021-12-11 | 2021-07-30 | 2021_22_P09 | 2021_22_P04 | 2021_22_Q3 | 2021_22_Q2
G110501233 | 501233 | Herricks WTW - QUALITY | Water | G110 | Gate 110 | 2022-04-30 | 2021-10-29 | 2022_23_P01 | 2021_22_P07 | 2022_23_Q1 | 2021_22_Q3
G110501599 | 501599 | Southpark Avenue Barrhead Repair Sewer | Wastewater | G110 | Gate 110 | 2022-03-31 | 2023-03-26 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4
G110501352 | 501352 | Battery Park WWPS | Wastewater | G110 | Gate 110 | 2022-09-09 | 2022-12-21 | 2022_23_P06 | 2022_23_P09 | 2022_23_Q2 | 2022_23_Q3
G110501158 | 501158 | Ardoch STW | Wastewater | G110 | Gate 110 | 2022-03-04 | 2022-09-28 | 2021_22_P12 | 2022_23_P06 | 2021_22_Q4 | 2022_23_Q2
G110501021 | 501021 | Banchory WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-09-10 | 2022_23_P09 | 2023_24_P06 | 2022_23_Q3 | 2023_24_Q2
G110501518 | 501518 | STEVENSTON POINT WWTW NS275404 | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-03-31 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110501642 | 501642 | Loch Eck | Water | G110 | Gate 110 | 2021-12-30 | 2021-10-28 | 2021_22_P09 | 2021_22_P07 | 2021_22_Q3 | 2021_22_Q3
G110501232 | 501232 | Whitehillocks WTW - Quality and CM | Water | G110 | Gate 110 | 2022-11-03 | 2024-06-26 | 2022_23_P08 | 2024_25_P03 | 2022_23_Q3 | 2024_25_Q1
G110501165 | 501165 | Rothesay STW | Wastewater | G110 | Gate 110 | 2022-03-17 | 2022-02-28 | 2021_22_P12 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501218 | 501218 | Badentinan WTW - Quality | Water | G110 | Gate 110 | 2022-05-28 | 2022-10-31 | 2022_23_P02 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G110501156 | 501156 | Tillicoultry STW | Wastewater | G110 | Gate 110 | 2022-07-12 | 2023-02-27 | 2022_23_P04 | 2022_23_P11 | 2022_23_Q2 | 2022_23_Q4
G110501402 | 501402 | DALMACOULTER DSR NS767679 | Water | G110 | Gate 110 | 2022-02-05 | 2021-11-12 | 2021_22_P11 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110501512 | 501512 | INSH WWTW 1996 NH809016 | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-06-12 | 2024_25_P10 | 2024_25_P03 | 2024_25_Q4 | 2024_25_Q1
G110501720 | 501720 | Cambuslang SPS 2 RM - Replace Rising Main | Wastewater | G110 | Gate 110 | 2022-05-31 | 2022-02-28 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110501632 | 501632 | CMA Market Releases | Support Services | G110 | Gate 110 | 2022-02-05 | 2021-06-30 | 2021_22_P11 | 2021_22_P03 | 2021_22_Q4 | 2021_22_Q1
G110501635 | 501635 | Happendon - Camps TM Douglas Water Crossing | Water | G110 | Gate 110 | 2022-03-31 | 2021-08-31 | 2021_22_P12 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110501393 | 501393 | WTW000712 - HOWDEN WTW NT456275 | Water | G110 | Gate 110 | 2023-02-28 | 2023-11-01 | 2022_23_P11 | 2023_24_P08 | 2022_23_Q4 | 2023_24_Q3
G110501579 | 501579 | DALDERSE WWTW 1966 NS903822 | Wastewater | G110 | Gate 110 | 2023-09-30 | 2023-12-13 | 2023_24_P06 | 2023_24_P09 | 2023_24_Q2 | 2023_24_Q3
G110501379 | 501379 | WTW000640 - MARCHBANK WTW NT165645 | Water | G110 | Gate 110 | 2023-06-30 | 2023-12-13 | 2023_24_P03 | 2023_24_P09 | 2023_24_Q1 | 2023_24_Q3
G110501670 | 501670 | DAER WOA - Stablewood Pipe Bridge - H&S upgrade | Water | G110 | Gate 110 | 2025-06-05 | 2024-11-27 | 2025_26_P03 | 2024_25_P08 | 2025_26_Q1 | 2024_25_Q3
G110501666 | 501666 | Hungry Snout | Water | G110 | Gate 110 | 2022-03-26 | 2023-02-27 | 2021_22_P12 | 2022_23_P11 | 2021_22_Q4 | 2022_23_Q4
G110501243 | 501243 | Invercannie WTW Pre-Treatment CWT and CM | Water | G110 | Gate 110 | 2023-11-02 | 2024-01-24 | 2023_24_P08 | 2023_24_P10 | 2023_24_Q3 | 2023_24_Q4
G110501258 | 501258 | Sanday WTW - CM | Water | G110 | Gate 110 | 2021-12-24 | 2021-11-12 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110501259 | 501259 | Backies WOA Brora Dalchalm and Victoria Road Mains Rehab | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110501388 | 501388 | WTW000626 - PATESHILL WTW NS983595 | Water | G110 | Gate 110 | 2022-11-01 | 2023-07-26 | 2022_23_P08 | 2023_24_P04 | 2022_23_Q3 | 2023_24_Q2
G110501488 | 501488 | STRAN LARG ROAD WWPS No 1 NX048623 | Wastewater | G110 | Gate 110 | 2022-12-29 | 2022-08-31 | 2022_23_P09 | 2022_23_P05 | 2022_23_Q3 | 2022_23_Q2
G110501499 | 501499 | PATNA WWTW NS414124 | Wastewater | G110 | Gate 110 | 2022-11-22 | 2023-01-31 | 2022_23_P08 | 2022_23_P10 | 2022_23_Q3 | 2022_23_Q4
G110501500 | 501500 | Earlston WwTW | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-02-28 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110501592 | 501592 | EARLSTON WWTW 1959 NT573382 | Wastewater | G110 | Gate 110 | 2022-02-28 | 2022-03-16 | 2021_22_P11 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110501593 | 501593 | LUGAR WWPS NS585207 | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-22 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110501600 | 501600 | Glendevon WTW - Quality (Reduce high Production risks in DWSP) | Water | G110 | Gate 110 | 2022-04-12 | 2022-02-24 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110501639 | 501639 | Telemetry Application Consolidation | Support Services | G110 | Gate 110 | 2022-03-16 | 2021-11-29 | 2021_22_P12 | 2021_22_P08 | 2021_22_Q4 | 2021_22_Q3
G110501683 | 501683 | Shieldhall WWTW Grade 5 HC Sewer Ph1 | Wastewater | G110 | Gate 110 | 2022-08-31 | 2023-10-18 | 2022_23_P05 | 2023_24_P07 | 2022_23_Q2 | 2023_24_Q3
G110501573 | 501573 | Dougliehill WTW | Water | G110 | Gate 110 | 2021-12-25 | 2021-06-10 | 2021_22_P09 | 2021_22_P03 | 2021_22_Q3 | 2021_22_Q1
G110501731 | 501731 | Kerse TWS Refurb | Water | G110 | Gate 110 | 2025-05-01 | 2024-06-12 | 2025_26_P02 | 2024_25_P03 | 2025_26_Q1 | 2024_25_Q1
G110501436 | 501436 | 500788 - Alexandria WTW | Water | G110 | Gate 110 | 2022-01-27 | 2022-03-23 | 2021_22_P10 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110501829 | 501829 | Daldowie WWTW Grade 5 HC Sewer | Wastewater | G110 | Gate 110 | 2022-09-11 | 2022-10-14 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110501703 | 501703 | Station Rd - Nairn Rd Ardersier - replace sewer | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-05-29 | 2024_25_P10 | 2024_25_P02 | 2024_25_Q4 | 2024_25_Q1
G110501418 | 501418 | 500122 - Ness WTW | Water | G110 | Gate 110 | 2022-09-03 | 2023-07-12 | 2022_23_P06 | 2023_24_P04 | 2022_23_Q2 | 2023_24_Q2
G110501421 | 501421 | 500793 - Carrick Castle WTW | Water | G110 | Gate 110 | 2021-12-31 | 2021-12-21 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110501554 | 501554 | Carfin Incident - MD interventions | Water | G110 | Gate 110 | 2023-08-11 | 2023-11-29 | 2023_24_P05 | 2023_24_P08 | 2023_24_Q2 | 2023_24_Q3
G110501739 | 501739 | Meadowhead WwTW HCS | Wastewater | G110 | Gate 110 | 2022-04-22 | 2023-03-26 | 2022_23_P01 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4
G110501898 | 501898 | Cost Investment Intelligence Project for EES and SWISS Strategic Refresh Upgrade | Support Services | G110 | Gate 110 | 2022-06-30 | 2022-07-27 | 2022_23_P03 | 2022_23_P04 | 2022_23_Q1 | 2022_23_Q2
G110502243 | 502243 | Mannofield WTW -Improvements to Treatment Process | Water | G110 | Gate 110 | 2025-08-01 | 2025-07-09 | 2025_26_P05 | 2025_26_P04 | 2025_26_Q2 | 2025_26_Q2
G110502231 | 502231 | South WWTW MCC Replacements Phase 1 | Wastewater | G110 | Gate 110 | 2022-01-01 | 2021-12-21 | 2021_22_P10 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110501818 | 501818 | LIMS Refresh | Support Services | G110 | Gate 110 | 2022-04-28 | 2021-12-21 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110502246 | 502246 | Rosebery WTW Lime to Caustic | Water | G110 | Gate 110 | 2022-04-12 | 2022-08-22 | 2022_23_P01 | 2022_23_P05 | 2022_23_Q1 | 2022_23_Q2
G110502267 | 502267 | HV Asset Replacement Phase 1 - Laighpark WwTW | Wastewater | G110 | Gate 110 | 2022-01-21 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G110502268 | 502268 | HV Asset Replacement Phase 1 - Shieldhall WwTW | Wastewater | G110 | Gate 110 | 2023-01-13 | 2023-10-04 | 2022_23_P10 | 2023_24_P07 | 2022_23_Q4 | 2023_24_Q3
G110502132 | 502132 | Burncrooks WTW Quality THM Compliance | Water | G110 | Gate 110 | 2023-10-21 | 2024-07-24 | 2023_24_P07 | 2024_25_P04 | 2023_24_Q3 | 2024_25_Q2
G110502269 | 502269 | HV Asset Replacement Phase 1 - Stevenston Point WwTW | Wastewater | G110 | Gate 110 | 2022-01-11 | 2022-01-27 | 2021_22_P10 | 2021_22_P10 | 2021_22_Q4 | 2021_22_Q4
G110502332 | 502332 | Drumnadrochit WwTW - Growth | Wastewater | G110 | Gate 110 | 2024-07-19 | 2024-01-10 | 2024_25_P04 | 2023_24_P10 | 2024_25_Q2 | 2023_24_Q4
G110502281 | 502281 | Savalbeg WTW Sludge Lagoon Upgrade | Wastewater | G110 | Gate 110 | 2022-08-20 | 2022-08-26 | 2022_23_P05 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G110502280 | 502280 | Londornoch WTW Sludge Lagoon Upgrade | Wastewater | G110 | Gate 110 | 2022-12-06 | 2023-08-23 | 2022_23_P09 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2
G110502282 | 502282 | Oykel Bridge - Radon | Water | G110 | Gate 110 | 2024-06-10 | 2023-08-09 | 2024_25_P03 | 2023_24_P05 | 2024_25_Q1 | 2023_24_Q2
G110502220 | 502220 | IR18 Allowance - Edgehead Septic Tank | Wastewater | G110 | Gate 110 | 2026-05-14 | 2025-03-19 | 2026_27_P02 | 2024_25_P12 | 2026_27_Q1 | 2024_25_Q4
G110502329 | 502329 | Loch Thom MIOS Drawdown & Freebaoard Enhancement | Water | G110 | Gate 110 | 2022-05-10 | 2022-02-25 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110502425 | 502425 | SW599 - Laighlands Road Bothwell | Wastewater | G110 | Gate 110 | 2025-05-11 | 2024-02-21 | 2025_26_P02 | 2023_24_P11 | 2025_26_Q1 | 2023_24_Q4
G110502375 | 502375 | W574 1-21 Clarkston Road, Glasgow | Wastewater | G110 | Gate 110 | 2024-04-13 | 2023-07-26 | 2024_25_P01 | 2023_24_P04 | 2024_25_Q1 | 2023_24_Q2
G110502212 | 502212 | IR18 Allowance - Newton Septic Tank | Wastewater | G110 | Gate 110 | 2024-07-20 | 2023-08-09 | 2024_25_P04 | 2023_24_P05 | 2024_25_Q2 | 2023_24_Q2
G110502342 | 502342 | MCC SR15- Hamilton WWTW MCC Replacement | Wastewater | G110 | Gate 110 | 2022-11-22 | 2023-02-20 | 2022_23_P08 | 2022_23_P11 | 2022_23_Q3 | 2022_23_Q4
G110502584 | 502584 | Carbarns WwTW - Inlet Screen Replacement | Wastewater | G110 | Gate 110 | 2021-12-31 | 2021-12-16 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110502578 | 502578 | Johnstone Black Cart Aerial Sewer | Wastewater | G110 | Gate 110 | 2023-01-26 | 2022-06-30 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1
G110502358 | 502358 | Black Esk and Winterhope WOA - Gretna Water Supply | Water | G110 | Gate 110 | 2025-03-03 | 2025-02-13 | 2024_25_P12 | 2024_25_P11 | 2024_25_Q4 | 2024_25_Q4
G110502383 | 502383 | IR18 Allowance - Fife - Abstraction Improvement | Water | G110 | Gate 110 | 2022-09-20 | 2022-07-27 | 2022_23_P06 | 2022_23_P04 | 2022_23_Q2 | 2022_23_Q2
G110502412 | 502412 | Bradan WTW Water Quality | Water | G110 | Gate 110 | 2022-03-26 | 2023-03-31 | 2021_22_P12 | 2022_23_P12 | 2021_22_Q4 | 2022_23_Q4
G110502380 | 502380 | IR18 Allowance - Forth Valley - Abstraction Improvement | Water | G110 | Gate 110 | 2021-12-31 | 2022-10-19 | 2021_22_P09 | 2022_23_P07 | 2021_22_Q3 | 2022_23_Q3
G110502382 | 502382 | IR18 Allowance - East Berwickshire - Abstraction Improvement | Water | G110 | Gate 110 | 2022-07-30 | 2022-10-19 | 2022_23_P04 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110502369 | 502369 | Beasdale WTW UV Alterations | Water | G110 | Gate 110 | 2025-05-12 | 2024-08-21 | 2025_26_P02 | 2024_25_P05 | 2025_26_Q1 | 2024_25_Q2
G110502895 | 502895 | SW1392 - Third Avenue Glasgow | Wastewater | G110 | Gate 110 | 2023-06-15 | 2023-03-29 | 2023_24_P03 | 2022_23_P12 | 2023_24_Q1 | 2022_23_Q4
G110502896 | 502896 | Barcraigs Drawdown Capacity Enhancement (MIoS) | Water | G110 | Gate 110 | 2022-07-13 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502648 | 502648 | IR18 Allowance - Ardrishaig WTW | Water | G110 | Gate 110 | 2023-08-23 | 2024-02-21 | 2023_24_P05 | 2023_24_P11 | 2023_24_Q2 | 2023_24_Q4
G110502741 | 502741 | WATER OF LEITH UIDs BATCH 2 Currie Old Mill Off Lanark Road CSO and Juniper Green | Wastewater | G110 | Gate 110 | 2022-04-22 | 2022-03-24 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110502742 | 502742 | WATER OF LEITH UIDs BATCH 3 Juniper Green Off Lanark Road CSO | Wastewater | G110 | Gate 110 | 2022-07-15 | 2022-03-29 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502747 | 502747 | WATER OF LEITH UIDs BATCH 8 Kingsknowe R 0 29 Dovecot Grove CSO | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-05-30 | 2022_23_P04 | 2022_23_P02 | 2022_23_Q2 | 2022_23_Q1
G110502765 | 502765 | WATER OF LEITH UIDs - BATCH 9.2 - Currie GDN 2A Lanark Road West CSO | Wastewater | G110 | Gate 110 | 2022-07-27 | 2022-09-16 | 2022_23_P04 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G110502651 | 502651 | Afton WTW_Ayrshire_THM Research and Investigation | Water | G110 | Gate 110 | 2023-04-19 | 2024-03-20 | 2023_24_P01 | 2023_24_P12 | 2023_24_Q1 | 2023_24_Q4
G110502652 | 502652 | IR18 Allowance - Barra WTW | Water | G110 | Gate 110 | 2023-10-16 | 2023-05-17 | 2023_24_P07 | 2023_24_P02 | 2023_24_Q3 | 2023_24_Q1
G110502827 | 502827 | Tarves WwTW - Growth | Wastewater | G110 | Gate 110 | 2022-10-14 | 2022-09-26 | 2022_23_P07 | 2022_23_P06 | 2022_23_Q3 | 2022_23_Q2
G110502606 | 502606 | Greenock RSZ - DW5 Interventions Phase 2 | Water | G110 | Gate 110 | 2021-05-19 | 2021-10-28 | 2021_22_P02 | 2021_22_P07 | 2021_22_Q1 | 2021_22_Q3
G110502780 | 502780 | Erskine WwTW Coarse Screens Replacement CM | Wastewater | G110 | Gate 110 | 2022-03-12 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110502772 | 502772 | Daer WRZ SR Residual Chorine Monitors | Water | G110 | Gate 110 | 2022-02-09 | 2021-12-03 | 2021_22_P11 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110502392 | 502392 | Barrhead South SDO | Water | G110 | Gate 110 | 2023-06-14 | 2023-06-28 | 2023_24_P03 | 2023_24_P03 | 2023_24_Q1 | 2023_24_Q1
G110502743 | 502743 | WATER OF LEITH UIDs BATCH 4 Balerno Bridge Road CSOs | Wastewater | G110 | Gate 110 | 2023-03-14 | 2023-03-23 | 2022_23_P12 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110502746 | 502746 | WATER OF LEITH UIDs BATCH 7 Longstone CSOs | Wastewater | G110 | Gate 110 | 2026-01-17 | 2024-08-21 | 2025_26_P10 | 2024_25_P05 | 2025_26_Q4 | 2024_25_Q2
G110502947 | 502947 | IR18 CAS Compliance Improvements - WWTW North, Complex | Wastewater | G110 | Gate 110 | 2022-04-26 | 2022-03-23 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110502740 | 502740 | WATER OF LEITH UIDs BATCH 1 South Gyle Gogarloch SPS EO | Wastewater | G110 | Gate 110 | 2022-05-28 | 2021-12-21 | 2022_23_P02 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110502783 | 502783 | Balmore Pipebridge Repairs | Water | G110 | Gate 110 | 2023-03-24 | 2024-07-24 | 2022_23_P12 | 2024_25_P04 | 2022_23_Q4 | 2024_25_Q2
G110502955 | 502955 | EFOS - A8 East Hamilton Street Greenock | Wastewater | G110 | Gate 110 | 2025-10-09 | 2024-05-01 | 2025_26_P07 | 2024_25_P02 | 2025_26_Q3 | 2024_25_Q1
G110502563 | 502563 | IR18 Allowance - Dye Water Fish Pass | Water | G110 | Gate 110 | 2022-10-19 | 2022-04-08 | 2022_23_P07 | 2022_23_P01 | 2022_23_Q3 | 2022_23_Q1
G110502748 | 502748 | WATER OF LEITH UIDs BATCH 9.1 Currie Kinleith Ind Est CSO | Wastewater | G110 | Gate 110 | 2023-04-24 | 2022-09-16 | 2023_24_P01 | 2022_23_P06 | 2023_24_Q1 | 2022_23_Q2
G110502749 | 502749 | WATER OF LEITH UIDs - BATCH 10 - Gyle Public Park No1 and No2 CSOs | Wastewater | G110 | Gate 110 | 2023-02-08 | 2023-03-23 | 2022_23_P11 | 2022_23_P12 | 2022_23_Q4 | 2022_23_Q4
G110502792 | 502792 | Lease line telecoms OFCOM deregulation | Support Services | G110 | Gate 110 | 2021-12-01 | 2021-04-13 | 2021_22_P09 | 2021_22_P01 | 2021_22_Q3 | 2021_22_Q1
G110502605 | 502605 | Carron Valley RSZ Cleaning - Mains Conditioning | Water | G110 | Gate 110 | 2022-07-01 | 2022-06-30 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G110502808 | 502808 | NRSWA Construction Water A9 Dualling Luncarty to Birnam | Water | G110 | Gate 110 | 2022-08-03 | 2022-02-10 | 2022_23_P05 | 2021_22_P11 | 2022_23_Q2 | 2021_22_Q4
G110502958 | 502958 | Aboyne WwTW - Capital Maintenance | Wastewater | G110 | Gate 110 | 2023-09-30 | 2023-09-06 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
G110502600 | 502600 | Back Tolsta- Main out form North Lochs | Water | G110 | Gate 110 | 2022-10-11 | 2023-03-30 | 2022_23_P07 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G110502934 | 502934 | Flemington Road Glenrothes Sewer Rehab | Wastewater | G110 | Gate 110 | 2022-07-04 | 2022-03-24 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110502944 | 502944 | IR18 CAS Compliance Improvements - Networks East & North, Complex | Wastewater | G110 | Gate 110 | 2022-06-07 | 2024-02-21 | 2022_23_P03 | 2023_24_P11 | 2022_23_Q1 | 2023_24_Q4
G110502649 | 502649 | Dhu Loch_Argyll and Bute_THM Research and Investigation | Water | G110 | Gate 110 | 2023-10-31 | 2024-01-10 | 2023_24_P07 | 2023_24_P10 | 2023_24_Q3 | 2023_24_Q4
G110502650 | 502650 | IR18 Allowance - Tarbert WTW | Water | G110 | Gate 110 | 2023-09-20 | 2023-10-04 | 2023_24_P06 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3
G110502866 | 502866 | NRSWA Construction Sewer Greenhills Road Widening East Kilbride | Wastewater | G110 | Gate 110 | 2022-10-15 | 2023-08-23 | 2022_23_P07 | 2023_24_P05 | 2022_23_Q3 | 2023_24_Q2
G110502867 | 502867 | NRSWA Construction Water Greenhills Road Widening East Kilbride | Water | G110 | Gate 110 | 2022-10-15 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110502853 | 502853 | Chemical Dosing Programme - Phase 1 - Glendevon WTW | Water | G110 | Gate 110 | 2023-07-23 | 2023-01-25 | 2023_24_P04 | 2022_23_P10 | 2023_24_Q2 | 2022_23_Q4
G110502945 | 502945 | IR18 CAS Compliance Improvements - Networks South & West, Complex | Wastewater | G110 | Gate 110 | 2022-06-30 | 2023-03-10 | 2022_23_P03 | 2022_23_P12 | 2022_23_Q1 | 2022_23_Q4
G110502946 | 502946 | IR18 CAS Compliance Improvements - WWTW East Complex | Wastewater | G110 | Gate 110 | 2022-09-03 | 2023-03-10 | 2022_23_P06 | 2022_23_P12 | 2022_23_Q2 | 2022_23_Q4
G110502949 | 502949 | Dunfermline Wellwood Waste Water Infrastructure | Wastewater | G110 | Gate 110 | 2023-03-08 | 2024-05-29 | 2022_23_P12 | 2024_25_P02 | 2022_23_Q4 | 2024_25_Q1
G110503119 | 503119 | IR18 Network Segregation Treatment | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503037 | 503037 | NRSWA Construction Water-A77 Maybole Bypass | Water | G110 | Gate 110 | 2021-12-30 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503050 | 503050 | Wishaw TM Water Quality | Water | G110 | Gate 110 | 2023-05-22 | 2023-07-12 | 2023_24_P02 | 2023_24_P04 | 2023_24_Q1 | 2023_24_Q2
G110503072 | 503072 | Turriff WTW - Essential CM | Water | G110 | Gate 110 | 2023-07-01 | 2023-03-30 | 2023_24_P04 | 2022_23_P12 | 2023_24_Q2 | 2022_23_Q4
G110502857 | 502857 | Chemical Dosing Programme - Phase 1 - Turriff WTW | Water | G110 | Gate 110 | 2024-03-16 | 2024-01-10 | 2023_24_P12 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G110502943 | 502943 | IR18 CAS Compliance Improvements - WWTW, Non Complex | Wastewater | G110 | Gate 110 | 2022-06-07 | 2022-10-12 | 2022_23_P03 | 2022_23_P07 | 2022_23_Q1 | 2022_23_Q3
G110503106 | 503106 | Newfield Trunk Main Reinforcement | Water | G110 | Gate 110 | 2021-12-23 | 2021-09-28 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503083 | 503083 | IR18 - 59077 - Inner Clyde Estuary Modelling | Wastewater | G110 | Gate 110 | 2022-03-15 | 2022-03-24 | 2021_22_P12 | 2021_22_P12 | 2021_22_Q4 | 2021_22_Q4
G110502940 | 502940 | Fair Isle WTW - Quality | Water | G110 | Gate 110 | 2023-01-11 | 2023-09-20 | 2022_23_P10 | 2023_24_P06 | 2022_23_Q4 | 2023_24_Q2
G110503193 | 503193 | Water Quality Improvement- Amlaird Flushing RSZ | Water | G110 | Gate 110 | 2021-12-01 | 2021-12-15 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110503194 | 503194 | Amlaird RSZ - DW5 Interventions | Water | G110 | Gate 110 | 2022-01-26 | 2022-02-28 | 2021_22_P10 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110503256 | 503256 | Water Quality Improvement - Greenock Phase 2 - Conditioning | Water | G110 | Gate 110 | 2022-04-06 | 2022-03-30 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503257 | 503257 | Water Quality Improvement - Greenock Phase 2 - Flushing | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503045 | 503045 | Winchburgh WwTW - Growth Intermediate Solution Support | Wastewater | G110 | Gate 110 | 2022-04-02 | 2022-02-01 | 2022_23_P01 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110503195 | 503195 | IR18 Water Quality Improvement - Camps RSZ | Water | G110 | Gate 110 | 2023-05-31 | 2022-03-30 | 2023_24_P02 | 2021_22_P12 | 2023_24_Q1 | 2021_22_Q4
G110503197 | 503197 | IR18 Water Quality Improvement - Pateshill RSZ | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-31 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503198 | 503198 | IR18 Water Quality Improvement - Rawburn RSZ | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503199 | 503199 | IR18 Water Quality Improvement - Roberton RSZ | Water | G110 | Gate 110 | 2022-10-19 | 2022-03-30 | 2022_23_P07 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503200 | 503200 | IR18 Water Quality Improvement - Spynie RSZ | Water | G110 | Gate 110 | 2022-04-20 | 2021-12-23 | 2022_23_P01 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110503177 | 503177 | IR18 External Flooding Clarkston | Wastewater | G110 | Gate 110 | 2022-08-18 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503120 | 503120 | IR18 Network Segregation Datacentre | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-31 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503229 | 503229 | Dalmuir Wastewater Strategy Review | Wastewater | G110 | Gate 110 | 2022-09-10 | 2022-09-13 | 2022_23_P06 | 2022_23_P06 | 2022_23_Q2 | 2022_23_Q2
G110503092 | 503092 | Legbrannock DSR | Water | G110 | Gate 110 | 2024-12-09 | 2024-06-12 | 2024_25_P09 | 2024_25_P03 | 2024_25_Q3 | 2024_25_Q1
G110503170 | 503170 | Milngavie M1 RSZ Trunk Mains | Water | G110 | Gate 110 | 2021-06-30 | 2022-03-31 | 2021_22_P03 | 2021_22_P12 | 2021_22_Q1 | 2021_22_Q4
G110503234 | 503234 | Allt Sanna WFPM | Water | G110 | Gate 110 | 2022-09-20 | 2022-03-18 | 2022_23_P06 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503235 | 503235 | Galashiels Manse Street Infra | Water | G110 | Gate 110 | 2023-08-31 | 2024-01-24 | 2023_24_P05 | 2023_24_P10 | 2023_24_Q2 | 2023_24_Q4
G110503249 | 503249 | IR18 Investigate Future Changes in the Occurrance of Algal Blooms | Water | G110 | Gate 110 | 2022-01-20 | 2023-01-25 | 2021_22_P10 | 2022_23_P10 | 2021_22_Q4 | 2022_23_Q4
G110503162 | 503162 | Auchneel WTW - Lime to Caustic | Water | G110 | Gate 110 | 2023-05-10 | 2024-05-15 | 2023_24_P02 | 2024_25_P02 | 2023_24_Q1 | 2024_25_Q1
G110503248 | 503248 | IR18 THM- TOC Catchment Manangement Study -Pateshill | Water | G110 | Gate 110 | 2021-12-29 | 2023-03-29 | 2021_22_P09 | 2022_23_P12 | 2021_22_Q3 | 2022_23_Q4
G110503393 | 503393 | Ayr Shore Road SPS - Emergency Repairs to Transfer Pumps and Wet Well Guide Rails | Wastewater | G110 | Gate 110 | 2022-08-04 | 2023-10-18 | 2022_23_P05 | 2023_24_P07 | 2022_23_Q2 | 2023_24_Q3
G110503121 | 503121 | IR18 Legacy Infrastructure | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-03-11 | 2022_23_P01 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503336 | 503336 | Water Quality Improvement-Wick East DMA | Water | G110 | Gate 110 | 2023-06-14 | 2024-05-29 | 2023_24_P03 | 2024_25_P02 | 2023_24_Q1 | 2024_25_Q1
G110503094 | 503094 | IR18 - 59034 - Legacy sludge requirement at Operational Sites | Water | G110 | Gate 110 | 2021-12-31 | 2022-01-20 | 2021_22_P09 | 2021_22_P10 | 2021_22_Q3 | 2021_22_Q4
G110503291 | 503291 | IR18 Security Operations Tools | Support Services | G110 | Gate 110 | 2022-04-28 | 2022-05-06 | 2022_23_P01 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G110503230 | 503230 | Main Street Kirkconnel Pipe Bridge | Wastewater | G110 | Gate 110 | 2024-03-16 | 2023-07-26 | 2023_24_P12 | 2023_24_P04 | 2023_24_Q4 | 2023_24_Q2
G110503110 | 503110 | IR18 Tighnabruaich Lead Comms Investigation and Replacement | Water | G110 | Gate 110 | 2024-02-25 | 2024-01-10 | 2023_24_P11 | 2023_24_P10 | 2023_24_Q4 | 2023_24_Q4
G110503480 | 503480 | Kettleton Impounding Reservoir | Water | G110 | Gate 110 | 2025-05-11 | 2024-09-18 | 2025_26_P02 | 2024_25_P06 | 2025_26_Q1 | 2024_25_Q2
G110503266 | 503266 | Howden WTW Chloramination | Water | G110 | Gate 110 | 2022-02-28 | 2021-09-21 | 2021_22_P11 | 2021_22_P06 | 2021_22_Q4 | 2021_22_Q2
G110503239 | 503239 | Sharphill_Saltcoats | Water | G110 | Gate 110 | 2024-07-10 | 2022-11-02 | 2024_25_P04 | 2022_23_P08 | 2024_25_Q2 | 2022_23_Q3
G110503243 | 503243 | IR18 Daer WTW Bacti Risk Reduction Study | Water | G110 | Gate 110 | 2021-12-16 | 2021-09-13 | 2021_22_P09 | 2021_22_P06 | 2021_22_Q3 | 2021_22_Q2
G110503250 | 503250 | Carron Valley RSZ Cleaning – Flushing | Water | G110 | Gate 110 | 2023-01-25 | 2022-11-14 | 2022_23_P10 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110503236 | 503236 | IR18- Investigation of Long Term DOC increases in Drinking Water Catchments | Water | G110 | Gate 110 | 2022-01-05 | 2021-08-30 | 2021_22_P10 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110503237 | 503237 | IR18 THM- TOC Catchment Manangement - Forehill | Water | G110 | Gate 110 | 2021-12-29 | 2021-12-17 | 2021_22_P09 | 2021_22_P09 | 2021_22_Q3 | 2021_22_Q3
G110503269 | 503269 | Dalmarnock WWTW Improvements | Wastewater | G110 | Gate 110 | 2023-02-16 | 2024-04-03 | 2022_23_P11 | 2024_25_P01 | 2022_23_Q4 | 2024_25_Q1
G110503362 | 503362 | Infra-Kingdom Park | Wastewater | G110 | Gate 110 | 2024-06-12 | 2024-11-13 | 2024_25_P03 | 2024_25_P08 | 2024_25_Q1 | 2024_25_Q3
G110503408 | 503408 | Blairlinnans PSC TM Monitoring | Water | G110 | Gate 110 | 2023-08-27 | 2022-12-21 | 2023_24_P05 | 2022_23_P09 | 2023_24_Q2 | 2022_23_Q3
G110503412 | 503412 | Dalmacoulter WSZ Trunk Main Cleaning | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503413 | 503413 | Garbethill WSZ Trunk Main Cleaning | Water | G110 | Gate 110 | 2022-12-28 | 2022-03-30 | 2022_23_P09 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503415 | 503415 | Bothwell Sewer - Replacement of approximatly 130m of 600mm | Wastewater | G110 | Gate 110 | 2023-01-21 | 2023-06-28 | 2022_23_P10 | 2023_24_P03 | 2022_23_Q4 | 2023_24_Q1
G110503418 | 503418 | Mauldslie Access Road & Bridge Repairs | Wastewater | G110 | Gate 110 | 2022-07-01 | 2022-06-07 | 2022_23_P04 | 2022_23_P03 | 2022_23_Q2 | 2022_23_Q1
G110503421 | 503421 | Stornoway WTW - Interim THM and Cryptosporidium measures | Water | G110 | Gate 110 | 2023-12-31 | 2023-08-23 | 2023_24_P09 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2
G110503424 | 503424 | Linwood WwPS - Emergency Works | Wastewater | G110 | Gate 110 | 2021-12-18 | 2021-11-26 | 2021_22_P09 | 2021_22_P08 | 2021_22_Q3 | 2021_22_Q3
G110503434 | 503434 | IR18 Daer CWT | Water | G110 | Gate 110 | 2022-12-30 | 2023-03-28 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G110503441 | 503441 | Oldmeldrum STW - Surface Aerator Replacement & Interim Oxymem Install | Wastewater | G110 | Gate 110 | 2024-05-16 | 2023-11-29 | 2024_25_P02 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3
G110503562 | 503562 | Torra WTW Growth - TTU Installation | Water | G110 | Gate 110 | 2022-06-11 | 2022-03-24 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503564 | 503564 | Brechin WwTW - Bio Filter Media Filter | Wastewater | G110 | Gate 110 | 2022-11-04 | 2022-11-29 | 2022_23_P08 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110503571 | 503571 | E1287 - Claredon Place Dunblane | Wastewater | G110 | Gate 110 | 2022-12-30 | 2023-03-24 | 2022_23_P09 | 2022_23_P12 | 2022_23_Q3 | 2022_23_Q4
G110503587 | 503587 | Argyll SCADA - Ardrishaig | Water | G110 | Gate 110 | 2022-07-31 | 2022-08-30 | 2022_23_P04 | 2022_23_P05 | 2022_23_Q2 | 2022_23_Q2
G110503594 | 503594 | E1050 Marchmont Road Warrender Park Road Edinburgh Recycled | Wastewater | G110 | Gate 110 | 2025-04-06 | 2024-10-16 | 2025_26_P01 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3
G110503595 | 503595 | Yarrowfues WTW main-out 2019 | Water | G110 | Gate 110 | 2022-12-28 | 2023-12-13 | 2022_23_P09 | 2023_24_P09 | 2022_23_Q3 | 2023_24_Q3
G110503628 | 503628 | SR21ES Herricks WTW upgrade | Water | G110 | Gate 110 | 2026-11-16 | 2025-10-29 | 2026_27_P08 | 2025_26_P07 | 2026_27_Q3 | 2025_26_Q3
G110503630 | 503630 | OMG06 Shortfall Project | Water | G110 | Gate 110 | 2022-10-19 | 2022-11-08 | 2022_23_P07 | 2022_23_P08 | 2022_23_Q3 | 2022_23_Q3
G110503631 | 503631 | Bradan WOA- WQ High Priority Customer Interventions | Water | G110 | Gate 110 | 2022-10-28 | 2022-12-23 | 2022_23_P07 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
G110503638 | 503638 | SR21 Carstairs Junction Overland Sewer | Wastewater | G110 | Gate 110 | 2024-12-16 | 2024-05-15 | 2024_25_P09 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1
G110503632 | 503632 | Bradan WQ Improvement Pennyburn Road DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2023-04-05 | 2023-02-28 | 2023_24_P01 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G110503613 | 503613 | SR21 ES Loch Calder WOA - Roster Occumster Mains Rehab | Water | G110 | Gate 110 | 2027-01-04 | 2025-06-11 | 2026_27_P10 | 2025_26_P03 | 2026_27_Q4 | 2025_26_Q1
G110503617 | 503617 | Tullich WOA Oban 12 Main Refurbishment -CWA- | Water | G110 | Gate 110 | 2022-12-16 | 2022-12-23 | 2022_23_P09 | 2022_23_P09 | 2022_23_Q3 | 2022_23_Q3
G110503543 | 503543 | Drongan WwTW Bathing Water Improvement | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-05-30 | 2022_23_P03 | 2022_23_P02 | 2022_23_Q1 | 2022_23_Q1
G110503545 | 503545 | Mauchline WwTW Bathing Water Improvement | Wastewater | G110 | Gate 110 | 2022-06-22 | 2022-03-29 | 2022_23_P03 | 2021_22_P12 | 2022_23_Q1 | 2021_22_Q4
G110503546 | 503546 | Belleisle Golf Course CSO Bathing Water Improvement | Wastewater | G110 | Gate 110 | 2022-06-22 | 2021-12-22 | 2022_23_P03 | 2021_22_P09 | 2022_23_Q1 | 2021_22_Q3
G110503678 | 503678 | SR21 ES Camps | Water | G110 | Gate 110 | 2024-10-12 | 2027-03-03 | 2024_25_P07 | 2026_27_P12 | 2024_25_Q3 | 2026_27_Q4
G110503680 | 503680 | Dunside Upper and Lower Risk Reduction | Water | G110 | Gate 110 | 2026-12-14 | 2026-03-18 | 2026_27_P09 | 2025_26_P12 | 2026_27_Q3 | 2025_26_Q4
G110503733 | 503733 | Aird a Mhachair - Benbecula DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2023-03-01 | 2022-03-31 | 2022_23_P12 | 2021_22_P12 | 2022_23_Q4 | 2021_22_Q4
G110503686 | 503686 | SR21 ES Munnoch Breach | Water | G110 | Gate 110 | 2024-05-27 | 2023-03-23 | 2024_25_P02 | 2022_23_P12 | 2024_25_Q1 | 2022_23_Q4
G110503714 | 503714 | SR21 ES North Third | Water | G110 | Gate 110 | 2024-12-12 | 2024-09-18 | 2024_25_P09 | 2024_25_P06 | 2024_25_Q3 | 2024_25_Q2
G110503716 | 503716 | SR21 ES Mill Glen Breach | Water | G110 | Gate 110 | 2023-01-29 | 2022-06-30 | 2022_23_P10 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1
G110503730 | 503730 | Stonebyres DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2024-07-22 | 2023-03-13 | 2024_25_P04 | 2022_23_P12 | 2024_25_Q2 | 2022_23_Q4
G110503731 | 503731 | Elsrickle DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2023-05-24 | 2023-02-28 | 2023_24_P02 | 2022_23_P11 | 2023_24_Q1 | 2022_23_Q4
G110503732 | 503732 | Portree - Braes DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2025-03-17 | 2024-06-26 | 2024_25_P12 | 2024_25_P03 | 2024_25_Q4 | 2024_25_Q1
G110503726 | 503726 | Neilston and Uplawmoor Rd - Neilston High DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2022-07-07 | 2022-03-30 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110503727 | 503727 | SR21 ES Alyth Loyal - Cothelhill DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2022-11-16 | 2022-03-31 | 2022_23_P08 | 2021_22_P12 | 2022_23_Q3 | 2021_22_Q4
G110503728 | 503728 | SR21 ES Edzell Rural DMA Mains Rehabilitation | Water | G110 | Gate 110 | 2022-03-31 | 2021-12-23 | 2021_22_P12 | 2021_22_P09 | 2021_22_Q4 | 2021_22_Q3
G110503701 | 503701 | Dalmarnock WwTW STW000222 - Asset Cleaning Project & Control of Odours | Wastewater | G110 | Gate 110 | 2022-02-12 | 2021-08-27 | 2021_22_P11 | 2021_22_P05 | 2021_22_Q4 | 2021_22_Q2
G110503761 | 503761 | SR21 Bonnycraig WTW Growth and Quality | Water | G110 | Gate 110 | 2024-03-20 | 2023-10-04 | 2023_24_P12 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G110503860 | 503860 | EFOS Crow Wood Terrace Chryston W1000 | Wastewater | G110 | Gate 110 | 2023-04-28 | 2023-01-31 | 2023_24_P01 | 2022_23_P10 | 2023_24_Q1 | 2022_23_Q4
G110504434 | 504434 | Bradan WTW - Top and Bottom Generator Install | Water | G110 | Gate 110 | 2022-08-19 | 2022-03-29 | 2022_23_P05 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110504465 | 504465 | Forehill WTW - Ferric Storage and delivery area | Water | G110 | Gate 110 | 2025-01-12 | 2025-01-22 | 2024_25_P10 | 2024_25_P10 | 2024_25_Q4 | 2024_25_Q4
G110505032 | 505032 | ICF - Grandholm, Aberdeen - Water Main Installation. | Water | G110 | Gate 110 | 2022-09-10 | 2022-10-31 | 2022_23_P06 | 2022_23_P07 | 2022_23_Q2 | 2022_23_Q3
G110504995 | 504995 | Loch Calder WTW - Treated Water Pumps | Water | G110 | Gate 110 | 2025-07-21 | 2024-11-27 | 2025_26_P04 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3
G110505053 | 505053 | EFOS - Sauchie Road Crieff - 0248 | Wastewater | G110 | Gate 110 | 2024-04-28 | 2023-09-06 | 2024_25_P01 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110505384 | 505384 | NRSWA Edinburgh Trams York Place to Newhaven | Water | G110 | Gate 110 | 2024-10-19 | 2024-05-15 | 2024_25_P07 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1
G110505447 | 505447 | RCI Bigton DMA Maywick Road | Water | G110 | Gate 110 | 2024-03-07 | 2023-03-31 | 2023_24_P12 | 2022_23_P12 | 2023_24_Q4 | 2022_23_Q4
G110505504 | 505504 | RCI High Dykes DMA (Auchincarroch Rd) | Water | G110 | Gate 110 | 2023-09-01 | 2023-10-18 | 2023_24_P06 | 2023_24_P07 | 2023_24_Q2 | 2023_24_Q3
G110505687 | 505687 | Rosewell WwTW - Interim Growth Solution SAF | Wastewater | G110 | Gate 110 | 2024-11-24 | 2024-05-15 | 2024_25_P08 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1
G110505693 | 505693 | RCI West Ballochy DMA (Hillside) | Water | G110 | Gate 110 | 2024-11-22 | 2024-02-21 | 2024_25_P08 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4
G110505641 | 505641 | Lochwinnoch WwTW - Inlet Screw Pumps Refurbishment - 500k | Wastewater | G110 | Gate 110 | 2023-09-10 | 2023-09-06 | 2023_24_P06 | 2023_24_P06 | 2023_24_Q2 | 2023_24_Q2
G110505927 | 505927 | RCI Hilliclay DMA (Stainland) | Water | G110 | Gate 110 | 2025-01-03 | 2024-04-17 | 2024_25_P10 | 2024_25_P01 | 2024_25_Q4 | 2024_25_Q1
G110505949 | 505949 | Skellyton WwTW SR10 Outstanding CM | Wastewater | G110 | Gate 110 | 2025-12-15 | 2025-10-29 | 2025_26_P09 | 2025_26_P07 | 2025_26_Q3 | 2025_26_Q3
G110506029 | 506029 | RCI Roskhill DMA and Dunvegan DMA Roag | Water | G110 | Gate 110 | 2025-03-16 | 2025-09-17 | 2024_25_P12 | 2025_26_P06 | 2024_25_Q4 | 2025_26_Q2
G110506032 | 506032 | RCI Broadford DMA and Breakish DMA Broadford | Water | G110 | Gate 110 | 2025-04-25 | 2025-01-22 | 2025_26_P01 | 2024_25_P10 | 2025_26_Q1 | 2024_25_Q4
G110506149 | 506149 | RCI Tankerness and Foubister DMA Tankerness | Water | G110 | Gate 110 | 2024-12-12 | 2024-10-30 | 2024_25_P09 | 2024_25_P07 | 2024_25_Q3 | 2024_25_Q3
G110506151 | 506151 | RCI West Line DMA Oust WSZ | Water | G110 | Gate 110 | 2025-08-21 | 2026-04-01 | 2025_26_P05 | 2026_27_P01 | 2025_26_Q2 | 2026_27_Q1
G110506234 | 506234 | RCI Luing DMA Cullipool | Water | G110 | Gate 110 | 2024-03-28 | 2023-02-24 | 2023_24_P12 | 2022_23_P11 | 2023_24_Q4 | 2022_23_Q4
G110506232 | 506232 | RCI Kinlochleven DMA | Water | G110 | Gate 110 | 2024-03-28 | 2023-06-14 | 2023_24_P12 | 2023_24_P03 | 2023_24_Q4 | 2023_24_Q1
G110506228 | 506228 | RCI Bowmore DMA (Torra Mains) | Water | G110 | Gate 110 | 2024-03-28 | 2023-09-20 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G110506231 | 506231 | RCI Eathie DMA (Muirhead Farm and Eathie Mains) | Water | G110 | Gate 110 | 2025-06-12 | 2024-12-11 | 2025_26_P03 | 2024_25_P09 | 2025_26_Q1 | 2024_25_Q3
G110506275 | 506275 | RCI Tore and Drumderfit DMA (Tore to Kessock) | Water | G110 | Gate 110 | 2024-10-17 | 2024-06-12 | 2024_25_P07 | 2024_25_P03 | 2024_25_Q3 | 2024_25_Q1
G110506271 | 506271 | RCI Bragar DMA (West Lewis WOA) | Water | G110 | Gate 110 | 2025-06-01 | 2025-02-19 | 2025_26_P03 | 2024_25_P11 | 2025_26_Q1 | 2024_25_Q4
G110506422 | 506422 | Business Management System | Support Services | G110 | Gate 110 | 2024-03-17 | 2023-09-06 | 2023_24_P12 | 2023_24_P06 | 2023_24_Q4 | 2023_24_Q2
G110506608 | 506608 | E-W-NI-140520-Craighead WTW - Upgrade Mn removal - Covid 19 - 66 | Water | G110 | Gate 110 | 2024-01-21 | 2023-10-18 | 2023_24_P10 | 2023_24_P07 | 2023_24_Q4 | 2023_24_Q3
G110506618 | 506618 | RCI Kinlochbervie DMA (Kinlochbervie WOA) | Water | G110 | Gate 110 | 2024-11-17 | 2025-02-05 | 2024_25_P08 | 2024_25_P11 | 2024_25_Q3 | 2024_25_Q4
G110506684 | 506684 | Repair at Glenhove DSR 2 | Water | G110 | Gate 110 | 2023-12-23 | 2023-08-09 | 2023_24_P09 | 2023_24_P05 | 2023_24_Q3 | 2023_24_Q2
G110506779 | 506779 | Stoneybridge WTW - Essential Capital Maintenance | Water | G110 | Gate 110 | 2024-10-14 | 2024-01-24 | 2024_25_P07 | 2023_24_P10 | 2024_25_Q3 | 2023_24_Q4
G110506864 | 506864 | ICF - Forres Strategic Water upgrade | Water | G110 | Gate 110 | 2023-11-30 | 2024-08-14 | 2023_24_P08 | 2024_25_P05 | 2023_24_Q3 | 2024_25_Q2
G110506865 | 506865 | ICF - Forres Strategic Wastewater upgrade | Wastewater | G110 | Gate 110 | 2023-11-30 | 2024-08-14 | 2023_24_P08 | 2024_25_P05 | 2023_24_Q3 | 2024_25_Q2
G110506896 | 506896 | Windows 10 Upgrade | Support Services | G110 | Gate 110 | 2022-07-01 | 2022-03-10 | 2022_23_P04 | 2021_22_P12 | 2022_23_Q2 | 2021_22_Q4
G110507057 | 507057 | RCI Catterthun DMA Craigton of Monikie | Water | G110 | Gate 110 | 2024-09-12 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G110507186 | 507186 | RCI Craigie DMA Plewlands | Water | G110 | Gate 110 | 2024-04-11 | 2023-03-28 | 2024_25_P01 | 2022_23_P12 | 2024_25_Q1 | 2022_23_Q4
G110507189 | 507189 | RCI Rossie DMA Ethie PMA | Water | G110 | Gate 110 | 2024-09-13 | 2024-03-20 | 2024_25_P06 | 2023_24_P12 | 2024_25_Q2 | 2023_24_Q4
G110507173 | 507173 | Oracle ULA Exit | Support Services | G110 | Gate 110 | 2022-05-03 | 2022-02-01 | 2022_23_P02 | 2021_22_P11 | 2022_23_Q1 | 2021_22_Q4
G110507455 | 507455 | ICF - Ellon - Bridge of Don Aberdeen Development Corridor - Balmedie to Blackdog Section Water | Water | G110 | Gate 110 | 2025-01-29 | 2024-06-26 | 2024_25_P10 | 2024_25_P03 | 2024_25_Q4 | 2024_25_Q1
G110507493 | 507493 | RCI SR21 ES Mains of Moyness - Non DMA Phase 2 | Water | G110 | Gate 110 | 2025-01-11 | 2024-02-07 | 2024_25_P10 | 2023_24_P11 | 2024_25_Q4 | 2023_24_Q4
G110507813 | 507813 | Simple Repair at Aberdeen Kirkhill DSR | Water | G110 | Gate 110 | 2023-01-24 | 2022-08-15 | 2022_23_P10 | 2022_23_P05 | 2022_23_Q4 | 2022_23_Q2
G110507860 | 507860 | Simple Repair at Rochomie DSR | Water | G110 | Gate 110 | 2023-02-13 | 2022-06-29 | 2022_23_P11 | 2022_23_P03 | 2022_23_Q4 | 2022_23_Q1
G110507808 | 507808 | Croy WwTW - Growth | Wastewater | G110 | Gate 110 | 2025-09-01 | 2024-11-25 | 2025_26_P06 | 2024_25_P08 | 2025_26_Q2 | 2024_25_Q3
G110507933 | 507933 | Catrineholm WwTW- Emergency Project to Maintain CAR Licence Compliance | Wastewater | G110 | Gate 110 | 2023-08-13 | 2023-11-15 | 2023_24_P05 | 2023_24_P08 | 2023_24_Q2 | 2023_24_Q3
G110508109 | 508109 | Microsoft Teams | Support Services | G110 | Gate 110 | 2022-02-12 | 2022-02-10 | 2021_22_P11 | 2021_22_P11 | 2021_22_Q4 | 2021_22_Q4
G110508601 | 508601 | SR15 Milnbe Weir Eel Pass PPD | Wastewater | G110 | Gate 110 | 2023-03-09 | 2022-11-29 | 2022_23_P12 | 2022_23_P08 | 2022_23_Q4 | 2022_23_Q3
G110508752 | 508752 | E-WW-NI-150920-PERTH CITY WWTW-IFAS | Wastewater | G110 | Gate 110 | 2025-02-02 | 2024-07-24 | 2024_25_P11 | 2024_25_P04 | 2024_25_Q4 | 2024_25_Q2
G110509283 | 509283 | Simple Repair at Peterhead Newfield DSR | Water | G110 | Gate 110 | 2023-03-05 | 2022-09-29 | 2022_23_P12 | 2022_23_P06 | 2022_23_Q4 | 2022_23_Q2
G110510392 | 510392 | Oban, Stevenson Street SPS - Replace Screw Pumps | Wastewater | G110 | Gate 110 | 2024-05-28 | 2023-10-18 | 2024_25_P02 | 2023_24_P07 | 2024_25_Q1 | 2023_24_Q3
G110510727 | 510727 | Infrastructure Tactical Project | Support Services | G110 | Gate 110 | 2023-04-03 | 2023-08-09 | 2023_24_P01 | 2023_24_P05 | 2023_24_Q1 | 2023_24_Q2
G110510931 | 510931 | Dores DMA - Mains Rehab | Water | G110 | Gate 110 | 2024-08-12 | 2023-08-23 | 2024_25_P05 | 2023_24_P05 | 2024_25_Q2 | 2023_24_Q2
G110511334 | 511334 | RCI Clachan DMA Longrigg | Water | G110 | Gate 110 | 2024-10-11 | 2023-10-18 | 2024_25_P07 | 2023_24_P07 | 2024_25_Q3 | 2023_24_Q3
G110511344 | 511344 | Field Service Transformation Project | Support Services | G110 | Gate 110 | 2025-01-16 | 2023-03-24 | 2024_25_P10 | 2022_23_P12 | 2024_25_Q4 | 2022_23_Q4
G110511495 | 511495 | SR21 Core WTW pilots - Chlorine Dioxide | Water | G110 | Gate 110 | 2025-04-17 | 2024-10-30 | 2025_26_P01 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3
G110511500 | 511500 | SR21 Core WTW pilots - Ozone GAC | Water | G110 | Gate 110 | 2024-09-21 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G110511704 | 511704 | RCI Comrie and Bogside DMA Righead Farm | Water | G110 | Gate 110 | 2024-09-30 | 2024-06-26 | 2024_25_P06 | 2024_25_P03 | 2024_25_Q2 | 2024_25_Q1
G110512469 | 512469 | SR21 Core WTW Pilots - Filter Columns | Water | G110 | Gate 110 | 2024-07-22 | 2024-04-03 | 2024_25_P04 | 2024_25_P01 | 2024_25_Q2 | 2024_25_Q1
G110512600 | 512600 | ICF - NIA0157 Glencorse WOA - Danderhall and Gilmerton DMAs - Solution 01 | Water | G110 | Gate 110 | 2024-05-20 | 2023-06-14 | 2024_25_P02 | 2023_24_P03 | 2024_25_Q1 | 2023_24_Q1
G110512639 | 512639 | Server and Storage Project | Support Services | G110 | Gate 110 | 2024-06-26 | 2023-11-15 | 2024_25_P03 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3
G110512749 | 512749 | RCI Benbecula DMA Ceann a Bunteag | Water | G110 | Gate 110 | 2024-08-26 | 2023-03-29 | 2024_25_P05 | 2022_23_P12 | 2024_25_Q2 | 2022_23_Q4
G110512711 | 512711 | WQ Mains Rehabilitation Ph1 Ma2b Patna DMA | Water | G110 | Gate 110 | 2024-06-06 | 2024-02-21 | 2024_25_P03 | 2023_24_P11 | 2024_25_Q1 | 2023_24_Q4
G110512815 | 512815 | RCI Garelochhead Shandon DMA Faslane Diversion | Water | G110 | Gate 110 | 2025-07-10 | 2025-01-22 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4
G110512940 | 512940 | RCI Bixter Tresta and Sandsound DMA Effirth | Water | G110 | Gate 110 | 2025-03-20 | 2025-04-02 | 2024_25_P12 | 2025_26_P01 | 2024_25_Q4 | 2025_26_Q1
G110512997 | 512997 | ICF - Nairn Water Main Upgrade - Galantray Element | Water | G110 | Gate 110 | 2025-05-01 | 2024-06-26 | 2025_26_P02 | 2024_25_P03 | 2025_26_Q1 | 2024_25_Q1
G110513208 | 513208 | SR21 Carron Valley WTW - Air Curtain | Water | G110 | Gate 110 | 2024-12-30 | 2024-06-26 | 2024_25_P09 | 2024_25_P03 | 2024_25_Q3 | 2024_25_Q1
G110513312 | 513312 | Hydro Nation Chair | CE&FS | G110 | Gate 110 | 2028-06-12 | 2027-09-15 | 2028_29_P03 | 2027_28_P06 | 2028_29_Q1 | 2027_28_Q2
G110513433 | 513433 | SR21 Glenfarg WTW - Air Curtain | Water | G110 | Gate 110 | 2024-11-24 | 2024-04-03 | 2024_25_P08 | 2024_25_P01 | 2024_25_Q3 | 2024_25_Q1
G110513461 | 513461 | Inverness Laboratory Extension | Support Services | G110 | Gate 110 | 2023-05-18 | 2023-08-23 | 2023_24_P02 | 2023_24_P05 | 2023_24_Q1 | 2023_24_Q2
G110513826 | 513826 | RCI Newfield PS To Broadmuir TM DMA Hatton Hotspot | Water | G110 | Gate 110 | 2025-02-09 | 2024-09-18 | 2024_25_P11 | 2024_25_P06 | 2024_25_Q4 | 2024_25_Q2
G110513832 | 513832 | Non-Complex Service Delivery (NCSD) Phase 3 | Support Services | G110 | Gate 110 | 2022-12-26 | 2022-06-30 | 2022_23_P09 | 2022_23_P03 | 2022_23_Q3 | 2022_23_Q1
G110513923 | 513923 | Black Isle Trunk Main - Valve Replacement | Water | G110 | Gate 110 | 2024-03-28 | 2025-04-02 | 2023_24_P12 | 2025_26_P01 | 2023_24_Q4 | 2025_26_Q1
G110514041 | 514041 | C-WW-NI-Management of Wastewater Temporary Process Units - Aberuthven STW | Wastewater | G110 | Gate 110 | 2025-09-08 | 2025-01-22 | 2025_26_P06 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4
G110514047 | 514047 | RCI Stornoway Point DMA Bayble | Water | G110 | Gate 110 | 2025-10-09 | 2025-07-23 | 2025_26_P07 | 2025_26_P04 | 2025_26_Q3 | 2025_26_Q2
G110514080 | 514080 | RCI Dolphinton Line DMA | Water | G110 | Gate 110 | 2025-08-24 | 2025-03-05 | 2025_26_P05 | 2024_25_P12 | 2025_26_Q2 | 2024_25_Q4
G110514217 | 514217 | E-WW-NI-140721-Inverurie Old STW Redundant Assets Demo | Wastewater | G110 | Gate 110 | 2024-04-13 | 2023-09-20 | 2024_25_P01 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110514441 | 514441 | Digital Securing Operational Assets | Support Services | G110 | Gate 110 | 2024-10-06 | 2024-02-21 | 2024_25_P07 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4
G110514448 | 514448 | EFOS - Main Street Bridge of Weir - 281-1 | Wastewater | G110 | Gate 110 | 2025-08-01 | 2024-04-17 | 2025_26_P05 | 2024_25_P01 | 2025_26_Q2 | 2024_25_Q1
G110514598 | 514598 | Networks Refresh Project | Support Services | G110 | Gate 110 | 2024-06-20 | 2023-11-15 | 2024_25_P03 | 2023_24_P08 | 2024_25_Q1 | 2023_24_Q3
G110514631 | 514631 | E-WWNI-050821-Kirkcaldy STW-Renew media in 1st stage biopur (BAFF) process | Wastewater | G110 | Gate 110 | 2024-08-04 | 2024-02-21 | 2024_25_P05 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4
G110515139 | 515139 | Dirty Dam - Silt removal | Water | G110 | Gate 110 | 2024-12-02 | 2024-04-17 | 2024_25_P09 | 2024_25_P01 | 2024_25_Q3 | 2024_25_Q1
G110515505 | 515505 | SR21 Eela WTW Interim Measures | Water | G110 | Gate 110 | 2023-07-16 | 2024-04-03 | 2023_24_P04 | 2024_25_P01 | 2023_24_Q2 | 2024_25_Q1
G110515607 | 515607 | C-WW-NI-MCC Replacement – Pitmedden STW | Wastewater | G110 | Gate 110 | 2025-07-03 | 2025-01-22 | 2025_26_P04 | 2024_25_P10 | 2025_26_Q2 | 2024_25_Q4
G110515625 | 515625 | rDWD Implementation - Juniper House | Support Services | G110 | Gate 110 | 2024-01-28 | 2023-03-08 | 2023_24_P10 | 2022_23_P12 | 2023_24_Q4 | 2022_23_Q4
G110516045 | 516045 | TWS Tiree WTW CWBT Replacement | Water | G110 | Gate 110 | 2025-07-14 | 2024-02-21 | 2025_26_P04 | 2023_24_P11 | 2025_26_Q2 | 2023_24_Q4
G110516085 | 516085 | Milngavie WTW - replace hypo bulk tank 2 | Water | G110 | Gate 110 | 2025-12-07 | 2025-04-02 | 2025_26_P09 | 2025_26_P01 | 2025_26_Q3 | 2025_26_Q1
G110516502 | 516502 | SR21 Black Esk WTW - Manganese Monitors | Water | G110 | Gate 110 | 2023-09-24 | 2023-08-09 | 2023_24_P06 | 2023_24_P05 | 2023_24_Q2 | 2023_24_Q2
G110516659 | 516659 | Greater Glasgow Bioresource Treatment Project | Wastewater | G110 | Gate 110 | 2024-07-06 | 2023-10-09 | 2024_25_P04 | 2023_24_P07 | 2024_25_Q2 | 2023_24_Q3
G110517533 | 517533 | SR21 Islay Flow Gauging | Water | G110 | Gate 110 | 2026-06-13 | 2025-10-15 | 2026_27_P03 | 2025_26_P07 | 2026_27_Q1 | 2025_26_Q3
G110518244 | 518244 | Shieldhall WWTW - PST Maintenance Bays - Replacement | Wastewater | G110 | Gate 110 | 2025-09-26 | 2025-04-02 | 2025_26_P06 | 2025_26_P01 | 2025_26_Q2 | 2025_26_Q1
G110518444 | 518444 | Orkney Sludge Trial Enabling Works | Water | G110 | Gate 110 | 2024-07-14 | 2024-02-07 | 2024_25_P04 | 2023_24_P11 | 2024_25_Q2 | 2023_24_Q4
G110518591 | 518591 | Cults Pitfodels TWP - Replace MCC | Water | G110 | Gate 110 | 2026-04-06 | 2025-08-06 | 2026_27_P01 | 2025_26_P05 | 2026_27_Q1 | 2025_26_Q2
G110518579 | 518579 | Shieldhall WWTW - cleaning of Inlet Delta Storm Bypass Culvert and Velocity Channels at Pre-Sed Bldng | Wastewater | G110 | Gate 110 | 2024-10-22 | 2024-05-01 | 2024_25_P07 | 2024_25_P02 | 2024_25_Q3 | 2024_25_Q1
G110520228 | 520228 | NCSD Need4621 Loch Turret investigation overpumping drought periods | Water | G110 | Gate 110 | 2025-04-27 | 2024-08-21 | 2025_26_P01 | 2024_25_P05 | 2025_26_Q1 | 2024_25_Q2
G110520229 | 520229 | Non Complex Service Delivery (NCSD) Phase 3 Implementation | Support Services | G110 | Gate 110 | 2024-05-20 | 2023-09-20 | 2024_25_P02 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110520459 | 520459 | Apex Applications Replacement | Support Services | G110 | Gate 110 | 2024-05-26 | 2023-09-20 | 2024_25_P02 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110520500 | 520500 | E-WW-NI-070422-Banchory STW Chemical Dosing | Wastewater | G110 | Gate 110 | 2025-06-16 | 2024-10-02 | 2025_26_P03 | 2024_25_P07 | 2025_26_Q1 | 2024_25_Q3
G110520606 | 520606 | RCI Colmonell DMA | Water | G110 | Gate 110 | 2025-03-23 | 2024-01-10 | 2024_25_P12 | 2023_24_P10 | 2024_25_Q4 | 2023_24_Q4
G110520761 | 520761 | Field Connectivity Project | Support Services | G110 | Gate 110 | 2024-08-22 | 2023-12-13 | 2024_25_P05 | 2023_24_P09 | 2024_25_Q2 | 2023_24_Q3
G110522707 | 522707 | Redcraigs DSR - Rationalisation | Water | G110 | Gate 110 | 2024-10-31 | 2024-02-21 | 2024_25_P07 | 2023_24_P11 | 2024_25_Q3 | 2023_24_Q4
G110523508 | 523508 | Powfoot SEP - Refurbish Reed Beds | Wastewater | G110 | Gate 110 | 2025-01-20 | 2024-04-17 | 2024_25_P10 | 2024_25_P01 | 2024_25_Q4 | 2024_25_Q1
G110524913 | 524913 | SW Reporting Redefined | Support Services | G110 | Gate 110 | 2024-07-25 | 2023-11-29 | 2024_25_P04 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3
G110524914 | 524914 | Open Data | Support Services | G110 | Gate 110 | 2024-07-25 | 2023-11-17 | 2024_25_P04 | 2023_24_P08 | 2024_25_Q2 | 2023_24_Q3
G110525189 | 525189 | Saltcoats Stormflow WWPS Rising Main Replacement - Emergency Works | Wastewater | G110 | Gate 110 | 2025-01-31 | 2025-02-05 | 2024_25_P10 | 2024_25_P11 | 2024_25_Q4 | 2024_25_Q4
G110527220 | 527220 | SIP Yr 3 OKR Delivery | Support Services | G110 | Gate 110 | 2024-04-22 | 2023-09-27 | 2024_25_P01 | 2023_24_P06 | 2024_25_Q1 | 2023_24_Q2
G110528868 | 528868 | WQ Carron Valley WOA Discolouration Management Plan Delivery | Water | G110 | Gate 110 | 2026-12-07 | 2026-06-24 | 2026_27_P09 | 2026_27_P03 | 2026_27_Q3 | 2026_27_Q1

## G5
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G5: Growth
|  |  |  | Actual and Forecast | [5 empty] | Confidence Grades
Line | Description | Units | Field | Report Year -1 | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year | Report Year -1 | Report Year | Forecast Year | Forecast Year | Forecast Year | Forecast Year
Ref. |  |  | Type
|  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27
Growth expenditure (gross)
G5.1 | Expenditure for Reasonable Cost Contributions - household - water | £m | I | 9.8776 | 10.1082 | 6.6569 | 5.4454 | 8.3883 | 8.4514 | A1 | A1 | A1 | A1 | A1 | A1
G5.2 | Expenditure for Reasonable Cost Contributions - non-household - water | £m | I | -0.047478 | -0.12103 | 0.14124 | 2.4e-07 | 2.4e-07 | 2.2e-07 | A1 | A1 | A1 | A1 | A1 | A1
G5.3 | Total expenditure on Reasonable Cost Contributions - water | £m | C | 9.8301 | 9.9872 | 6.7982 | 5.4454 | 8.3883 | 8.4514
G5.4 | Expenditure for Reasonable Cost Contributions - household - wastewater | £m | I | 14.7358 | 22.6901 | 17.7324 | 10.6697 | 10.1626 | 8.8375 | A1 | A1 | A1 | A1 | A1 | A1
G5.5 | Expenditure for Reasonable Cost Contributions - non-household - wastewater | £m | I | -0.0018045 | -0.0018652 | 0.049214 | 4.8e-07 | 4.8e-07 | 4.4e-07 | A1 | A1 | A1 | A1 | A1 | A1
G5.6 | Total expenditure on Reasonable Cost Contributions - wastewater | £m | C | 14.734 | 22.6883 | 17.7816 | 10.6697 | 10.1626 | 8.8375
G5.7 | Total expenditure on Reasonable Cost Contributions - water and wastewater | £m | C | 24.5642 | 32.6754 | 24.5798 | 16.1151 | 18.5509 | 17.289
G5.8 | Expenditure on Part 3 Strategic Capacity - water | £m | I | 9.6267 | 15.6715 | 20.0574 | 10.541 | 22.3565 | 6.1076 | A1 | A1 | A1 | A1 | A1 | A1
G5.9 | Expenditure on Part 3 Strategic Capacity - wastewater | £m | I | 2.438 | 5.0625 | 13.048 | 35.9386 | 31.3194 | 7.3522 | A1 | A1 | A1 | A1 | A1 | A1
G5.10 | Total expenditure on Part 3 Strategic Capacity - water and wastewater | £m | C | 12.0647 | 20.734 | 33.1054 | 46.4796 | 53.6758 | 13.4598
G5.11 | Expenditure on Part 4 assets - water | £m | I | 4.2073 | 2.6764 | 2.5602 | 0.81624 | 4.8374 | 3.3885 | A1 | A1 | A1 | A1 | A1 | A1
G5.12 | Expenditure on Part 4 assets - wastewater | £m | I | 36.4602 | 48.0964 | 52.5194 | 98.2099 | 67.6158 | 58.9794 | A1 | A1 | A1 | A1 | A1 | A1
G5.13 | Total expenditure on Part 4 assets - water and wastewater | £m | C | 40.6675 | 50.7727 | 55.0796 | 99.0262 | 72.4532 | 62.3679
G5.14 | Total gross expenditure on growth - (RCC + Part 3 strategic capacity + Part 4) | £m | C | 77.2964 | 104.1822 | 112.7648 | 161.6209 | 144.6799 | 93.1167
Service Relocations
G5.15 | Service Relocations Water | £m | I | 3.5084 | 3.3781 | 2.5819 | 4.9078 | 1.4384 | 1.5234 | A1 | A1 | A1 | A1 | A1 | A1
G5.16 | Service Relocations Wastewater | £m | I | 0.77394 | 0.33532 | 0.92051 | 2.8753 | 0.67854 | 0.67854 | A1 | A1 | A1 | A1 | A1 | A1
G5.17 | Service Relocations Water Contributions | £m | I | -6.745 | -3.0716 | -5.3403 | -5.3403 | -5.3403 | -5.3403 | A1 | A1 | B1 | B1 | B1 | B1
G5.18 | Service Relocations Wastewater Contributions | £m | I | -3.4747 | -0.30379 | -2.0555 | -2.0555 | -2.0555 | -2.0555 | A1 | A1 | B1 | B1 | B1 | B1
G5.19 | Net Service Relocations | £m | C | -5.9373 | 0.33796 | -3.8933 | 0.38739 | -5.2788 | -5.1938
Gross Growth expenditure
G5.19a | Total gross expenditure on growth and service relocations | £m | C | 71.359 | 104.5202 | 108.8714 | 162.0083 | 139.401 | 87.9228
G5.19b | Total gross expenditure on growth and service relocations (excluding reasonable cost contributions) | £m | C | 46.7948 | 71.8447 | 84.2917 | 145.8931 | 120.8502 | 70.6339
Growth income (Infrastructure charge)
G5.20 | Water household infrastructure charge income | £m | I | 9.7321 | 9.6722 | 9.4071 | 9.4917 | 9.5772 | 9.6634 | A1 | A1 | A1 | A1 | A1 | A1
G5.21 | Water non-household infrastructure charge income | £m | I | 0.23477 | 0.23807 | 0.17617 | 0.17775 | 0.17935 | 0.18097 | A1 | A1 | A1 | A1 | A1 | A1
G5.22 | Wastewater household infrastructure charge income | £m | I | 9.0469 | 9.488 | 8.9367 | 9.0171 | 9.0983 | 9.1802 | A1 | A1 | A1 | A1 | A1 | A1
G5.23 | Wastewater non-household infrastructure charge income | £m | I | 0.017365 | 0.011622 | 0.050029 | 0.050479 | 0.050933 | 0.051391 | A1 | A1 | A1 | A1 | A1 | A1
G5.24 | Total infrastructure charge income | £m | C | 19.0311 | 19.4098 | 18.57 | 18.7371 | 18.9057 | 19.0759
Growth expenditure (net of income)
G5.25 | Total net growth expenditure | £m | C | 52.3279 | 85.1103 | 90.3014 | 143.2711 | 120.4953 | 68.8469
G5.26 | Total net growth expenditure (excluding reasonable cost contributions) | £m | C | 27.7637 | 52.4349 | 65.7217 | 127.156 | 101.9444 | 51.558
Growth - properties and populations
G5.27 | Number of new household properties connected to the water network | Nr | I | 23172 | 22620 | 22397.782 | 22599.362 | 22802.7563 | 23007.9811 | A1 | A1 | A1 | A1 | A1 | A1
G5.28 | Number of new non-household properties connected to the water network | Nr | I | 559 | 27 | 419.4494 | 423.2244 | 427.0334 | 430.8767 | A1 | A1 | A1 | A1 | A1 | A1
G5.29 | Total number of new properties connected to the water network | Nr | C | 23731 | 22647 | 22817.2314 | 23022.5865 | 23229.7897 | 23438.8578
G5.30 | Number of new household properties connected to the wastewater network | Nr | I | 21540 | 21164 | 21277.8929 | 21469.3939 | 21662.6185 | 21857.582 | A1 | A1 | A1 | A1 | A1 | A1
G5.31 | Number of new non-household properties connected to the wastewater network | Nr | I | 41 | 544 | 119.1155 | 120.1875 | 121.2692 | 122.3606 | A1 | A1 | A1 | A1 | A1 | A1
G5.32 | Total number of new properties connected to the wastewater network | Nr | C | 21581 | 21708 | 21397.0084 | 21589.5815 | 21783.8877 | 21979.9427
G5.33 | Number of new household properties receiving reasonable cost contributions - water | Nr | I | 28296 | 28675 | 27077.7135 | 27321.4129 | 27567.3056 | 27815.4114 | A1 | A1 | A1 | A1 | A1 | A1
G5.34 | Number of new non-household properties receiving reasonable cost contributions - water | Nr | I | 12 | -343 | 507.0917 | 511.6556 | 516.2605 | 520.9068 | A1 | A1 | A1 | A1 | A1 | A1
G5.35 | Total number of properties receiving reasonable cost contributions - water Part 2 | Nr | C | 28308 | 28332 | 27584.8052 | 27833.0685 | 28083.5661 | 28336.3182
G5.36 | Number of new household properties receiving reasonable cost contributions - wastewater | Nr | I | 14580 | 28418 | 8870.893 | 8950.731 | 9031.2876 | 9112.5692 | A1 | A1 | A1 | A1 | A1 | A1
G5.37 | Number of new non-household properties receiving reasonable cost contributions - wastewater | Nr | I | 95 | -2 | 49.66 | 50.107 | 50.5579 | 51.0129 | A1 | A1 | A1 | A1 | A1 | A1
G5.38 | Total number of properties receiving reasonable cost contributions - wastewater Part 2 | Nr | C | 14675 | 28416 | 8920.553 | 9000.838 | 9081.8455 | 9163.5821
G5.39 | Number of household property infrastructure charge payments - water | Nr | I | 23172 | 22620 | 22397.782 | 22599.362 | 22802.7563 | 23007.9811 | A1 | A1 | A1 | A1 | A1 | A1
G5.40 | Number of non-household property infrastructure charge payments - water | Nr | I | 559 | 27 | 419.4494 | 423.2244 | 427.0334 | 430.8767 | A1 | A1 | A1 | A1 | A1 | A1
G5.41 | Total number of infrastructure charge payments - water | Nr | C | 23731 | 22647 | 22817.2314 | 23022.5865 | 23229.7897 | 23438.8578
G5.42 | Number of household property infrastructure charge payments - wastewater | Nr | I | 21540 | 21164 | 21277.8929 | 21469.3939 | 21662.6185 | 21857.582 | A1 | A1 | A1 | A1 | A1 | A1
G5.43 | Number of non-household property infrastructure charge payments - wastewater | Nr | I | 41 | 544 | 119.1155 | 120.1875 | 121.2692 | 122.3606 | A1 | A1 | A1 | A1 | A1 | A1
G5.44 | Total number of property infrastructure charge - wastewater | Nr | C | 21581 | 21708 | 21397.0084 | 21589.5815 | 21783.8877 | 21979.9427
G5.45 | Additional population equivalent served from new Part 4 investment - water | Pe | I | 884 | 884 | 884 | 884 | 884 | 884 | B1 | B1 | B1 | B1 | B1 | B1
G5.46 | Additional population equivalent served from new Part 4 investment - wastewater | Pe | I | 3699 | 21787.11 | 133865.28 | 156969.28 | 162922.28 | 173457.28 | B1 | B1 | B1 | B1 | B1 | B1
Prepared by: …………………………………….………………………………..
Checked by: …………………………….…………………………………………..
Authorised by: |  |  | Date:

## G7
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G7: Repair, Refurbishment and Asset Replacement - Disaggregation by Management Approach
Line Ref. | Description | Units | Field Type | Management Approaches included within the Group | Actual Year 2017-18 | Actual Year 2018-19 | Actual Year 2019-20 | Actual Year 2020-21 | Actual year 2021-22 | Actual year 2022-23 | Forecast year 2023-24 | Forecast year 2024-25 | Forecast year 2025-26 | Forecast year 2026-27 | Total for SR21-27
|  |  |  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
CPI inflation assumption
G7.001 | Cost inflation (RPI until 2021 and CPI from 2021/22; financial year average) | % | I |  |  | 3.06% | 2.588% | 1.213% | 3.98% | 10.06% | 5.5% | 1.3% | 0.6% | 1.5%
G7.002 | Inflation index (2017/18 base year) | Nr. | I/C |  | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1127 | 1.2246 | 1.292 | 1.3088 | 1.3166 | 1.3364
| Management Approach Group 1 (Projected Outturn Prices) |  |  | Bioresource
G7.003 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA024 |  |  |  |  | 3.8944 | 4.2862 | 4.5219 | 4.5807 | 4.6082 | 4.6773 | 26.5688
G7.004 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.005 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 4.8217 | 5.3067 | 5.5986 | 5.6714 | 5.7054 | 5.791 | 32.8947
G7.006 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.87161 | 3.3216 | 1.8027 | 3.9893 | 1.5407 | 0 | 11.5259
G7.007 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.2132 | 0.41584 | 1.778 | 1.6748 | 1.824 | 1.2759 | 7.1817
G7.008 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 3.0384 | 4.3599 | 4.1866 | 0.69678 | 0.9151 | 0.94412 | 14.1409
| Management Approach Group 2 (Projected Outturn Prices) |  |  | common Asset groups
G7.009 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA011, MA013, MA018, MA022, MA044, MA068, MA082, MA089, MA091, MA092, MA096, MA105 |  |  |  |  | 30.2326 | 33.274 | 35.104 | 35.5604 | 35.7737 | 36.3103 | 206.255
G7.010 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.011 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 60.4896 | 66.5748 | 70.2364 | 71.1495 | 71.5764 | 72.65 | 412.6767
G7.012 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 25.1498 | 33.8068 | 34.2996 | 42.043 | 34.2607 | 42.9534 | 212.5134
G7.013 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 3.9395 | 5.3329 | 9.6665 | 8.6511 | 17.6516 | 12.2466 | 57.4882
G7.014 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 14.9364 | 16.961 | 32.3118 | 74.3628 | 87.8729 | 97.3893 | 323.8342
| Management Approach Group 3 (Projected Outturn Prices) |  |  | Customer & Community
G7.015 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.016 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.017 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.018 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.019 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.020 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 4 (Projected Outturn Prices) |  |  | Environmental improvement
G7.021 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA005, MA076, MA084, MA085 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.022 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.023 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.024 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.025 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.00011763 | -0.0045747 | 0.0045747 | 0 | 0 | 0 | 0.00011761
G7.026 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.06348 | 0.010725 | 0 | 0 | 0 | 0 | 0.074205
| Management Approach Group 5 (Projected Outturn Prices) |  |  | Flourishing Scotland
G7.027 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA048, MA102, MA103, MA110 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.028 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.029 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.030 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.031 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.032 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 6 (Projected Outturn Prices) |  |  | Managing Flood Risk
G7.033 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA020 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.034 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.035 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.036 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 1.6862 | 2.2721 | 2.3788 | 2.5423 | 8.8794
G7.037 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.038 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 7 (Projected Outturn Prices) |  |  | Net Zero
G7.039 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA027, MA056, MA077, MA101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.040 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.041 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 1.5746 | 1.733 | 1.8283 | 1.8521 | 1.8632 | 1.8911 | 10.7424
G7.042 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.0070051 | 0 | 0 | 0 | 0 | 0 | 0.0070051
G7.043 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | -0.0013044 | 0 | 0 | 0 | 0 | 0 | -0.0013044
G7.044 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.844 | 0.96974 | 3.9041 | 1.7989 | 0.11817 | 0.0020156 | 7.6369
| Management Approach Group 8 (Projected Outturn Prices) |  |  | Other Services
G7.045 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | _MA_proj_app_SS, _MA_proj_app_W, MA029, MA034, MA048, MA053, MA054, MA066, MA071 |  |  |  |  | 0.18545 | 0.2041 | 0.21533 | 0.21813 | 0.21944 | 0.22273 | 1.2652
G7.046 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.047 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 72.9341 | 80.2713 | 84.6862 | 85.7871 | 86.3018 | 87.5963 | 497.5768
G7.048 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.033889 | 0.0022805 | 0.012904 | 0.011096 | 4.9741 | 10.086 | 15.1203
G7.049 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 7.2791 | 10.3903 | 9.2044 | 15.4209 | 10.7847 | 9.2179 | 62.2974
G7.050 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 37.6321 | 64.3459 | 96.1565 | 107.5748 | 61.0805 | 35.933 | 402.7229
| Management Approach Group 9 (Projected Outturn Prices) |  |  | Overheads
G7.051 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | SR21_Prog_Over |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.052 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.053 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.054 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 6.7062e-05 | 0 | 0 | 0 | 0 | 0 | 6.7062e-05
G7.055 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | -1.1466 | 1.4566 | -0.15717 | -0.20534 | 0 | 0 | -0.052484
G7.056 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.4962 | 0.30388 | 2.5446 | 1.2665 | 2.334 | 0.95883 | 7.9039
| Management Approach Group 10 (Projected Outturn Prices) |  |  | PFI
G7.057 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.058 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.059 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.060 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0.73706 | 1.158 | 2.674 | 2.7141 | 7.2831
G7.061 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.062 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 11 (Projected Outturn Prices) |  |  | RCC
G7.063 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | RCC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.064 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.065 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.066 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.067 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.068 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 12 (Projected Outturn Prices) |  |  | Resilience & Growth
G7.069 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA026, MA032, MA065, MA084, MA087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.070 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.071 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 4.0137 | 4.4175 | 4.6604 | 4.721 | 4.7493 | 4.8206 | 27.3825
G7.072 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0.02 | 0 | 0 | 0 | 0.02
G7.073 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.074 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.36941 | 0.59589 | 2.3304 | 9.7385 | 14.5154 | 16.4066 | 43.9563
| Management Approach Group 13 (Projected Outturn Prices) |  |  | sludge treatment
G7.075 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.076 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.077 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.078 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.079 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.080 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 14 (Projected Outturn Prices) |  |  | SR15
G7.081 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, SR15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.082 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.083 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.084 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.085 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.086 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management Approach Group 15 (Projected Outturn Prices) |  |  | Transformation
G7.087 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA066, MA104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.088 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.089 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 60.0757 | 66.1193 | 69.7559 | 70.6627 | 71.0867 | 72.153 | 409.8532
G7.090 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.091 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.092 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 20.3519 | 42.8859 | 51.9529 | 57.3728 | 71.9291 | 244.4925
| Management approach group 16 (Projected outturn prices) |  |  | Water Quality
G7.093 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA006, MA016, MA028, MA033, MA037, MA046, MA052, MA081, MA093, MA094, MA095, MA100, MA106 |  |  |  |  | 50.5442 | 55.629 | 58.6885 | 59.4515 | 59.8082 | 60.7053 | 344.8267
G7.094 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.095 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 72.2022 | 79.4657 | 83.8363 | 84.9262 | 85.4358 | 86.7173 | 492.5836
G7.096 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 19.1319 | 20.5311 | 30.8796 | 30.7636 | 40.7079 | 51.5881 | 193.6022
G7.097 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 25.3457 | 41.3916 | 37.9812 | 28.8776 | 12.4806 | 6.7174 | 152.7941
G7.098 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 67.6579 | 54.7247 | 67.7372 | 71.2698 | 75.6415 | 75.862 | 412.8931
| Management approach group 17 (Projected outturn prices) |  |  | Water Quality (lead)
G7.099 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.100 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.101 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0.23156 | 0.25485 | 0.26887 | 0.27237 | 0.274 | 0.27811 | 1.5798
G7.102 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0 | 0 | 0.12812 | 1.5619 | 2.5271 | 3.5902 | 7.8073
G7.103 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.104 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Management approach group 18 (Projected outturn prices) |  |  | water resources
G7.105 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA063 |  |  |  |  | 0.18545 | 0.2041 | 0.21533 | 0.21813 | 0.21944 | 0.22273 | 1.2652
G7.106 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.107 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 0.31472 | 0.34638 | 0.36543 | 0.37018 | 0.3724 | 0.37799 | 2.1471
G7.108 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 0.18326 | 0.055394 | 0.22308 | 0.26602 | 0.26843 | 0.27206 | 1.2682
G7.109 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 0.00095652 | 0.075912 | 0.13107 | 0.01 | 0 | 0 | 0.21794
G7.110 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 0.35387 | 0.46865 | 0.77497 | 0.95956 | 1.1359 | 1.4329 | 5.1259
| Management approach group 19 (Projected outturn prices) |  |  | Water Supply
G7.111 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA001, MA004, MA015, MA025, MA058, MA060, MA070, MA073, MA074, MA080, MA098, MA099 |  |  |  |  | 42.8979 | 47.2134 | 49.8102 | 50.4577 | 50.7605 | 51.5219 | 292.6615
G7.112 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.113 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 152.674 | 168.033 | 177.2748 | 179.5793 | 180.6568 | 183.3667 | 1041.5845
G7.114 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 53.7598 | 59.4247 | 55.3739 | 72.9363 | 93.0071 | 100.7942 | 435.2959
G7.115 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 17.3796 | 30.1241 | 39.5972 | 26.0288 | 21.3472 | 10.5592 | 145.036
G7.116 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 39.6712 | 57.4011 | 82.7938 | 108.1 | 60.8867 | 62.7763 | 411.629
| Management approach group 20 (Projected outturn prices) |  |  | WW Collection
G7.117 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | IR 18, MA002, MA003, MA012, MA014, MA023, MA039, MA062, MA107 |  |  |  |  | 33.0618 | 36.3878 | 38.3891 | 38.8881 | 39.1215 | 39.7083 | 225.5565
G7.118 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.119 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 64.4922 | 70.9801 | 74.884 | 75.8575 | 76.3127 | 77.4573 | 439.9839
G7.120 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 34.8923 | 40.9798 | 40.8165 | 38.2562 | 48.65 | 54.7951 | 258.3899
G7.121 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 21.6973 | 19.1785 | 22.644 | 24.5389 | 9.1964 | 4.1901 | 101.4452
G7.122 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 17.8505 | 17.4195 | 29.7231 | 43.5227 | 51.9921 | 52.857 | 213.3649
| Management approach group 21 (Projected outturn prices) |  |  | WW Treatment
G7.123 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | Text; £m | I/C | MA017, MA021, MA035, MA036, MA042, MA043, MA049, MA057 |  |  |  |  | 19.3829 | 21.3328 | 22.5061 | 22.7987 | 22.9355 | 23.2795 | 132.2355
G7.124 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | Text; £m | I/C |  |  | 11: 0
G7.125 | Projected expenditure for Tier 2 replacement from the original management approaches | Text; £m | I/C | [5 empty] | 70.6123 | 77.7159 | 81.9902 | 83.0561 | 83.5544 | 84.8078 | 481.7367
G7.126 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | Text; £m | I/C | [5 empty] | 18.6097 | 34.7841 | 25.9795 | 15.3531 | 17.9426 | 25.0128 | 137.6818
G7.127 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | Text; £m | I/C | [5 empty] | 10.3919 | 14.7504 | 16.3012 | 12.0226 | 12.4182 | 9.6765 | 75.5608
G7.128 | Latest forecast expenditure for Tier 2 replacement | Text; £m | I/C | [5 empty] | 40.787 | 43.6954 | 53.5672 | 52.3469 | 46.0046 | 58.8082 | 295.2093
Totals Across All Management Approaches (Projected Outturn Prices)
G7.129 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | £m | C | [5 empty] | 180.3846 | 198.5313 | 209.4505 | 212.1734 | 213.4464 | 216.6481 | 1230.6345
G7.130 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.131 | Projected expenditure for Tier 2 replacement from the original management approaches | £m | C | [5 empty] | 564.4362 | 621.2185 | 655.3855 | 663.9055 | 667.8889 | 677.9073 | 3850.7418
G7.132 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | £m | C | [5 empty] | 152.6393 | 192.9057 | 191.9593 | 208.6106 | 248.9314 | 294.3482 | 1289.3946
G7.133 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | £m | C | [5 empty] | 85.0994 | 123.1116 | 137.151 | 117.0193 | 85.7028 | 53.8835 | 601.9677
G7.134 | Latest forecast expenditure for Tier 2 replacement | £m | C | [5 empty] | 223.7004 | 281.6083 | 418.9162 | 523.5901 | 459.8696 | 475.2994 | 2382.984
Totals Across All Management Approaches (2017/18 prices; CPI based)
G7.135 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 1; responsive) | £m | C | [5 empty] | 162.1158 | 178.4247 | 188.2381 | 190.6852 | 191.8293 | 194.7067 | 1105.9997
G7.136 | Projected expenditure for repair, refurbishment and inspections from the original management approaches (Tier 2; planned) | £m | C | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
G7.137 | Projected expenditure for Tier 2 replacement from the original management approaches | £m | C | [5 empty] | 507.2719 | 558.3034 | 589.0101 | 596.6672 | 600.2472 | 609.251 | 3460.7509
G7.138 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 1; responsive) | £m | C | [5 empty] | 137.1805 | 173.3689 | 172.5183 | 187.4832 | 223.7204 | 264.5376 | 1158.8088
G7.139 | Latest forecast expenditure for repair, refurbishment and inspections (Tier 2; planned) | £m | C | [5 empty] | 76.4808 | 110.6433 | 123.2607 | 105.168 | 77.0231 | 48.4264 | 541.0023
G7.140 | Latest forecast expenditure for Tier 2 replacement | £m | C | [5 empty] | 201.0447 | 253.0879 | 376.4897 | 470.5626 | 413.2954 | 427.1626 | 2141.643
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: |  |  | Date:

## G8
SCOTTISH WATER
ANNUAL RETURN INFORMATION REQUIREMENTS 2023
SECTION G: INVESTMENT MONITORING
Table G8: Investment and Capital Price Inflation
Line | Description | Units | Field | Actual Year 2017-18 | Actual Year 2018-19 | Actual Year 2019-20 | Actual Year 2020-21 | Actual Year 2021-22 | Actual Year 2022-23 | Forecast Year 2023-24 | Forecast Year 2024-25 | Forecast Year 2025-26 | Forecast Year 2026-27 | Total SR21
Ref. |  |  | Type
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Inflation assumptions
G8.1 | Capital price inflation | % | I |  | 3.06% | 2.588% | 1.213% | 5.98% | 11.26% | 6.2% | 2% | 0.6% | 1.5%
G8.2 | Capital price inflation factor | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1341 | 1.2618 | 1.34 | 1.3668 | 1.375 | 1.3956
G8.3 | Cost inflation (RPI until 2021 and CPI from 2021/22; financial year average) | % | I |  | 3.06% | 2.588% | 1.213% | 3.98% | 10.06% | 5.5% | 1.3% | 0.6% | 1.5%
G8.4 | Inflation index (2017/18 base year) | Nr. | I/C | 1 | 1.0306 | 1.0573 | 1.0701 | 1.1127 | 1.2246 | 1.292 | 1.3088 | 1.3166 | 1.3364
Repair and refurbishment (Tier 1a) and Tier 2 Investment
G8.5 | Repair and refurbishment (Tier 1a) and Tier 2 investment pre-efficiency (2017/18 prices) | £m | I |  |  |  |  | 578.5838 | 648.8147 | 667.0745 | 672.5592 | 513.0534 | 418.4149
G8.6 | Repair and refurbishment (Tier 1a) and Tier 2 investment pre-efficiency (projected outturn prices based on capital price inflation) | £m | C |  |  |  |  | 656.1671 | 818.6681 | 893.8941 | 919.2687 | 705.4601 | 583.9599
G8.7 | Efficiency (projected outturn prices) | £m | I | bar: 4 to 9
G8.8 | Repair and refurbishment (Tier 1a) and Tier 2 investment post-efficiency (projected outturn prices) | £m | C |  |  |  |  | 656.1671 | 818.6681 | 893.8941 | 919.2687 | 705.4601 | 583.9599
G8.9 | Repair and refurbishment (Tier 1a) and Tier 2 investment post-efficiency (2017/18 prices; CPI based) | £m | C |  |  |  |  | 589.7126 | 668.5044 | 691.8788 | 702.3878 | 535.8077 | 436.9719 | 3625.2633
Completion investment
G8.10 | Completion investment post-efficiency (projected outturn prices) | £m | I |  |  |  |  | 118.2513 | 60.8761 | 48.733 | 33.0822 | 28.6186 | -5.2303
G8.11 | Completion investment post-efficiency (2017/18 prices; CPI based) | £m | C |  |  |  |  | 106.2752 | 49.71 | 37.7196 | 25.2772 | 21.7363 | -3.9138 | 236.8044
Expenditure Totals (Gross)
G8.12 | Total Investment (projected outturn prices) | £m | C |  |  |  |  | 774.4184 | 879.5442 | 942.627 | 952.3508 | 734.0786 | 578.7296
G8.13 | Total Investment (2017/18 prices) | £m | C |  |  |  |  | 695.9878 | 718.2144 | 729.5984 | 727.665 | 557.544 | 433.0581 | 3862.0677
Prepared by: ……………………………………………..
Checked by: ……………………………………………..
Authorised by: |  |  | Date: